## Sheet1
Helene Bowden Design Ltd.
This shows how much input needed even for smaller tasks like new WC
21 Highgate High Street
Draft scope of works
1 | Preliminaries/Site Set up:
Prepare site and lay down floor/wall protection outside construction area
Strip out/demolition and rubbish disposal (collection only - no skip)
Existing WC and low level cistern
Hack off existing wall tiles and prep existing walls to receive new
Areas :
850 x 1300mm 2 no.
1335 x 1300mm 1 no.
800 x 1300 1 no.
Removal of existing low level electrical heater
Removal of cloakroom basin and waste
Cap off existing water outlet
Strip out existing vinyl floor
Strip out trunking to wall mounted electrical light
Removal of existing skirting board
3 | Electrics
Install new low level electrical heater and amend wiring as required
Rewire existing wall mounted light for chasing in
5 | General carpentry:
New stud box frame for wall mounted WC cistern approx 150 x 850 x 900h
Fit new door handle on bathroom door (designer supply)
To be discussed: possible boxing in of mains water pipe with stopcock access panel above WC
6 | Plastering
Skim out as necessary walls/ceilings above tiling areas (if required)
1000m to 2.2m H
space approx 1.45m x. 85W x 2.2H
7 | Plumbing installation
Install wall mounted concealed cistern WC with bolt fixings
Renew exisitng pipework where required (TBC)
Install flush plate into cistern frame
Fit 500 x 220mm wall mounted basin
Fit deck mounted tap and bottle trap waste
9 | Cistern shelf and basin splashback
To be supplied fitted by stone specialist- attend on site
10 | Surface Tiling
Sheet mosaics, 30 x 27cm web backing - install and grout
Areas:
1335 x 1000mm
850 x 1000mm 2 no.
800 x 1000mm 1 no.
Include tile edging to datum line (designer supply)
Bathroom floor: Client supply vinyl plank tiles
11 | Decorations:
sand down, fill and make good all paintable surfaces
Paint all walls ceiling mist coat, 2 top coats
Paint windows and woodwork (window frame, architrave, door)
Finishing paint colour supplied by Designer
Leave site clean and tidy of dust and and waste and fit for client use