## Sheet1
| The Worlds End Camden External Works | [12 empty] | 2014-04-01 | [32 empty] | 2014-05-01 | [30 empty] | 2014-06-01 | [29 empty] | 2014-07-01 | [30 empty] | 2014-08-01 | [30 empty] | 2014-09-01 | [29 empty] | 2014-10-01 | [30 empty] | 2014-11-01 | [29 empty] | 2014-12-01 | [30 empty] | 2015-01-01 | [30 empty] | 2015-02-01 | [27 empty] | 2015-03-01
|  | Pre-start, Preliminary works, Tennant notifications & scaffold license applications | [37 empty] | Wk1 | [6 empty] | Wk2 | [6 empty] | Wk3 | [6 empty] | Wk4 | [6 empty] | Wk5 | [6 empty] | Wk6 | [6 empty] | Wk7 | [6 empty] | Wk8 | [5 empty] | Wk9 | [6 empty] | Wk10 | [7 empty] | Wk11 | [6 empty] | Wk12 | [6 empty] | Wk13 | [6 empty] | Wk14 | [6 empty] | Wk15 | [6 empty] | Wk16 | [6 empty] | Wk17 |  |  |  |  | Wk18 | [6 empty] | Wk19 | [6 empty] | Wk20 | [6 empty] | Wk21 | [6 empty] | Wk22 | [6 empty] | Wk23 | [7 empty] | Wk24 | [6 empty] | Wk25 | [6 empty] | Wk26 | [5 empty] | Wk27 | [6 empty] | Wk28 | [7 empty] | Wk29 | [6 empty] | Wk30 | [6 empty] | Wk31 | [6 empty] | Wk32 | [6 empty] | Wk33 | [6 empty] | Wk34 | [6 empty] | Wk35 | [6 empty] | Wk36 | [6 empty] | Wk37 | [6 empty] | Wk38 | [6 empty] | Wk39 | [6 empty] | Wk40 | [6 empty] | Wk41 | [6 empty] | Wk42 | [6 empty] | Wk43 | [6 empty] | Wk44 | [6 empty] | Wk45 | [6 empty] | Wk46 | [6 empty] | Wk47 | [6 empty] | Wk48 | [6 empty] | Wk50
| ITEM | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
|  | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
1 | Tenant Notifications
2 | License Application
3 | Site set-up
4 | Health & Safety Documentation
5 | Pre-Start meeting
6 | License Application/internal works
7 | Drawing/layout approval (toilets)
8 | Design Approval (toilets)
9 | Pre Start Meeting (toilets)
Site Meetings
10 | SCAFFOLD ERECTION
11 | Camden high st elevation | bar: Pre-start, Preliminary works, Tennant notifications & scaffold license applications M 21 to Wk1 F 25; Wk1 M 28 to Wk2 F 2; Wk2 M 5 to Wk2 W 7
12 | Camden Rd elevation(front) | bar: Wk2 M 5 to Wk3 F 9; Wk3 M 12 to Wk4 F 16; Wk4 M 19 to Wk5 F 23
13 | Greenland st elevation | bar: Wk5 M 26 to Wk6 F 30; Wk6 M 2 to Wk7 F 6
14 | Bayham St elevation | bar: Wk7 M 9 to Wk8 F 13; Wk8 M 16 to Wk9 F 20
Camden Rd Elevation(rear) | bar: Wk9 M 23 to Wk10 F 27
15 | MEDIA HOARDING
16 | Camden high st elevation | bar: Wk2 W 7 to Wk3 F 9; Wk3 M 12 to Wk4 F 16; Wk4 M 19 to Wk4 W 21
17 | Camden Rd elevation (front) | bar: Wk5 T 22 to Wk5 F 23; Wk5 M 26 to Wk6 F 30; Wk6 M 2 to Wk6 W 4
18 | Greenland st elevation | bar: Wk7 T 5 to Wk7 F 6; Wk7 M 9 to Wk8 T 12
19 | Bayham St elevation | bar: Wk8 F 13; Wk8 M 16 to Wk9 F 20
Camden Rd elevation (rear) | bar: Wk9 T 19 to Wk9 F 20; Wk9 M 23 to Wk10 F 27
Ground Floor Toilets (Gents)
Install new water tanks to roof | bar: Wk1 T 24 to Wk1 F 25
Remove catering area | bar: Pre-start, Preliminary works, Tennant notifications & scaffold license applications M 21 to Wk1 T 24
Form new openings for staff access | bar: Wk1 T 24 to Wk1 F 25; Wk1 M 28
Form new gents wc's lobbies etc | bar: Wk1 T 29 to Wk2 F 2
1st Fix M&E | bar: Wk1 T 24 to Wk1 F 25; Wk1 M 28 to Wk1 T 29
Resin Floors
New drainage | bar: Wk2 F 2
Form cubicles/vanity units etc | bar: Wk2 F 2; Wk2 M 5 to Wk2 T 6
Tiling to all areas | bar: Wk2 M 5 to Wk3 T 8
2nd fix electrics | bar: Wk2 T 6 to Wk2 W 7
Joinery works/doors etc | bar: Wk2 W 7 to Wk3 F 9
Builders clean | bar: Wk3 F 9
Handover gents wc's | bar: Wk3 F 9
Ground Floor Toilets (Ladies)
Stripout wc cubicles,sanitryware etc | bar: Wk3 M 12 to Wk3 T 13
Carry out structural alterations | bar: Wk3 W 14 to Wk4 F 16; Wk4 M 19
Form new lobby | bar: Wk4 M 19 to Wk4 T 20
1st Fix M&E | bar: Wk4 M 19 to Wk4 W 21
Resin Floors
New drainage | bar: Wk5 T 22 to Wk5 F 23
Form cubicles/vanity units etc | bar: Wk5 M 26 to Wk5 W 28
Tiling to all areas | bar: Wk5 T 27 to Wk6 F 30
2nd fix electrics | bar: Wk6 T 29 to Wk6 F 30
Joinery works/doors etc | bar: Wk6 F 30; Wk6 M 2 to Wk6 T 3
Builders clean | bar: Wk6 T 3
Handover ladies wc's | bar: Wk6 W 4
Basement Toilets (Ladies)
Stripout wc cubicles,sanitryware etc | bar: Wk7 M 9 to Wk7 T 10
Form new lobby | bar: Wk7 T 10
1st Fix M&E | bar: Wk7 T 10 to Wk7 W 11
Resin Floors
New drainage | bar: Wk8 F 13
Form cubicles/vanity units etc | bar: Wk8 T 12 to Wk8 F 13; Wk8 M 16
Tiling to all areas | bar: Wk8 M 16 to Wk9 T 19
2nd fix electrics | bar: Wk9 W 18 to Wk9 T 19
Joinery works/doors etc | bar: Wk9 T 19 to Wk9 F 20
Builders clean | bar: Wk9 F 20
Handover ladies wc's | bar: Wk9 F 20
Basement Toilets (Gents)
Stripout wc cubicles,sanitryware etc | bar: Wk9 M 23 to Wk10 T 26
Carry out structural alterations | bar: Wk10 T 26 to Wk10 F 27; Wk10 M 30 to Wk10 W 2
Form new lobby | bar: Wk10 T 1 to Wk10 W 2
1st Fix M&E | bar: Wk10 T 1 to Wk11 F 4
Resin Floors
New drainage | bar: Wk11 F 4
Form cubicles/vanity units etc | bar: Wk11 M 7 to Wk11 W 9
Tiling to all areas | bar: Wk11 T 8 to Wk12 F 11
2nd fix electrics | bar: Wk11 W 9 to Wk12 F 11
Joinery works/doors etc | bar: Wk11 W 9 to Wk12 F 11
Builders clean | bar: Wk12 F 11
Handover gents wc's | bar: Wk12 F 11
20 | Masonry Repairs
21 | Camden high st elevation | bar: Wk3 M 12 to Wk4 F 16; Wk4 M 19 to Wk5 F 23; Wk5 M 26 to Wk6 F 30; Wk6 M 2 to Wk7 F 6; Wk7 M 9 to Wk8 F 13
22 | Camden Rd elevation (front) | bar: Wk7 M 9 to Wk8 F 13; Wk8 M 16 to Wk9 F 20; Wk9 M 23 to Wk10 F 27
23 | Greenland st elevation | bar: Wk8 M 16 to Wk9 F 20; Wk9 M 23 to Wk10 F 27; Wk10 M 30 to Wk11 F 4; Wk11 M 7 to Wk12 F 11
Bayham St elevation | bar: Wk12 M 14 to Wk13 F 18; Wk13 M 21 to Wk14 F 25; Wk14 M 28 to Wk15 F 1; Wk15 M 4 to Wk16 F 8; Wk16 M 11 to Wk17 F 15; Wk17 M 18 to Wk18 F 22
24 | Camden Rd elevation (rear) | bar: Wk18 M 25 to Wk19 F 29; Wk19 M 1 to Wk20 F 5; Wk20 M 8 to Wk21 F 12; Wk21 M 15 to Wk22 F 19
25 | Widow repairs/Replacement
26 | Camden high st elevation
27 | Camden Rd elevation (front)
28 | Greenland st elevation
29 | Bayham St elevation
30 | Camden Rd elevation (rear)
31 | Replacement doors/timber
32 | Camden high st elevation | bar: Wk5 M 26 to Wk6 F 30
33 | Camden Rd elevation (front) | bar: Wk6 F 30; Wk6 M 2 to Wk6 W 4
34 | Greenland st elevation | bar: Wk6 W 4 to Wk7 F 6
35 | Bayham St elevation | bar: Wk7 M 9 to Wk7 T 10
36 | Camden Rd elevation (rear) | bar: Wk7 M 9 to Wk7 T 10
37 | Gutter repairs/Parapets
38 | Camden high st elevation | bar: Wk7 W 11 to Wk8 F 13; Wk8 M 16 to Wk9 F 20
39 | Camden Rd elevation (front) | bar: Wk7 W 11 to Wk8 F 13; Wk8 M 16 to Wk9 F 20
40 | Greenland st elevation | bar: Wk9 F 20; Wk9 M 23 to Wk9 T 24
41 | Bayham St elevation | bar: Wk9 F 20; Wk9 M 23 to Wk10 T 26
42 | Camden Rd elevation (rear) | bar: Wk9 F 20; Wk9 M 23 to Wk10 F 27; Wk10 M 30 to Wk11 F 4
43 | Dormer Repairs
44 | Camden high st elevation | bar: Wk11 M 7 to Wk12 F 11; Wk12 M 14 to Wk13 F 18
45 | Camden Rd elevation (front) | bar: Wk12 T 15 to Wk13 F 18
46 | Greenland st elevation | bar: Wk12 T 15 to Wk13 F 18
47 | Bayham St elevation
48 | Camden Rd elevation (rear) | bar: Wk13 M 21 to Wk14 F 25
External lighting (relamp/repair)
Camden high st elevation | bar: Wk14 M 28 to Wk15 T 31
Camden Rd elevation (front) | bar: Wk14 W 30 to Wk15 F 1; Wk15 M 4 to Wk15 T 5
Greenland st elevation | bar: Wk15 T 5 to Wk15 W 6
Bayham St elevation | bar: Wk15 W 6
Camden Rd elevation (rear) | bar: Wk16 T 7; Wk16 T 12 to Wk17 T 14; Wk18 W 20 to Wk18 F 22
Decorations Externally
Camden high st elevation | bar: Wk16 M 11 to Wk17 F 15; Wk17 M 18 to Wk18 F 22; Wk18 M 25 to Wk19 F 29; Wk19 M 1 to Wk20 F 5; Wk20 M 8 to Wk21 F 12; Wk21 M 15 to Wk22 F 19; Wk22 M 22 to Wk23 F 26
Camden Rd elevation (front) | bar: Wk16 M 11 to Wk17 F 15; Wk17 M 18 to Wk18 F 22; Wk18 M 25 to Wk19 F 29; Wk19 M 1 to Wk20 F 5; Wk20 M 8 to Wk21 F 12; Wk21 M 15 to Wk22 F 19; Wk22 M 22 to Wk23 F 26
Greenland st elevation | bar: Wk23 M 29 to Wk24 F 3; Wk24 M 6 to Wk25 F 10
Bayham St elevation | bar: Wk25 M 13 to Wk26 F 17; Wk26 M 20 to Wk27 F 24
Camden Rd elevation (rear) | bar: Wk23 M 29 to Wk24 F 3; Wk24 M 6 to Wk25 F 10; Wk25 M 13 to Wk26 F 17; Wk26 M 20 to Wk27 F 24
Internal courtyard repairs(windows)
Carry out window repairs | bar: Wk27 T 21 to Wk27 F 24; Wk27 M 27 to Wk28 F 31; Wk28 M 3 to Wk28 T 4
Carry out asphalt repairs | bar: Wk27 T 21 to Wk27 F 24; Wk27 M 27 to Wk28 F 31; Wk28 M 3 to Wk28 T 4
REMOVE MEDIA HOARDING
Camden high st elevation | bar: Wk29 W 5 to Wk29 F 7; Wk29 M 10 to Wk30 F 14
Camden Rd elevation (front) | bar: Wk29 W 5 to Wk29 F 7; Wk29 M 10 to Wk30 F 14
Greenland st elevation | bar: Wk29 W 5 to Wk29 F 7; Wk29 M 10 to Wk30 F 14
Bayham St elevation | bar: Wk29 W 5 to Wk29 F 7; Wk29 M 10 to Wk30 F 14
Camden Rd elevation (rear) | bar: Wk29 W 5 to Wk29 F 7; Wk29 M 10 to Wk30 F 14
CLEANDOWN BUILDING
Camden high st elevation | bar: Wk30 M 17 to Wk31 T 20
Camden Rd elevation (front) | bar: Wk31 T 20 to Wk31 F 21; Wk31 M 24 to Wk32 W 26
Greenland st elevation | bar: Wk32 W 26 to Wk32 F 28
Bayham St elevation | bar: Wk31 T 25 to Wk32 T 27
Camden Rd elevation (rear) | bar: Wk32 W 26 to Wk32 F 28
UNDERPINNING WORKS | bar: Wk32 W 26 to Wk32 F 28
Cut out floor & wall for new padstones | bar: Wk32 W 26 to Wk32 F 28
Supply & fit structural steelwork | bar: Wk32 W 26 to Wk32 F 28
Carry out section a-d of underpinning | bar: Wk33 W 3 to Wk33 F 5; Wk33 M 8 to Wk34 F 12; Wk34 M 15 to Wk35 F 19
Carry out section e-j of underpinning | bar: Wk36 W 24 to Wk36 F 26; Wk36 M 29 to Wk37 F 2; Wk37 M 5 to Wk37 T 6
Drying times for sectional works | bar: Wk38 W 7 to Wk42 F 6
Make good all surfaces | bar: Wk42 M 9 to Wk43 F 13; Wk43 M 16 to Wk44 W 18
Remove spoil from site | bar: Wk44 M 23 to Wk45 F 27; Wk45 M 2 to Wk46 F 6
REMOVE SCAFFOLDING
Camden high st elevation | bar: Wk32 M 1 to Wk33 F 5; Wk46 M 9 to Wk47 F 13; Wk47 M 16 to Wk48 F 20
Camden Rd elevation (front) | bar: Wk33 M 8 to Wk34 T 11
Greenland st elevation | bar: Wk34 T 11 to Wk34 F 12; Wk34 M 15 to Wk34 T 16
Bayham St elevation | bar: Wk35 W 17 to Wk35 F 19; Wk35 M 22
Camden Rd elevation (rear) | bar: Wk35 T 23 to Wk36 F 26
HANDOVER COMPLETE SITE | bar: Wk37 W 31 to Wk37 F 2; Wk38 W 7 to Wk38 F 9; Wk39 W 14 to Wk39 F 16; Wk40 W 21 to Wk40 F 23; Wk41 W 28 to Wk41 F 30; Wk42 W 4 to Wk42 F 6; Wk43 W 11 to Wk43 F 13; Wk44 W 18 to Wk44 F 20; Wk45 W 25 to Wk45 F 27; Wk46 W 4 to Wk46 F 6; Wk47 W 11 to Wk47 F 13; Wk48 W 18 to Wk48 F 20; Wk50 W 25 to Wk50 F 27