ADDENDUM ‘B’

SPACE BASEMENTS LTD

PROGRAMME FOR ENABLING WORKS, CONSTRUCTION AND RESTORATION

FOR

# FORMATION OF HABITABLE SPACE WITHIN EXISTING BASEMENT

AT

5, ALDRED ROAD, WEST HAMPSTEAD

- Site preparation including removal of front wall and hedge, temporary access to ground floor, removal of soil, boarding etc from front garden.

- Erect hoarding to front area incorporating screen at pavement edge, overhead chute and all Health and safety signage for protection of the public and house owners.

- Excavate in front garden to expose front wall and foundations of house.

- Excavate for front light well and garden retaining wall, install supporting shuttering to perimeter.

- Form opening into existing basement under bay window and door to basement together with all necessary supports including new steel beam.

- Excavate to lower ground level within front half of area of basement under front living room down to new formation level.

- Excavate for underpin existing foundations to front area in accordance with Structural Engineer’s details and sequencing.

- Install steel beam to support ground floor joists under front living room.

- Repeat sequence as noted in Items 6 and 7 to rear half of area under ground floor living room.

- Form openings in cross wall and install steel beams.

- Repeat sequencing as Items 6 and 7 to rear area including existing understairs store.

- Adapt existing drain pipework running from back of area to front light well as noted on the drawings, as work proceeds, with temporary connection to existing manhole.

- On completion of structural works in basement, rebuild walling to bay window including extending down to new level.

- Form strip foundations for hall under ground floor access, adapt existing manhole and form permanent drainage connection, reinforced concrete slab, steps and retaining wall to front lightwell/access.

- Connect

- Build cavity wall to form front hall.

- Carry out fit out works to completion including rendering and paving slabs etc to front lightwell/access.

- Fit new railings to front wall.

- Clear site, remove hoarding.

- All surplus spoil, rubbish and debris to be removed from as work proceeds.

A. T. Green Builders Ltd – 30th July 2010