## Sheet1
|  |  |  | PROJECT No | [5 empty] | Risk Assessment No |  |  | 1 | [6 empty] | Final Risk Factor
|  |  | Cient Name |  | Higgins Construction |  |  |  |  | Activity |  | Removal of Contaminated Soil |  |  |  | Location | Plender Street, Camden |  |  |  | 5
Assessment Owner: |  |  | Prodem Ltd |  |  | Assessment by: Name |  |  | James Friar (Prodem Ltd) |  |  |  |  | Approved by: Name |  |  | Mick Hunt H&S Manager
Risk Factor = S x O
Re-Assessment is required by Safety Advisor if Final Risk Factor is RED | [14 empty] | Occurrence |  |  |  |  | RF = Final
Proceed with caution if Final Risk Factor is AMBER | [14 empty] | 5 | 4 | 3 | 2 | 1 | RI = Initial
Severity | 5 | Catastrophe |  |  |  |  | Occurrence | 5 | Certain |  |  |  | Severity | 5 | 25 | 20 | 15 | 10 | 5 | 9 - 25 Red
| 4 | Major injury/dangerous occurrence/major pollution incident | [5 empty] | 4 | Probable |  |  |  |  | 4 | 20 | 16 | 12 | 8 | 4
| 3 | More than 7 days off work | [5 empty] | 3 | Possible |  |  |  |  | 3 | 15 | 12 | 9 | 6 | 3 | 5 - 8 Amber
| 2 | Less than 7 days off work/minor pollution incident | [5 empty] | 2 | Unlikely |  |  |  |  | 2 | 10 | 8 | 6 | 4 | 2
| 1 | Minor injury/no lost hours | [5 empty] | 1 | Extremely unlikely |  |  |  |  | 1 | 5 | 4 | 3 | 2 | 1 | < 4 Green
No | Activity/Operation |  | Hazards Identified |  |  | At Risk |  | S | O | RI | Preventative and Protective Measures | [5 empty] | Action By |  | S | O | RF
1 | ACCESSING / TRAVELLING AROUND SITE |  | SITE DEBRIS ---cuts, bruises sprains. Collision with plant |  |  | Site operatives and visitors |  | 4 | 3 | 12 | GOOD HOUSEKEEPING BY AND OTHER SITE OPERATIVES. BANKSMEN MUST BE USED WHEN REVERSING VEHICLES. ALL OPERATIVES MUST OBSERVE SIGNATE NOT ENTER UNAUTHORISED AREAS. PPE must be worn and traffic routes clearly marked | [5 empty] | Prodem |  | 4 | 1 | 4
2 | MANUAL HANDLING |  | MUSCOLETAL INJURIES |  |  | Site operatives |  | 3 | 3 | 9 | Staff are trained in lifting techniques and provided with suitable equipment for task. Double lifting will be used as required. Gloves will be worn to prevent cuts and abrasions., steel will be removed in small managable sections. | [5 empty] | Prodem |  | 3 | 1 | 3
3 | NOISE |  | TINITIS HEARING DAMAGE |  |  | Site operatives and others |  | 3 | 3 | 9 | PROVIDE HEARING PROTECTION AT 80db ENSURE ITS WORN AT 85db. USE LOW NOISE EQUIPMENT WHERE POSSIBLE. ERECT SIGNAGE AS REQUIRED. WORK AWAY FROM THIRD PARTIES WHERE POSSIBLE | [5 empty] | Prodem |  | 3 | 1 | 3
4 | REFUELLING PLANT |  | Slips/ falls Dermatitis Environmental impact due to spillage |  |  | Site operatives |  | 3 | 2 | 6 | All drivers to be trained in operation of fuel pumps. Spill kits must be kept on site and readily available All spills to be cleaned up immediately. Apply barrier cream before operation. Wash hands after operation. PPE to include impervious disposable gloves. | [5 empty] | Prodem |  | 3 | 1 | 3
5 | LOADING UNLOADING PLANT |  | Plant falling from loader Trapping Injury to operatives. |  |  | Site operatives and others |  | 3 | 2 | 6 | Loading area of sufficient size Transporters to be positioned on firm ground brakes on. Loading/unloading carried out at slowest possible speed and with utmost care. Persons not involved in the process are kept clear. Driver of plant is trained / experianced. Banksmen to be employed both and off the transporters. PPE to be appropriate to task issue and used e.g safety boots, hard hats, gloves and high vis vests. | [5 empty] | Prodem |  | 3 | 1 | 3
6 | ON SITE PLANT MANOEUVRES |  | Collision with persons Overturning Collision with other plant Equipment failure |  |  | Site operatives |  | 3 | 2 | 6 | Only trained drivers are to be permitted to use plant. Plant is to be fitted with reversing alarm / flashing amber beacon. All plant to be in safe condition, equipped with all necessary safety devices, regularly maintained and complying with PUWER regulations. Plant is to be accompanied by trained banksman where vision could be impaired. Organize segregated pedestrian route on site. Banksman/Operatives to wear high visibility tabard or jacket. All operatives are to be conversant with the safe system of work. | [5 empty] | Prodem |  | 3 | 1 | 3
7 | EXCAVATION OF CONTAMINATED MATERIAL |  | Contamination from materials being worked Striking live services/cables Noise |  |  | Site operatives |  | 4 | 3 | 12 | Experienced and trained operators used. Existing contamination/suitable controls identified prior to works. Cables/services identified/located on drawings. Equipment examined/inspected/maintained as per requirements under PUWER regulations (records kept). Shoring/batter back/step excavation as appropriate. Ensure scrupulous personal hygiene. Ori nasal masks to BS EN 149. Ear protection, gloves, hi-vi vests, foot protection. | [5 empty] | Prodem |  | 4 | 2 | 8
8 | WORKING AROUND CONTAMINATED GROUND |  | Contamination with substance being worked Contamination from ground |  |  | Site operatives |  | 4 | 3 | 12 | Exclusion zones are set up around the working area. Operatives are trained to recognize and avoid contamination hazards. PPE to include impervious gloves, wellingtons, goggles to EN166 (Full face visor preferred), ori-nasal mask to EN149. Operatives are encouraged to use barrier cream. Ensure all operatives maintain scrupulous personal hygiene – wash thoroughly before eating, drinking, smoking. | [5 empty] | Prodem |  | 4 | 2 | 8
9 | WORKING AROUND LIVE SERVICES |  | Explosion / fire resulting from contact with live electricity cables Burns resulting from contact with live electricity cables Electrocution resulting from contact with live electricity cables Explosion / fire resulting from damage to gas pipes Poisoning / asphyxiation resulting from damage to other pipelines Flooding / subsidence resulting from damage to water pipes / sewers Biological contamination resulting from damage to sewers Injury resulting from damage to water pipes / sewers |  |  | Site operatives |  | 5 | 3 | 15 | Obtain rellivent permits of isolation and termination certificates for disconnection of services. | [5 empty] | Prodem |  | 5 | 2 | 10
Obtain plans of all services from owners / providers. Any live services must be clearly identified
Use a cable and pipe locator to trace underground services.
Hand dig trial holes using spades / shovels to confirm positions of underground services.
Ensure positions of services are clearly marked.
All operatives trained and competent to carry out the works.
10 | ANY OPERATION WHICH COULD PRESENT A HAZARD TO THE PUBLIC OR ANY OTHER PARTIES |  | Injury to member of the public or third party Contamination to a member of public |  |  | Members of public. |  | 4 | 3 | 12 | Site boundaries to be guarded using heras fencing, hoarding etc. Warning notices to be displayed around site boundaries. Screen, fans, debris netting to be used. All equipment/materials used on site to be in good condition. Induction training and PPE to be provided for all visitors to site. Safe working practices to be employed. Banksman to be used for controlling traffic movements. Constant interface between the public/local residents. Air Monitoring | [5 empty] | Prodem |  | 4 | 1 | 4