## Activities Schedule
ACTIVITY SCHEDULE
NEC3: Engineering and Construction Contract Option A: Priced contract with activity schedule.
Please provide duration for every activity by filling in the cells below. 46 Shirlock Road is filled in as an example (please modify)
Activities match the requirement types as per the pricing document
Completion of the works required in street properties are not expected to exceed 13 weeks and scaffold hire is not expected to exceed 12 weeks
Please provide the total price per property as per the pricing schedule in the yellow cells in column AO
Activity No | Property | Works | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26 | Wk 27 | Wk 28 | Wk 29 | Wk 30 | Wk 31 | Wk 32 | Wk 33 | Wk 34 | Wk 35 | Wk 36 | Price Totals
Activity 1 | 46 Shirlock Road | Scaffolding | bar: Wk 1; Wk 11
Activity 2 | 46 Shirlock Road | Asbestos Survey and Removal | bar: Wk 2
Activity 3 | 46 Shirlock Road | Roofing | bar: Wk 3 to Wk 5
Activity 4 | 46 Shirlock Road | Fabric Repairs and Decorations | bar: Wk 5 to Wk 9
Activity 5 | 46 Shirlock Road | Window Works | bar: Wk 5 to Wk 9
Activity 6 | 46 Shirlock Road | Energy Efficiency | bar: Wk 9
Activity 7 | 46 Shirlock Road | Communal Works | bar: Wk 6 to Wk 9
Activity 8 | 46 Shirlock Road | FRA Works | bar: Wk 8 to Wk 10
Activity 9 | 46 Shirlock Road | Estate Works | bar: Wk 7 to Wk 10
Activity 10 | 6 Lancaster Grove | Scaffolding | bar: Wk 1; Wk 11
Activity 11 | 6 Lancaster Grove | Asbestos Survey and Removal | bar: Wk 2
Activity 12 | 6 Lancaster Grove | Roofing | bar: Wk 3 to Wk 5
Activity 13 | 6 Lancaster Grove | Fabric Repairs and Decorations | bar: Wk 5 to Wk 9
Activity 14 | 6 Lancaster Grove | Window Works | bar: Wk 5 to Wk 9
Activity 15 | 6 Lancaster Grove | Energy Efficiency | bar: Wk 9
Activity 16 | 6 Lancaster Grove | Communal Works | bar: Wk 6 to Wk 9
Activity 17 | 6 Lancaster Grove | FRA Works | bar: Wk 8 to Wk 10
Activity 18 | 6 Lancaster Grove | Estate Works | bar: Wk 7 to Wk 10
Activity 19 | 4 South Hill Park Gardens | Scaffolding | bar: Wk 2; Wk 12
Activity 20 | 4 South Hill Park Gardens | Asbestos Survey and Removal | bar: Wk 3
Activity 21 | 4 South Hill Park Gardens | Roofing | bar: Wk 4 to Wk 6
Activity 22 | 4 South Hill Park Gardens | Fabric Repairs and Decorations | bar: Wk 6 to Wk 10
Activity 23 | 4 South Hill Park Gardens | Window Works | bar: Wk 6 to Wk 10
Activity 24 | 4 South Hill Park Gardens | Energy Efficiency | bar: Wk 10
Activity 25 | 4 South Hill Park Gardens | Communal Works | bar: Wk 7 to Wk 10
Activity 26 | 4 South Hill Park Gardens | FRA Works | bar: Wk 9 to Wk 11
Activity 27 | 4 South Hill Park Gardens | Estate Works | bar: Wk 8 to Wk 11
Activity 28 | 6 South Hill Park Gardens | Scaffolding | bar: Wk 2; Wk 12
Activity 29 | 6 South Hill Park Gardens | Asbestos Survey and Removal | bar: Wk 3
Activity 30 | 6 South Hill Park Gardens | Roofing | bar: Wk 4 to Wk 6
Activity 31 | 6 South Hill Park Gardens | Fabric Repairs and Decorations | bar: Wk 6 to Wk 10
Activity 32 | 6 South Hill Park Gardens | Window Works | bar: Wk 6 to Wk 10
Activity 33 | 6 South Hill Park Gardens | Energy Efficiency | bar: Wk 10
Activity 34 | 6 South Hill Park Gardens | Communal Works | bar: Wk 7 to Wk 10
Activity 35 | 6 South Hill Park Gardens | FRA Works | bar: Wk 9 to Wk 11
Activity 36 | 6 South Hill Park Gardens | Estate Works | bar: Wk 8 to Wk 11
Activity 37 | 17-19 Savernake Road | Scaffolding | bar: Wk 3; Wk 13
Activity 38 | 17-19 Savernake Road | Asbestos Survey and Removal | bar: Wk 4
Activity 39 | 17-19 Savernake Road | Roofing | bar: Wk 5 to Wk 7
Activity 40 | 17-19 Savernake Road | Fabric Repairs and Decorations | bar: Wk 7 to Wk 11
Activity 41 | 17-19 Savernake Road | Window Works | bar: Wk 7 to Wk 11
Activity 42 | 17-19 Savernake Road | Energy Efficiency | bar: Wk 11
Activity 43 | 17-19 Savernake Road | Communal Works | bar: Wk 8 to Wk 11
Activity 44 | 17-19 Savernake Road | FRA Works | bar: Wk 10 to Wk 12
Activity 45 | 17-19 Savernake Road | Estate Works | bar: Wk 9 to Wk 12
Activity 46 | 52 Roderic Road | Scaffolding | bar: Wk 3; Wk 13
Activity 47 | 52 Roderic Road | Asbestos Survey and Removal | bar: Wk 4
Activity 48 | 52 Roderic Road | Roofing | bar: Wk 5 to Wk 7
Activity 49 | 52 Roderic Road | Fabric Repairs and Decorations | bar: Wk 7 to Wk 11
Activity 50 | 52 Roderic Road | Window Works | bar: Wk 7 to Wk 11
Activity 51 | 52 Roderic Road | Energy Efficiency | bar: Wk 11
Activity 52 | 52 Roderic Road | Communal Works | bar: Wk 8 to Wk 11
Activity 53 | 52 Roderic Road | FRA Works | bar: Wk 10 to Wk 12
Activity 54 | 52 Roderic Road | Estate Works | bar: Wk 9 to Wk 12
Activity 55 | 88 Mansfield Road | Scaffolding | bar: Wk 4; Wk 14
Activity 56 | 88 Mansfield Road | Asbestos Survey and Removal | bar: Wk 5
Activity 57 | 88 Mansfield Road | Roofing | bar: Wk 6 to Wk 8
Activity 58 | 88 Mansfield Road | Fabric Repairs and Decorations | bar: Wk 8 to Wk 12
Activity 59 | 88 Mansfield Road | Window Works | bar: Wk 8 to Wk 12
Activity 60 | 88 Mansfield Road | Energy Efficiency | bar: Wk 12
Activity 61 | 88 Mansfield Road | Communal Works | bar: Wk 9 to Wk 12
Activity 62 | 88 Mansfield Road | FRA Works | bar: Wk 11 to Wk 13
Activity 63 | 88 Mansfield Road | Estate Works | bar: Wk 10 to Wk 13
Activity 64 | 19 Downside Crescent | Scaffolding | bar: Wk 4; Wk 14
Activity 65 | 19 Downside Crescent | Asbestos Survey and Removal | bar: Wk 5
Activity 66 | 19 Downside Crescent | Roofing | bar: Wk 6 to Wk 8
Activity 67 | 19 Downside Crescent | Fabric Repairs and Decorations | bar: Wk 8 to Wk 12
Activity 68 | 19 Downside Crescent | Window Works | bar: Wk 8 to Wk 12
Activity 69 | 19 Downside Crescent | Energy Efficiency | bar: Wk 12
Activity 70 | 19 Downside Crescent | Communal Works | bar: Wk 9 to Wk 12
Activity 71 | 19 Downside Crescent | FRA Works | bar: Wk 11 to Wk 13
Activity 72 | 19 Downside Crescent | Estate Works | bar: Wk 10 to Wk 13
Activity 73 | 2 Estelle Road | Scaffolding | bar: Wk 5; Wk 15
Activity 74 | 2 Estelle Road | Asbestos Survey and Removal | bar: Wk 6
Activity 75 | 2 Estelle Road | Roofing | bar: Wk 7 to Wk 9
Activity 76 | 2 Estelle Road | Fabric Repairs and Decorations | bar: Wk 9 to Wk 13
Activity 77 | 2 Estelle Road | Window Works | bar: Wk 9 to Wk 13
Activity 78 | 2 Estelle Road | Energy Efficiency | bar: Wk 13
Activity 79 | 2 Estelle Road | Communal Works | bar: Wk 10 to Wk 13
Activity 80 | 2 Estelle Road | FRA Works | bar: Wk 12 to Wk 14
Activity 81 | 2 Estelle Road | Estate Works | bar: Wk 11 to Wk 14
Activity 82 | 1-29 Grove Place | Scaffolding | bar: Wk 1 to Wk 3; Wk 15 to Wk 16
Activity 83 | 1-29 Grove Place | Asbestos Survey and Removal | bar: Wk 3 to Wk 4
Activity 84 | 1-29 Grove Place | Roofing | bar: Wk 5 to Wk 8
Activity 85 | 1-29 Grove Place | Fabric Repairs and Decorations | bar: Wk 7 to Wk 13
Activity 86 | 1-29 Grove Place | Window Works | bar: Wk 8 to Wk 13
Activity 87 | 1-29 Grove Place | Energy Efficiency | bar: Wk 12 to Wk 14
Activity 88 | 1-29 Grove Place | Communal Works | bar: Wk 11 to Wk 15
Activity 89 | 1-29 Grove Place | FRA Works | bar: Wk 12 to Wk 16
Activity 90 | 1-29 Grove Place | Estate Works | bar: Wk 14 to Wk 16
Activity 91 | 1 Roderic Road | Scaffolding | bar: Wk 5; Wk 15
Activity 92 | 1 Roderic Road | Asbestos Survey and Removal | bar: Wk 6
Activity 93 | 1 Roderic Road | Roofing | bar: Wk 7 to Wk 9
Activity 94 | 1 Roderic Road | Fabric Repairs and Decorations | bar: Wk 9 to Wk 13
Activity 95 | 1 Roderic Road | Window Works | bar: Wk 9 to Wk 13
Activity 96 | 1 Roderic Road | Energy Efficiency | bar: Wk 13
Activity 97 | 1 Roderic Road | Communal Works | bar: Wk 10 to Wk 13
Activity 98 | 1 Roderic Road | FRA Works | bar: Wk 12 to Wk 14
Activity 99 | 1 Roderic Road | Estate Works | bar: Wk 11 to Wk 14
Activity 100 | 58 Fleet Street | Scaffolding | bar: Wk 6; Wk 16
Activity 101 | 58 Fleet Street | Asbestos Survey and Removal | bar: Wk 7
Activity 102 | 58 Fleet Street | Roofing | bar: Wk 8 to Wk 10
Activity 103 | 58 Fleet Street | Fabric Repairs and Decorations | bar: Wk 10 to Wk 14
Activity 104 | 58 Fleet Street | Window Works | bar: Wk 10 to Wk 14
Activity 105 | 58 Fleet Street | Energy Efficiency | bar: Wk 14
Activity 106 | 58 Fleet Street | Communal Works | bar: Wk 11 to Wk 14
Activity 107 | 58 Fleet Street | FRA Works | bar: Wk 13 to Wk 15
Activity 108 | 58 Fleet Street | Estate Works | bar: Wk 12 to Wk 15
Activity 109 | 1-5 Oaktree House | Scaffolding | bar: Wk 6; Wk 16
Activity 110 | 1-5 Oaktree House | Asbestos Survey and Removal | bar: Wk 7
Activity 111 | 1-5 Oaktree House | Roofing | bar: Wk 8 to Wk 10
Activity 112 | 1-5 Oaktree House | Fabric Repairs and Decorations | bar: Wk 10 to Wk 14
Activity 113 | 1-5 Oaktree House | Window Works | bar: Wk 10 to Wk 14
Activity 114 | 1-5 Oaktree House | Energy Efficiency | bar: Wk 14
Activity 115 | 1-5 Oaktree House | Communal Works | bar: Wk 11 to Wk 14
Activity 116 | 1-5 Oaktree House | FRA Works | bar: Wk 13 to Wk 15
Activity 117 | 1-5 Oaktree House | Estate Works | bar: Wk 12 to Wk 15
Project Overheads