## Activities Schedule
ACTIVITY SCHEDULE
NEC3: Engineering and Construction Contract Option A: Priced contract with activity schedule.
Please provide duration for every activity by filling in the cells below. 13 Doynton St is filled in as an example (please modify)
Activities match the requirement types as per the pricing document
Completion of the works required in street properties are not expected to exceed 13 weeks and scaffold hire is not expected to exceed 12 weeks
Please provide the total price per property as per the pricing schedule in the yellow cells in column AO
Activity No | Property | Works | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26 | Wk 27 | Wk 28 | Wk 29 | Wk 30 | Wk 31 | Wk 32 | Wk 33 | Wk 34 | Wk 35 | Wk 36 | Price Totals
Activity 1 | 1-44 Denyer House | Scaffolding | bar: Wk 1 to Wk 9
Activity 2 | 1-44 Denyer House | Asbestos Survey and Removal | bar: Wk 1 to Wk 6
Activity 3 | 1-44 Denyer House | Communal Works | bar: Wk 2 to Wk 6
Activity 4 | 1-44 Denyer House | Roofing | bar: Wk 3 to Wk 9
Activity 5 | 1-44 Denyer House | Energy Efficiency | bar: Wk 5 to Wk 7
Activity 6 | 1-44 Denyer House | Window Works | bar: Wk 5 to Wk 8
Activity 7 | 1-44 Denyer House | Fabric Repairs and Decorations | bar: Wk 6 to Wk 11
Activity 8 | 1-44 Denyer House | Estate Works | bar: Wk 11 to Wk 12
Activity 9 | 111 Chetwynd Road, NW5 1DA | Scaffolding | bar: Wk 1 to Wk 6
Activity 10 | 111 Chetwynd Road, NW5 1DA | Asbestos Survey and Removal | bar: Wk 1 to Wk 2
Activity 11 | 111 Chetwynd Road, NW5 1DA | Communal Works | bar: Wk 2 to Wk 4
Activity 12 | 111 Chetwynd Road, NW5 1DA | Roofing | bar: Wk 2 to Wk 5
Activity 13 | 111 Chetwynd Road, NW5 1DA | Fabric Repairs and Decorations | bar: Wk 4 to Wk 6
Activity 14 | 111 Chetwynd Road, NW5 1DA | Energy Efficiency | bar: Wk 5
Activity 15 | 111 Chetwynd Road, NW5 1DA | Window Works | bar: Wk 5 to Wk 6
Activity 16 | 111 Chetwynd Road, NW5 1DA | Estate Works | bar: Wk 7
Activity 17 | 13 Doynton Street | Scaffolding | bar: Wk 1 to Wk 5
Activity 18 | 13 Doynton Street | Asbestos Survey and Removal | bar: Wk 2
Activity 19 | 13 Doynton Street | FRA Works | bar: Wk 2 to Wk 3
Activity 20 | 13 Doynton Street | Roofing | bar: Wk 2 to Wk 3
Activity 21 | 13 Doynton Street | Energy Efficiency | bar: Wk 3
Activity 22 | 13 Doynton Street | Window Works | bar: Wk 3
Activity 23 | 13 Doynton Street | Fabric Repairs and Decorations | bar: Wk 3 to Wk 5
Activity 24 | 13 Doynton Street | Estate Works | bar: Wk 6
Activity 25 | 1-10 Lissenden Mansions, | Scaffolding | bar: Wk 2 to Wk 11
Activity 26 | 1-10 Lissenden Mansions, | Asbestos Survey and Removal | bar: Wk 4
Activity 27 | 1-10 Lissenden Mansions, | Communal Works | bar: Wk 4 to Wk 5
Activity 28 | 1-10 Lissenden Mansions, | Roofing | bar: Wk 4 to Wk 9
Activity 29 | 1-10 Lissenden Mansions, | Energy Efficiency | bar: Wk 9
Activity 30 | 1-10 Lissenden Mansions, | Window Works | bar: Wk 9 to Wk 10
Activity 31 | 1-10 Lissenden Mansions, | Fabric Repairs and Decorations | bar: Wk 9 to Wk 12
Activity 32 | 11-20 LISSENDEN MANSIONS, NW5 1PP | Scaffolding | bar: Wk 2 to Wk 11
Activity 33 | 11-20 LISSENDEN MANSIONS, NW5 1PP | Asbestos Survey and Removal | bar: Wk 4
Activity 34 | 11-20 LISSENDEN MANSIONS, NW5 1PP | Communal Works | bar: Wk 4 to Wk 5
Activity 35 | 11-20 LISSENDEN MANSIONS, NW5 1PP | Roofing | bar: Wk 4 to Wk 9
Activity 36 | 11-20 LISSENDEN MANSIONS, NW5 1PP | Energy Efficiency | bar: Wk 9
Activity 37 | 11-20 LISSENDEN MANSIONS, NW5 1PP | Window Works | bar: Wk 9 to Wk 10
Activity 38 | 11-20 LISSENDEN MANSIONS, NW5 1PP | Fabric Repairs and Decorations | bar: Wk 9 to Wk 12
Activity 39 | 1-25 Troyes House | Scaffolding | bar: Wk 2 to Wk 10
Activity 40 | 1-25 Troyes House | Asbestos Survey and Removal | bar: Wk 2 to Wk 5
Activity 41 | 1-25 Troyes House | Roofing | bar: Wk 4 to Wk 10
Activity 42 | 1-25 Troyes House | Energy Efficiency | bar: Wk 7 to Wk 8
Activity 43 | 1-25 Troyes House | Fabric Repairs and Decorations | bar: Wk 8 to Wk 11
Activity 44 | 25 Herbert Street, (Flats A-B), NW5 4HA | Scaffolding | bar: Wk 3 to Wk 6
Activity 45 | 25 Herbert Street, (Flats A-B), NW5 4HA | Asbestos Survey and Removal | bar: Wk 3
Activity 46 | 25 Herbert Street, (Flats A-B), NW5 4HA | FRA Works | bar: Wk 4
Activity 47 | 25 Herbert Street, (Flats A-B), NW5 4HA | Roofing | bar: Wk 4
Activity 48 | 25 Herbert Street, (Flats A-B), NW5 4HA | Communal Works | bar: Wk 4 to Wk 5
Activity 49 | 25 Herbert Street, (Flats A-B), NW5 4HA | Window Works | bar: Wk 5
Activity 50 | 25 Herbert Street, (Flats A-B), NW5 4HA | Energy Efficiency | bar: Wk 5
Activity 51 | 25 Herbert Street, (Flats A-B), NW5 4HA | Fabric Repairs and Decorations | bar: Wk 5 to Wk 6
Activity 52 | 25 Herbert Street, (Flats A-B), NW5 4HA | Estate Works | bar: Wk 7
Activity 53 | 66 Leverton Street (Flats A-B), NW5 2NU | Scaffolding | bar: Wk 3 to Wk 8
Activity 54 | 66 Leverton Street (Flats A-B), NW5 2NU | Asbestos Survey and Removal | bar: Wk 3 to Wk 4
Activity 55 | 66 Leverton Street (Flats A-B), NW5 2NU | Communal Works | bar: Wk 4 to Wk 5
Activity 56 | 66 Leverton Street (Flats A-B), NW5 2NU | Roofing | bar: Wk 4 to Wk 7
Activity 57 | 66 Leverton Street (Flats A-B), NW5 2NU | Energy Efficiency | bar: Wk 7
Activity 58 | 66 Leverton Street (Flats A-B), NW5 2NU | Window Works | bar: Wk 7 to Wk 8
Activity 59 | 66 Leverton Street (Flats A-B), NW5 2NU | Fabric Repairs and Decorations | bar: Wk 7 to Wk 9
Activity 60 | 66 Leverton Street (Flats A-B), NW5 2NU | Estate Works | bar: Wk 9 to Wk 10
Activity 61 | 29 Grove Terrace, NW5 1PL | Scaffolding | bar: Wk 3 to Wk 8
Activity 62 | 29 Grove Terrace, NW5 1PL | Asbestos Survey and Removal | bar: Wk 3 to Wk 4
Activity 63 | 29 Grove Terrace, NW5 1PL | Communal Works | bar: Wk 4 to Wk 5
Activity 64 | 29 Grove Terrace, NW5 1PL | Roofing | bar: Wk 4 to Wk 5
Activity 65 | 29 Grove Terrace, NW5 1PL | Energy Efficiency | bar: Wk 5
Activity 66 | 29 Grove Terrace, NW5 1PL | Window Works | bar: Wk 5 to Wk 6
Activity 67 | 29 Grove Terrace, NW5 1PL | Fabric Repairs and Decorations | bar: Wk 5 to Wk 8
Activity 68 | 29 Grove Terrace, NW5 1PL | Estate Works | bar: Wk 9
Activity 69 | 30 Grove Terrace, NW5 1PL | Scaffolding | bar: Wk 3 to Wk 8
Activity 70 | 30 Grove Terrace, NW5 1PL | Asbestos Survey and Removal | bar: Wk 3 to Wk 4
Activity 71 | 30 Grove Terrace, NW5 1PL | Communal Works | bar: Wk 4 to Wk 5
Activity 72 | 30 Grove Terrace, NW5 1PL | Roofing | bar: Wk 4 to Wk 5
Activity 73 | 30 Grove Terrace, NW5 1PL | Energy Efficiency | bar: Wk 5
Activity 74 | 30 Grove Terrace, NW5 1PL | Window Works | bar: Wk 5 to Wk 6
Activity 75 | 30 Grove Terrace, NW5 1PL | Fabric Repairs and Decorations | bar: Wk 5 to Wk 8
Activity 76 | 30 Grove Terrace, NW5 1PL | Estate Works | bar: Wk 9
Activity 77 | 13 Mortimer Terrace, NW5 1LH | Scaffolding | bar: Wk 4 to Wk 7
Activity 78 | 13 Mortimer Terrace, NW5 1LH | Asbestos Survey and Removal | bar: Wk 4 to Wk 5
Activity 79 | 13 Mortimer Terrace, NW5 1LH | FRA Works | bar: Wk 4 to Wk 6
Activity 80 | 13 Mortimer Terrace, NW5 1LH | Energy Efficiency | bar: Wk 5
Activity 81 | 13 Mortimer Terrace, NW5 1LH | Window Works | bar: Wk 5 to Wk 6
Activity 82 | 13 Mortimer Terrace, NW5 1LH | Fabric Repairs and Decorations | bar: Wk 6 to Wk 7
Activity 83 | 13 Mortimer Terrace, NW5 1LH | Communal Works | bar: Wk 6 to Wk 8
Activity 84 | 25 Elaine Grove (Flats A-B), NW5 4QH | Scaffolding | bar: Wk 4 to Wk 10
Activity 85 | 25 Elaine Grove (Flats A-B), NW5 4QH | Asbestos Survey and Removal | bar: Wk 5
Activity 86 | 25 Elaine Grove (Flats A-B), NW5 4QH | Roofing | bar: Wk 5 to Wk 7
Activity 87 | 25 Elaine Grove (Flats A-B), NW5 4QH | FRA Works | bar: Wk 5 to Wk 6
Activity 88 | 25 Elaine Grove (Flats A-B), NW5 4QH | Energy Efficiency | bar: Wk 7
Activity 89 | 25 Elaine Grove (Flats A-B), NW5 4QH | Window Works | bar: Wk 7 to Wk 9
Activity 90 | 25 Elaine Grove (Flats A-B), NW5 4QH | Fabric Repairs and Decorations | bar: Wk 8 to Wk 10
Activity 91 | 25 Elaine Grove (Flats A-B), NW5 4QH | Estate Works | bar: Wk 11
Activity 92 | 128 Prince Of Wales Road | Scaffolding | bar: Wk 4 to Wk 7
Activity 93 | 128 Prince Of Wales Road | Asbestos Survey and Removal | bar: Wk 5
Activity 94 | 128 Prince Of Wales Road | FRA Works | bar: Wk 5 to Wk 6
Activity 95 | 128 Prince Of Wales Road | Energy Efficiency | bar: Wk 5
Activity 96 | 128 Prince Of Wales Road | Window Works | bar: Wk 5 to Wk 6
Activity 97 | 128 Prince Of Wales Road | Fabric Repairs and Decorations | bar: Wk 6 to Wk 7
Activity 98 | 128 Prince Of Wales Road | Communal Works | bar: Wk 6 to Wk 7
Activity 99 | 130 PRINCE OF WALES ROAD (FLATS A-B), NW5 3NE | Scaffolding | bar: Wk 4 to Wk 8
Activity 100 | 130 PRINCE OF WALES ROAD (FLATS A-B), NW5 3NE | Asbestos Survey and Removal | bar: Wk 5
Activity 101 | 130 PRINCE OF WALES ROAD (FLATS A-B), NW5 3NE | FRA Works | bar: Wk 5 to Wk 7
Activity 102 | 130 PRINCE OF WALES ROAD (FLATS A-B), NW5 3NE | Roofing | bar: Wk 5 to Wk 7
Activity 103 | 130 PRINCE OF WALES ROAD (FLATS A-B), NW5 3NE | Energy Efficiency | bar: Wk 7
Activity 104 | 130 PRINCE OF WALES ROAD (FLATS A-B), NW5 3NE | Window Works | bar: Wk 7
Activity 105 | 130 PRINCE OF WALES ROAD (FLATS A-B), NW5 3NE | Fabric Repairs and Decorations | bar: Wk 7 to Wk 8
Activity 106 | 130 PRINCE OF WALES ROAD (FLATS A-B), NW5 3NE | Estate Works | bar: Wk 9
Activity 107 | 5 Gillies Street | Scaffolding | bar: Wk 5 to Wk 9
Activity 108 | 5 Gillies Street | Asbestos Survey and Removal | bar: Wk 6
Activity 109 | 5 Gillies Street | Roofing | bar: Wk 6
Activity 110 | 5 Gillies Street | Energy Efficiency | bar: Wk 6
Activity 111 | 5 Gillies Street | Window Works | bar: Wk 6 to Wk 7
Activity 112 | 5 Gillies Street | Fabric Repairs and Decorations | bar: Wk 7 to Wk 9
Activity 113 | 5 Gillies Street | Estate Works | bar: Wk 10
Activity 114 | 10 Gillies Street, NW5 4DL | Scaffolding | bar: Wk 5 to Wk 9
Activity 115 | 10 Gillies Street, NW5 4DL | Asbestos Survey and Removal | bar: Wk 6
Activity 116 | 10 Gillies Street, NW5 4DL | Roofing | bar: Wk 6
Activity 117 | 10 Gillies Street, NW5 4DL | Energy Efficiency | bar: Wk 6
Activity 118 | 10 Gillies Street, NW5 4DL | Window Works | bar: Wk 6 to Wk 7
Activity 119 | 10 Gillies Street, NW5 4DL | Fabric Repairs and Decorations | bar: Wk 7 to Wk 9
Activity 120 | 10 Gillies Street, NW5 4DL | Estate Works | bar: Wk 10
Activity 121 | 11 Gillies Street, (Flats A-B), NW5 4DL | Scaffolding | bar: Wk 5 to Wk 10
Activity 122 | 11 Gillies Street, (Flats A-B), NW5 4DL | Asbestos Survey and Removal | bar: Wk 6
Activity 123 | 11 Gillies Street, (Flats A-B), NW5 4DL | FRA Works | bar: Wk 6 to Wk 7
Activity 124 | 11 Gillies Street, (Flats A-B), NW5 4DL | Roofing | bar: Wk 6 to Wk 9
Activity 125 | 11 Gillies Street, (Flats A-B), NW5 4DL | Communal Works | bar: Wk 7 to Wk 8
Activity 126 | 11 Gillies Street, (Flats A-B), NW5 4DL | Energy Efficiency | bar: Wk 9
Activity 127 | 11 Gillies Street, (Flats A-B), NW5 4DL | Window Works | bar: Wk 9
Activity 128 | 11 Gillies Street, (Flats A-B), NW5 4DL | Fabric Repairs and Decorations | bar: Wk 9 to Wk 10
Activity 129 | 11 Gillies Street, (Flats A-B), NW5 4DL | Estate Works | bar: Wk 11 to Wk 12
Activity 130 | 13 Oseney Crescent (Flats A-D), NW5 2AT | Scaffolding | bar: Wk 5 to Wk 11
Activity 131 | 13 Oseney Crescent (Flats A-D), NW5 2AT | Asbestos Survey and Removal | bar: Wk 6
Activity 132 | 13 Oseney Crescent (Flats A-D), NW5 2AT | Roofing | bar: Wk 6 to Wk 8
Activity 133 | 13 Oseney Crescent (Flats A-D), NW5 2AT | Energy Efficiency | bar: Wk 8
Activity 134 | 13 Oseney Crescent (Flats A-D), NW5 2AT | Communal Works | bar: Wk 8 to Wk 9
Activity 135 | 13 Oseney Crescent (Flats A-D), NW5 2AT | Window Works | bar: Wk 8 to Wk 9
Activity 136 | 13 Oseney Crescent (Flats A-D), NW5 2AT | Fabric Repairs and Decorations | bar: Wk 9 to Wk 11
Activity 137 | 13 Oseney Crescent (Flats A-D), NW5 2AT | Estate Works | bar: Wk 11 to Wk 12
Activity 138 | 8 Dale Road | Scaffolding | bar: Wk 6 to Wk 10
Activity 139 | 8 Dale Road | Asbestos Survey and Removal | bar: Wk 6 to Wk 7
Activity 140 | 8 Dale Road | FRA Works | bar: Wk 6 to Wk 8
Activity 141 | 8 Dale Road | Roofing | bar: Wk 7 to Wk 8
Activity 142 | 8 Dale Road | Energy Efficiency | bar: Wk 8
Activity 143 | 8 Dale Road | Window Works | bar: Wk 8 to Wk 9
Activity 144 | 8 Dale Road | Fabric Repairs and Decorations | bar: Wk 9 to Wk 10
Activity 145 | 8 Dale Road | Estate Works | bar: Wk 11
Activity 146 | 17 Ascham Street, (Flats A-B), NW5 2PB | Scaffolding | bar: Wk 6 to Wk 9
Activity 147 | 17 Ascham Street, (Flats A-B), NW5 2PB | Asbestos Survey and Removal | bar: Wk 6
Activity 148 | 17 Ascham Street, (Flats A-B), NW5 2PB | Roofing | bar: Wk 7
Activity 149 | 17 Ascham Street, (Flats A-B), NW5 2PB | FRA Works | bar: Wk 7 to Wk 8
Activity 150 | 17 Ascham Street, (Flats A-B), NW5 2PB | Energy Efficiency | bar: Wk 8
Activity 151 | 17 Ascham Street, (Flats A-B), NW5 2PB | Window Works | bar: Wk 8
Activity 152 | 17 Ascham Street, (Flats A-B), NW5 2PB | Fabric Repairs and Decorations | bar: Wk 9
Activity 153 | 17 Ascham Street, (Flats A-B), NW5 2PB | Communal Works | bar: Wk 9 to Wk 10
Activity 154 | 17 Ascham Street, (Flats A-B), NW5 2PB | Estate Works | bar: Wk 10 to Wk 11
Activity 155 | 19 Ascham Street | Scaffolding | bar: Wk 6 to Wk 10
Activity 156 | 19 Ascham Street | Asbestos Survey and Removal | bar: Wk 6
Activity 157 | 19 Ascham Street | FRA Works | bar: Wk 7 to Wk 8
Activity 158 | 19 Ascham Street | Roofing | bar: Wk 7 to Wk 8
Activity 159 | 19 Ascham Street | Energy Efficiency | bar: Wk 8
Activity 160 | 19 Ascham Street | Window Works | bar: Wk 8
Activity 161 | 19 Ascham Street | Fabric Repairs and Decorations | bar: Wk 9 to Wk 10
Activity 162 | 19 Ascham Street | Communal Works | bar: Wk 9 to Wk 10
Activity 163 | 19 Ascham Street | Estate Works | bar: Wk 11 to Wk 12
Activity 164 | 28 Leighton Road, (Flats A-B), NW5 2QE | Scaffolding | bar: Wk 6 to Wk 11
Activity 165 | 28 Leighton Road, (Flats A-B), NW5 2QE | Asbestos Survey and Removal | bar: Wk 7
Activity 166 | 28 Leighton Road, (Flats A-B), NW5 2QE | FRA Works | bar: Wk 7 to Wk 9
Activity 167 | 28 Leighton Road, (Flats A-B), NW5 2QE | Roofing | bar: Wk 7 to Wk 9
Activity 168 | 28 Leighton Road, (Flats A-B), NW5 2QE | Energy Efficiency | bar: Wk 9
Activity 169 | 28 Leighton Road, (Flats A-B), NW5 2QE | Window Works | bar: Wk 9
Activity 170 | 28 Leighton Road, (Flats A-B), NW5 2QE | Communal Works | bar: Wk 9 to Wk 11
Activity 171 | 28 Leighton Road, (Flats A-B), NW5 2QE | Fabric Repairs and Decorations | bar: Wk 10 to Wk 11
Activity 172 | 28 Leighton Road, (Flats A-B), NW5 2QE | Estate Works | bar: Wk 12
Activity 173 | 13 Winscombe Terrace, N19 5DG | Scaffolding | bar: Wk 7 to Wk 10
Activity 174 | 13 Winscombe Terrace, N19 5DG | Asbestos Survey and Removal | bar: Wk 7 to Wk 8
Activity 175 | 15 Winscombe Terrace, N19 5DG | FRA Works | bar: Wk 8 to Wk 9
Activity 176 | 13 Winscombe Terrace, N19 5DG | Energy Efficiency | bar: Wk 8
Activity 177 | 13 Winscombe Terrace, N19 5DG | Window Works | bar: Wk 8
Activity 178 | 13 Winscombe Terrace, N19 5DG | Fabric Repairs and Decorations | bar: Wk 9 to Wk 10
Activity 179 | 14 Winscombe Terrace, N19 5DG | Communal Works | bar: Wk 10
Project Overheads

## Sheet1
13 Doynton Street
13 Winscombe Terrace, N19 5DG
111 Chetwynd Road, NW5 1DA
29 Grove Terrace, NW5 1PL
30 Grove Terrace, NW5 1PL
13 Mortimer Terrace, NW5 1LH
1-10 Lissenden Mansions, | NW5 1PP
8 Dale Road | NW5 4NS
5 Gillies Street
11 Gillies Street, (Flats A-B), NW5 4DL
1-25 Troyes House | NW5 1PP
17 Ascham Street, (Flats A-B), NW5 2PB
19 Ascham Street
28 Leighton Road, (Flats A-B), NW5 2QE
25 Herbert Street, (Flats A-B), NW5 4HA
1-44 Denyer House | NW5 1BN
128 Prince Of Wales Road | NW5 3NE
11-20 LISSENDEN MANSIONS, NW5 1PP
13 Oseney Crescent (Flats A-D), NW5 2AT
130 PRINCE OF WALES ROAD (FLATS A-B), NW5 3NE
66 Leverton Street (Flats A-B), NW5 2NU
10 Gillies Street, NW5 4DL
25 Elaine Grove (Flats A-B), NW5 4QH
259 Eversholt Street, | NW1 1BA
28 St. Augustine's Road, (Flats A-D) | NW1 9RN
3 Princess Road, NW1 8JN
34 Camden Road & Flat (B) | NW1 9DP
38-40 Camden Road & Flats (A-C) | NW1 9DR
4 Bayham Street (Flats Grnd Flr & A-B), NW1 0ES
5 Princess Road (Flats A-C) | NW1 8JN
53 Princess Road, NW1 8JS
57 Oakley Square, NW1 1NJ
62 Oakley Square, NW1 1NJ
65 Harmood Street, NW1 8DT
67 St Augustine's Road, NW1 9RR
68 Harmood Street, NW1 8DS
7 Princess Road (Flats A-C) | NW1 8JN
70 Harmood Street, NW1 8DS
71 St Augustine's Road, NW1 9RR
72 Camden Street (Flats A-C), NW1 0DX
72 Harmood Street, NW1 8DS
79 St Augustine's Road, NW1 9RR
86 St Augustine's Road, NW1 9RP
93 St Augustine's Road, NW1 9RR