## Tender Brief
Better Homes Construction Framework
Call-Off Brief
Date: |  | 17th June 2016
Tender Ref: |  | Wave C packet 16 NW5
Lot: |  | Lot 2 Internal & External Works
Return Date: |  | 17th June 2016
Method of Pricing: |  | NEC3: Engineering and Construction Contract Option A: Priced contract with activity schedule.
Evaluation Criteria |  | PRICE (Most Economically Advantageous Tender)
Scope of Works Required |  | Tender Brief as set out in Works Information Part I Employers Data
Project Lead |  | Stephen Platt
Telephone: |  | 0207 974 3937
Email: |  | Stephen.Platt@camden.gov.uk
The bidder is required to provide the following sumissions
1 | This Call Off brief including the following documents included in this call document: the Form of Tender, the NEC3 Contract Data Part 2, and the Project Resource Schedule
2 | The Activities Schedule
3 | The Pricing Schedule
4 | The Programme for the Works; (Contractor to submit)
5
Contractor: |  | Mulalley and Company Limited | Notes: - Tender to be valid for 60 days - Responses must be provided via e-tender portal.
Framework Manager: |  | John Gristey
Telephone: |  | 020 8551 9999
email: |  | john.gristey@mulalley.co.uk
Scope of Works Required:
Lot 2 Packet 16: As set out in the Works Information Section referred to under Part 1 of the Contract Data. The Works Information consists of the following 3 documents: THE WORKS INFORMATION The Scope of Work Internal and Externals Packet 16; THE WORKS INFORMATION Section A Employers Requirement Internals and Externals Packet 16; THE WORKS INFORMATION The Technical Standards as listed under the Scope of Works Internal and External packet 16. NB Individual projects will be governed by the NEC3 ECC Contract. Both forms are the NEC3 2013 version as amended. These have / will be amended by the contract data, additional clauses and Z Clauses. Evaluation Criteria: Tender is compliant, that the programme is acceptable (effectively an aspect of compliance). Tenders make a social value offer for the call-off in accordance with your method statement for the framework (effectively a matter of compliance). The tender will be evaluated against the following criteria: Price Criteria = 100%. Contractors will be successful if their bid, in the opinion of the Council at the conclusion of the evaluation, offers the most economically advantageous Tender(s) based on the award criteria and the tenderers ability to deliver with appropriate resources.

## Method of Pricing
Better Homes Construction Framework
Rates Schedule
Lot: | Lot 2 Internal & External Works
Method of Pricing: | NEC3: Engineering and Construction Contract Option A: Priced contract with activity schedule.
Services Required: | Tender Brief as set out in Works Information Part I Employers Data
Proposed Start and Finish Date | 29th August 2016 to 2nd December 2016
- Please complete the Price Schedule based on your proposal to deliver the scope of workks as laid out in the Brief. - A Pricing Document has been provided for you to complete. Please complete all sections. - Completed submissions should be returned to the Commercial Team via the eu-supply tender portal by the return date specified.
NEC3: Engineering and Construction Contract Option A: Priced contract with activity schedule. [The Activity Schedule: A programme where each activity is allocated a price and interim payments are made against completion of each activity. The activity schedule on these types of project is submitted together with a contract programme as part of the tender. It is important that all the activities priced add up to the tender sum. Some preliminaries will need to be accounted for within the tendered price schedule.]. The Activity schedule should include as a minimum the following range of basic data spread over columns: Activities, according to the order in which they are carried out. Budget or cost. Quantity in its corresponding units. Predicted performance for working equipment. Duration of the activity.
NEC3: Engineering and Construction Contract Option B: Priced contract with bill of quantities. [The ‘Bill of Quantities’ prepared by the cost consultant (QS) provides project specific measured quantities of the items of work identified by the drawings and specifications (Scope of work). The bill of quantities is issued to tenderers for them to prepare a price for carrying out the works. It means all tendering contractors will be pricing the same quantities. The contractor tenders against the bill of quantities, stating their price for each item. This priced bill of quantities constitutes the tenderer's offer.]
NEC3: Engineering and Construction Contract Option C: Target contract with activity schedule. [Target Contract Option C: a target cost contract with an activity schedule where the out-turn financial risks are shared in an agreed proportion. A form of target cost contract, or ‘gain/pain’ share arrangement. They introduce a mechanism enabling the contractor, and/or the consultant team, to share in the benefits of cost savings, but also to bear some of the cost when there are cost overruns.]
NEC3: Engineering and Construction Contract Option D: Target contract with bill of quantities. [Target Contract Option D: a target cost contract with a bill of quantities where the out-turn financial risks are shared in an agreed proportion. A form of target cost contract, or ‘gain/pain’ share arrangement. They introduce a mechanism enabling the contractor, and/or the consultant team, to share in the benefits of cost savings, but also to bear some of the cost when there are cost overruns.]
NEC3: Engineering and Construction Contract Option E: Cost reimbursable contract. Tendering may proceed based on an outline specification, any drawings and an estimate of costs. Costs are calculated based on the contractor’s accounts and other records, which are made available to the client on an ‘open book’ basis. The client may also monitor activities on site to verify that costs are legitimate.
NEC3: Engineering and Construction Contract Option F: Management contract. The most important aspect of selecting the management contractor is the cost of the project management team put forward. A management contractor might be reimbursed on the basis of fixed or variable costs (the works contract costs) plus either a percentage fee, a fixed fee, or on a target-cost basis. The terms of the appointment must be clear about what is to be provided by the management contractor (such as the provision of site facilities) and whether activities constitute pre-construction or construction services.
NB The successful bidder will be the one providing the lowest price. The bidder will be required to relate their price back to the framework tendered rates (the rates tendered in the mini-competition may be equal to or less than the tendered framework rates but may not be higher). Bids which exceed those tendered in the framework rates will be disqualified.

## Project Resource Schedule
Better Homes Construction Framework
Resource Schedule
| Project Start |  |  | Project end |  |  |  |  | Duration
| 2015-04-01 |  |  | 2015-05-01 |  |  |  |  | 30
Project Plan
Week
# | Work Plan | Resource | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
1 | Site Based | Site Manager | -2 | 13 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2 | Site Based | RLO | -2 | 13 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3 | Office/Site Based | Contracts Manager | -4 | 13 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
4 | Office/Site Based | Quantity Surveyor | -4 | 13 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
5 | Site Based | Labourer | 1 | 13 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 | Office | Head Office Support Team | -4 | 13 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7 | Office/Site Based | Safety Officer | 1 | 13 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
8
9
10
11
12
13
14
15
| Work Plan Key Stages | Dates
| Start on Site | 2016-08-30
| 1-44 Denyer House | 30/08/2016 to 14/11/2016
| 111 Chetwynd Road | 30/08/2016 to 17/10/2016
| 13 Doynton Street | 30/08/2016 to 5/10/2016
| 1-10 Lissenden Mansions | 5/09/2016 to 15/11/2016
| 11-20 Lissenden Mansions | 5/09/2016 to 15/11/2016
| 25 Troyes House | 5/09/2016 to 14/11/2016
| 25 Herbert Street | 12/09/2016 to 12/10/2016
| 66 Leverton Street | 12/09/2016 to 4/11/2016
| 29 Grove Terrace | 12/09/2016 to 28/10/2016
| 30 Grove Terrace | 12/09/2016 to 28/10/2016
| 13 Mortimer Terrace | 19/09/2016 to 18/10/2016
| 25 Elaine Grove | 19/09/2016 to 9/11/2016
| 128 Prince of Wales Road | 19/09/2016 to 17/10/2016
| 130 Prince of Wales Road | 19/09/2016 to 28/10/2016
| 5 Gillies Street | 26/09/2016 to 4/11/2016
| 10 Gillies Street | 26/09/2016 to 4/11/2016
| 11 Gillies Street | 26/09/2016 to 14/11/2016
| 13 Oseney Crescent | 26/09/2016 to 17/11/2016
| 8 Dale Road | 3/10/2016 to 10/11/2016
| 17 Ascham Street | 3/10/2016 to 9/11/2016
| 19 Ascham Street | 3/10/2016 to 18/11/2016
| 28 Leighton Road | 3/10/2016 to 18/11/2016
| 13 Winscombe Terrace | 10/10/2016 to 4/11/2016
| Completion | 2016-11-21
The proposed work plan project specific resource schedule should relate back to the pricing schedule

## Contractor Comments
Better Homes Construction Framework
Contractor Comments / Proposal
Lot: | Lot 2 Internal & External Works
Method of Pricing: | NEC3: Engineering and Construction Contract Option A: Priced contract with activity schedule.
Services / Works Required: | Tender Brief as set out in Works Information Part I Employers Data
Contractor Comments, Notes of Proposal
For the benefit of Camden we confirm below our social value offer for this project. Our offer will be delivered in accordance with our method statement for the Framework: • 2 Locally advertised jobs • 1 NVQ start for a subcontractor • 4 Training plans for a subcontractor • 2 Advanced H&S training sessions for a subcontractor • 3 work placements (16-19) • 1 work placement (14-16) • 1 apprentice (using the shared apprentice model) • 100% of non-hazardous waste will be recycled • Consideration of local businesses, SMEs and micro-businesses in our supply chain • CO2 emissions will be minimised and reported • Support for Camden’s Community Investment Programme • Support for local construction workers through the Construction Industry Helpline Should we be awarded multiple packages we will adjust our social value commitments accordingly. As per the Project Brief, we have made no allowance for planning other than initial consultaion with planners.

## Admin (hidden)
Lot 1A: Small Commissions - Design Services | Day Rate | Architects | Senior Construction Specialist | Mini-Competition
Lot 1B: Small Commissions - Engineering Services | Percentage Fee | Client Design Adviser | Construction Specialist | Direct Call-Off: Quotation
Lot 1C: Small Commissions - Project Delivery Services |  | Design Consultancy Services | Junior Construction Specialist
Lot 1D: Small Commissions - Cost & Commercial Services |  | Landscape Architects | Small Commissions: Work Package Below 100K
Lot 1E: Small Commissions - Complinace H&S Services |  | Lead Design Consultant | Small Commissions: Work Package Up to £500K
Lot 2: Design Services |  | Building Surveying & Inspection | Small Commissions: Work Package Up to £1M
Lot 3: Engineering Services |  | M&E Service Engineers | Work Packages Up to £500K
Lot 4: Project Delivery Services |  | Structural Engineers | Work Package Up to £1m
Lot 5: Cost & Commercial Services |  | Clerk of Works | Work Package Above £1m
Lot 6: Complinace H&S Services |  | Employers Agent
Lot 7: Asbestos Surveys, Testing & Reporting |  | Facilities / Asset Management Adviser
Lot 8: Risk Fire Assessment |  | Project Managers
Lot 9: Scoping Surveys: Investment Needs |  | Commercial Advice
Cost Management
Quantity Surveyor
Construction Design Management Consultant
Health & Safety Advisor
BREEAM Advisor
Client Design Advisor
Mechanical & Electrical Engineers
Planning Advice & Applications
Building Surveying & Inspection, Condition & Scoping Surveyors
Geotechnical Surveyors
Mechanical & Electrical Engineers
Partnering Adviser
Commercial Advice

## NEC3 ECC Contract Data Part 2
Better Homes Construction Framework
ECC Contract - Contract Data
Part Two (Data provided by the Contractor)
Statements given in all contracts
1. The Contractor is
Name | Mulalley and Company Limited
Address: | Teresa Gavin House, Woodford Avenue,
Woodford Green,
Essex. IG8 8FA
Telephone: | 020 8551 9999
Email:
2. The Central Overheads and Profit percentage is 4% as set out in the Framework Agreement
3. The working areas are the Site and [insert any additional areas]
4. The key persons are
4.1 Provide details of the Contract Manager
Name | Andre Cullerton
Job | Contracts Manager
Responsibilities | • Heads and controls site project team • Fosters relationships with Client and Consultants • Overall operational responsibility for all on site functions • Ensuring Client’s requirements are correctly implemented and objectives achieved • Champions Social Value and sustainability for Client
Qualifications | • SMSTS • CSCS Card • City & Guilds Graduateship in Construction • ILM Executive Diploma in Management • CITB Construction Site Managers Safety Certificate • NEBOSH General Certificate
Experience | • Basildon Decent Homes • LBBD Multiple Internal Elements • Hackney Decent Homes • Thurrock Decent Home
4.2. Two
Name | Fred Makumbi
Job | Site Manager
Responsibilities | • Ensure that works are completed safely, on time, to a good quality, within budget and to the Client’s requirements. • Responsible for the overall security of the project • Ensuring quality standards are met by direct use of Quality Control procedures • Developing and defining site personnel job specifics and training • Set-up and chair site team progress/team meetings, which includes supply chain partners • Controlling and co-ordinating all activities of supply chain partners
Qualifications | • SSMTS • CSCS Card • MCIOB
Experience | • Phoenix Major Works • Lambeth Street Properties • Southwark – Rockingham Estate Refurbishment
5. The following matters will be included in the Risk Register
[identify any risks]
Optional Statements
6. If the Contractor is to provide Works Information for his design
6.1. The Works Information for the Contractor’s design is in [identify document]
7. If a programme is to be identified in the Contract Data
7.1. The programme identified in the Contract Data is [identify document]
8. If the Contractor is to decide the completion date for the whole of the works
8.1. The completion date for the whole of the works is [insert]
9. If Option A or C is used
9.1. The activity schedule is as set out in the pricing doumentation issued to the Contractor.
10. If Options B or D are used
10.1. The bill of quantities is [identify document]
11. If Options A, B, C or D is used
11.1. The tendered total of the Prices is [insert]
12. If Option F is used
12.1. Work which the Contractor will do himself is
Activity | Price
13. If Options A or B are used
13.1. Data for the Shorter Schedule of Cost Components
13.1.1. The percentage of people overheads is [insert] %
13.1.2. The published list of Equipment is the last edition of the list published by [insert]
13.1.3. The percentage for adjustment for Equipment in the published list is [insert] % (state plus or minus)
13.1.4. The rates for other Equipment are
Equipment | Size or Capacity | Rate
13.1.5. The hourly rates for Defined Cost of design outside the Working Areas are
Category of Employee | Hourly Rate
Tradesman | 25.5
Labourer | 20.6
13.1.6. The percentage for design overheads is [insert]%
13.1.7. The categories of design employees whose travelling expenses to and from the Working Area are included in Defined Cost are [insert]
14. If Option C, D or E is used
14.1. Data for Schedule of Cost Components
14.1.1. The listed items of Equipment purchased for work on this contract, with an on cost charge, are
Equipment | Time Related Charge | Per time Period
14.1.2. The rates for special Equipment are
Equipment | Size or Capacity | Rate
14.1.3. The percentage for Working Area overheads is [insert] %
14.1.4. The hourly rates for Defined Cost of manufacture and fabrication outside the Working Areas are
Category of Employee | Hourly Rate
14.1.5. The percentage for manufacture and fabrication overheads is [insert] %
15. If Options C, D or E is used
15.1. Data for the Shorter Schedule of Cost Components
15.1.1. The percentage for people overheads is [insert] %
15.1.2. The published list of Equipment is the last edition of the list published by the [insert]
15.1.3. The percentage for adjustment for Equipment in the published list is [insert] % (plus/minus)
15.1.4. The rates for other Equipment are
Equipment | Size or Capacity | Rate

## Additional Conditions Contract
Better Homes Construction Framework
EEC Contract Additional Conditions of Contract
These are as set out in the Contract Data Part 1; refer to the scheduled Z clauses

## Form of Tender
Better Homes Construction Framework
Form of Tender
Date: | 17th June 2016
Tender Ref: | Wave C Packet 16 NW5
Lot:
Return Date: | 17th June 2016
Consultancy
Form of Tender: (Bona Fide tender statement),
1. Having examined the Tender Document for the above named project, we offer herewith our tender for Works for the execution and completion of conformity with the said Tender Documents including the Tender Brief Information for the VAT exclusive, total of the Prices Nine Hundred and Five Thousand, Eight Hundred and Fifty Three Pounds Forty Pence (£905,853.40 ) [Total of the tendered Price] 2. We further offer to complete the whole of the Works described within 13 weeks from the Starting Date. 3. This tender shall remain open for a period of 60 weeks from the date hereon. Yours faithfully: Signature: ……………………………………………………………………………………... Name (In Printed Capitals): BRUCE BENSON Position: Operations Director Address: Teresa Gavin House, Woodford Avenue, Woodford Green, Essex. IG8 8FA Telephone: 020 8551 9999 Email: bruce.benson@mulalley.co.uk Date: 17th June 2016
Please confirm the following: |  | Yes
Non-Collusion I / We certify that this is a bona fide quote, intended to be competitive, and that I / We have not fixed or adjusted the amount of the quote by, under, or in accordance with any agreement or arrangement with any other person. |  | P
Non-Canvassing I / we have not canvassed or solicited any officer or employee of the Employer, or its appointed Consultants in connection with this procurement or the award of the contract for the above project. |  | P
I / we comply with the terms or the framework agreement. |  | P

## Sheet1
Lot 1A Small Commissions-General Construction
Lot 1B Small Commissions - Mechanical & Electrical
Lot 2 Internal & External Works
Lot 3 Lift Replacement & Major Upgrades
Lot 4 Electrical Systems Replacement & Major Upgrades
Lot 5 Mechanical Systems Replacement & Major Upgrades
Lot 6 New Build Accommodation
NEC3: Engineering and Construction Contract Option A: Priced contract with activity schedule.
NEC3: Engineering and Construction Contract Option B: Priced contract with bill of quantities.
NEC3: Engineering and Construction Contract Option C: Target contract with activity schedule.
NEC3: Engineering and Construction Contract Option D: Target contract with bill of quantities.
NEC3: Engineering and Construction Contract Option E: Cost reimbursable contract.
NEC3: Engineering and Construction Contract Option F: Management contract.