## A2004
| Client: | Trades Union Congress
| Project: | TUC Congress House, South Side Refurbishment
| Application Reference: | 2016/3882/L
| Permission Granted: | 15/12/'2016
| Condition No: | 4
| Job No.: | 205
| Schedule No: | Salvaged Relocated Material Condition 4 Schedule
| Date: | Febraury 2017
| Revision: | RevP1
| Author: | GP
| Checked: | GP
| Approved: | GP
| Material | Element | Existing Location | Scope of work reference |  | Notes | Notes
1 | Sicilian Pearl Marble | Flooring | Internal Lobby Reception | Architect's Scope of Works document | N / A | Untouched - Marble floor retained and refurbished Where walls have been stripped out, infill with full tile only to match existing in format and colour. Use salvaged marble from internal wall cladding in stripped out Bainbridge Entrance (18) | Marble floors retained and refurbished where deemed necessary (26). Where walls have been stripped out, damaged tiles will be infilled with full tiles only to match existing in format and colour. Use salvaged stripped out marble tiles from former Bainbridge Street entrance (18). for making good.
2 | Timber | Flooring | Internal Offices Reception Toilet Corridors | Architect's Scope of Works document |  |  | Timber floor retained and refurbished throughout. (27).
3 | Glass | Flooring | Internal Floor to Marbel Hall | Architect's Scope of Works document |  |  | To remain untouched (28).
4 | Brass Insets | Flooring | Internal Floor to Marbel Hall |  |  |  | To remain untouched (28).
5 | York & Portland Stone | Flooring / Copings | Exterior Ramp Borders | Architect's Scope of Works document |  |  | Strip out existing coping cills (7). Retain throughout the Works for possible usage in the scheme.
6 | External Timber Door | Joinery Works | Former Baibridge Street Entrance | Architect's Scope of Works document | N / A | Existing doors, bronze window and cladding stripped out (20). Doors / frame refurbished and reinstated at Lower Ground floor in Congress Centre break out area. Cladding / Bronze windows are to be retained throughout the Works for possible usage during the scheme.
7 | Internal Timber Doors | Joinery Works | Offices Stairwell Carpark Lobby WC Cleaner's Cupboards Risers | Architect's Scope of Works document |  |  | Original timber door retained and refurbished throughout office / lift stairwell (24). Where removed from WC, risers and cleaner's cupboards to all floors (29), retain throughout the Works for possible usage during the scheme.
8 | Panelling / Skirting | Joinery Works | Lift lobbys Ground Floor Office / Atrium Radiator Casings | Architect's Scope of Works document |  |  | Existing timber panelling to lift lobby's to all floors are to be retained, protected and left untouched (25). Window cills / redundant radiator casings panelling to ground floor office section adjacent to the courtyard atrium, are to be stripped out (30) and retained throughout the Works for possible usage during the scheme.
9 | External Balustrade / Handrails | Metal Works | Exterior Ramp / Stairs / Walkway | Architect's Scope of Works document |  |  | Existing handrails and balustrades are to be retained and refurbished along the length of the refurbished ground floor offices. Adjacent section stripped along the length of the walkway are to be salvaged / relocated to the basement carpark area as acting barrier between bicycle area and the carpaking spaces. (5) Balustrade surrounding ramp are to salvaged / relocated along extended bin store area. (31) Outstanding handrail / balustrade are to be retained throughout the Works for possible usage during the scheme.
10 | Bronze Windows | Metal Works | Former Baibridge Street Entrance |  |  |  | Existing doors, bronze window and cladding stripped out (20). Bronze windows are to be retained throughout the Works for possible usage during the scheme.
11 | Mosaic | Tiling Works | Baibridge Street Eleveation |  |  |  | Strip out mosaic tiling to fascia. Repair substrate and re-clad with tiles as previously signed off by Conservation Officer in previous works / schemes executed at the TUC under application Ref: 2012/6775/L. Salvaged stripped out tiles are to be kept and used for patching up of mosaic sections of the facades and columns (17) throughout the external elevation. Any unused mosaic tiles are to be kept for future renovation and remedial works.
Notes: - Schedule to be read in conjunction with strip out drawing 205/P1050_RevP1 - Schedule to be read in conjunction with GRANTED proposed drawing series 205/P1010, 1011, 1012, 1013, 1014, 1015, 1016, 1017, 1020, 1021 - Nunbers in brakets (*) refer to drawing reference in RED