## Activities Schedule
ACTIVITY SCHEDULE
NEC3: Engineering and Construction Contract Option A: Priced contract with activity schedule.
Please provide duration for every activity by filling in the cells below. 1-84 Flaxman Court is filled in as an example (please modify)
Activities match the requirement types as per the pricing document
Completion of the works required in street properties are not expected to exceed 13 weeks and scaffold hire is not expected to exceed 12 weeks
Please provide the total price per property as per the pricing schedule in the yellow cells in column AO
Activity No | Property | Works | -5 | -4 | -3 | -2 | -1 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26 | Wk 27 | Wk 28 | Wk 29 | Wk 30 | Wk 31 | Wk 32 | Wk 33 | Wk 34 | Wk 35 | Wk 36 | Price Totals
Mobilisation Period | 1-84 Flaxman Court (cons) | Award of Contract
| 1-84 Flaxman Court (cons) | Consultation Period | bar: -5 to -4
| 1-84 Flaxman Court (cons) | Resident Consultation / Letter drop | bar: -3
| 1-84 Flaxman Court (cons) | Surveys | bar: -3 to -2
| 1-84 Flaxman Court (cons) | Site Set up | bar: -1
Activity 1 | 1-84 Flaxman Court (cons) | Scaffolding | bar: Wk 1 to Wk 4; Wk 28 to Wk 30
Activity 2 | 1-84 Flaxman Court (cons) | Asbestos Survey and Removal | bar: Wk 1 to Wk 4
Activity 3 | 1-84 Flaxman Court (cons) | Roofing | bar: Wk 5 to Wk 7
Activity 4 | 1-84 Flaxman Court (cons) | Fabric Repairs and Decorations | bar: Wk 6 to Wk 11
Activity 5 | 1-84 Flaxman Court (cons) | Window Works | -4: Window surveys; Wk 1: Drawing approval; Wk 4: Lead in time; Wk 12: Window fit
Activity 6 | 1-84 Flaxman Court (cons) | Energy Efficiency | bar: Wk 5
Activity 7 | 1-84 Flaxman Court (cons) | Communal Works | bar: Wk 5 to Wk 10
Activity 8 | 1-84 Flaxman Court (cons) | FRA Works | bar: Wk 7 to Wk 14
Activity 9 | 1-84 Flaxman Court (cons) | Estate Works
Project Overheads | bar: Wk 1 to Wk 30