## Tender Brief
Better Homes Construction Framework
Call-Off Brief
Date:
Tender Ref:
Lot: |  | Lot 2 Internal & External Works
Return Date:
Method of Pricing: |  | NEC3: Engineering and Construction Contract Option A: Priced contract with activity schedule.
Evaluation Criteria |  | PRICE (Most Economically Advantageous Tender)
Scope of Works Required |  | Tender Brief as set out in Works Information Part I Employers Data
Project Lead |  | Stephen Platt
Telephone: |  | 0207 974 3937
Email: |  | Stephen.Platt@camden.gov.uk
The bidder is required to provide the following submissions
1 | This Call Off brief including the following documents included in this call document: the Form of Tender, the NEC3 Contract Data Part 2, and the Project Resource Schedule
2 | The Activities Schedule
3 | The Pricing Schedule
4 | The Programme for the Works; (Contractor to submit)
5
Contractor: |  |  | Notes: - Tender to be valid for 60 days - Responses must be provided via e-tender portal.
Framework Manager:
Telephone:
email:
Scope of Works Required:
Lot 2 Packet 4: As set out in the Works Information Section referred to under Part 1 of the Contract Data. The Works Information consists of the following 3 documents: THE WORKS INFORMATION The Scope of Work Internal and Externals Packet 4; THE WORKS INFORMATION Section A Employers Requirement Internals and Externals Packet 4; THE WORKS INFORMATION The Technical Standards as listed under the Scope of Works Internal and External packet 1. NB Individual projects will be governed by the NEC3 ECC Contract. Both forms are the NEC3 2013 version as amended. These have / will be amended by the contract data, additional clauses and Z Clauses. Evaluation Criteria: Tender is compliant, that the programme is acceptable (effectively an aspect of compliance). Tenders make a social value offer for the call-off in accordance with your method statement for the framework (effectively a matter of compliance). The tender will be evaluated against the following criteria: Price Criteria = 100%. Contractors will be successful if their bid, in the opinion of the Council at the conclusion of the evaluation, offers the most economically advantageous Tender(s) based on the award criteria and the tenderers ability to deliver with appropriate resources.

## Method of Pricing
Better Homes Construction Framework
Rates Schedule
Lot: | Lot 2 Internal & External Works
Method of Pricing: | NEC3: Engineering and Construction Contract Option A: Priced contract with activity schedule.
Services Required: | Tender Brief as set out in Works Information Part I Employers Data
Proposed Start and Finish Date
- Please complete the Price Schedule based on your proposal to deliver the scope of workks as laid out in the Brief. - A Pricing Document has been provided for you to complete. Please complete all sections. - Completed submissions should be returned to the Commercial Team via the eu-supply tender portal by the return date specified.
NEC3: Engineering and Construction Contract Option A: Priced contract with activity schedule. [The Activity Schedule: A programme where each activity is allocated a price and interim payments are made against completion of each activity. The activity schedule on these types of project is submitted together with a contract programme as part of the tender. It is important that all the activities priced add up to the tender sum. Some preliminaries will need to be accounted for within the tendered price schedule.]. The Activity schedule should include as a minimum the following range of basic data spread over columns: Activities, according to the order in which they are carried out. Budget or cost. Quantity in its corresponding units. Predicted performance for working equipment. Duration of the activity.
NEC3: Engineering and Construction Contract Option B: Priced contract with bill of quantities. [The ‘Bill of Quantities’ prepared by the cost consultant (QS) provides project specific measured quantities of the items of work identified by the drawings and specifications (Scope of work). The bill of quantities is issued to tenderers for them to prepare a price for carrying out the works. It means all tendering contractors will be pricing the same quantities. The contractor tenders against the bill of quantities, stating their price for each item. This priced bill of quantities constitutes the tenderer's offer.]
NEC3: Engineering and Construction Contract Option C: Target contract with activity schedule. [Target Contract Option C: a target cost contract with an activity schedule where the out-turn financial risks are shared in an agreed proportion. A form of target cost contract, or ‘gain/pain’ share arrangement. They introduce a mechanism enabling the contractor, and/or the consultant team, to share in the benefits of cost savings, but also to bear some of the cost when there are cost overruns.]
NEC3: Engineering and Construction Contract Option D: Target contract with bill of quantities. [Target Contract Option D: a target cost contract with a bill of quantities where the out-turn financial risks are shared in an agreed proportion. A form of target cost contract, or ‘gain/pain’ share arrangement. They introduce a mechanism enabling the contractor, and/or the consultant team, to share in the benefits of cost savings, but also to bear some of the cost when there are cost overruns.]
NEC3: Engineering and Construction Contract Option E: Cost reimbursable contract. Tendering may proceed based on an outline specification, any drawings and an estimate of costs. Costs are calculated based on the contractor’s accounts and other records, which are made available to the client on an ‘open book’ basis. The client may also monitor activities on site to verify that costs are legitimate.
NEC3: Engineering and Construction Contract Option F: Management contract. The most important aspect of selecting the management contractor is the cost of the project management team put forward. A management contractor might be reimbursed on the basis of fixed or variable costs (the works contract costs) plus either a percentage fee, a fixed fee, or on a target-cost basis. The terms of the appointment must be clear about what is to be provided by the management contractor (such as the provision of site facilities) and whether activities constitute pre-construction or construction services.
NB The successful bidder will be the one providing the lowest price. The bidder will be required to relate their price back to the framework tendered rates (the rates tendered in the mini-competition may be equal to or less than the tendered framework rates but may not be higher). Bids which exceed those tendered in the framework rates will be disqualified.

## Project Resource Schedule
Better Homes Construction Framework
Resource Schedule
| Project Start |  |  | Project end |  |  |  |  | Duration
| 2015-04-01 |  |  | 2015-05-01 |  |  |  |  | 30
Project Plan
Week
# | Work Plan | Resource | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
1 |  |  | 1 | 2 | 1 | 1
2 |  |  | 2 | 3 |  | 1 | 1
3 |  |  | 4 | 4 |  |  |  | 1
4 |  |  | 5 | 6 |  |  |  |  | 1 | 1
5 |  |  | 7 | 8 | [6 empty] | 1 | 1
6 |  |  | 8 | 8 | [7 empty] | 1
7 |  |  | 9 | 9 | [8 empty] | 1
8 |  |  | 9 | 10 | [8 empty] | 1 | 1
9 |  |  | 10 | 11 | [9 empty] | 1 | 1
10 |  |  | 12 | 26 | [11 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
11 |  |  | 20 | 26 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
12 |  |  | 21 | 32 | [20 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
13 |  |  | 26 | 32 | [25 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
14 |  |  | 33 | 35 | [32 empty] | 1 | 1 | 1
15 |  |  | 36 | 36 | [35 empty] | 1
| Work Plan Key Stages | Dates
The proposed work plan project specific resource schedule should relate back to the pricing schedule

## Contractor Comments
Better Homes Construction Framework
Contractor Comments / Proposal
Lot: | Lot 2 Internal & External Works
Method of Pricing: | NEC3: Engineering and Construction Contract Option A: Priced contract with activity schedule.
Services / Works Required: | Tender Brief as set out in Works Information Part I Employers Data
Contractor Comments, Notes of Proposal

## Admin (hidden)
Lot 1A: Small Commissions - Design Services | Day Rate | Architects | Senior Construction Specialist | Mini-Competition
Lot 1B: Small Commissions - Engineering Services | Percentage Fee | Client Design Adviser | Construction Specialist | Direct Call-Off: Quotation
Lot 1C: Small Commissions - Project Delivery Services |  | Design Consultancy Services | Junior Construction Specialist
Lot 1D: Small Commissions - Cost & Commercial Services |  | Landscape Architects | Small Commissions: Work Package Below 100K
Lot 1E: Small Commissions - Complinace H&S Services |  | Lead Design Consultant | Small Commissions: Work Package Up to £500K
Lot 2: Design Services |  | Building Surveying & Inspection | Small Commissions: Work Package Up to £1M
Lot 3: Engineering Services |  | M&E Service Engineers | Work Packages Up to £500K
Lot 4: Project Delivery Services |  | Structural Engineers | Work Package Up to £1m
Lot 5: Cost & Commercial Services |  | Clerk of Works | Work Package Above £1m
Lot 6: Complinace H&S Services |  | Employers Agent
Lot 7: Asbestos Surveys, Testing & Reporting |  | Facilities / Asset Management Adviser
Lot 8: Risk Fire Assessment |  | Project Managers
Lot 9: Scoping Surveys: Investment Needs |  | Commercial Advice
Cost Management
Quantity Surveyor
Construction Design Management Consultant
Health & Safety Advisor
BREEAM Advisor
Client Design Advisor
Mechanical & Electrical Engineers
Planning Advice & Applications
Building Surveying & Inspection, Condition & Scoping Surveyors
Geotechnical Surveyors
Mechanical & Electrical Engineers
Partnering Adviser
Commercial Advice

## NEC3 ECC Contract Data Part 2
Better Homes Construction Framework
ECC Contract - Contract Data
Part Two (Data provided by the Contractor)
Statements given in all contracts
1. The Contractor is
Name
Address:
Telephone:
Email:
2. The Central Overheads and Profit percentage is [insert]% as set out in the Framework Agreement
3. The working areas are the Site and [insert any additional areas]
4. The key persons are
4.1 Provide details of the Contract Manager
Name
Job
Responsibilities
Qualifications
Experience
4.2. Two
Name
Job
Responsibilities
Qualifications
Experience
5. The following matters will be included in the Risk Register
[identify any risks]
Optional Statements
6. If the Contractor is to provide Works Information for his design
6.1. The Works Information for the Contractor’s design is in [identify document]
7. If a programme is to be identified in the Contract Data
7.1. The programme identified in the Contract Data is [identify document]
8. If the Contractor is to decide the completion date for the whole of the works
8.1. The completion date for the whole of the works is [insert]
9. If Option A or C is used
9.1. The activity schedule is as set out in the pricing documentation issued to the Contractor.
10. If Options B or D are used
10.1. The bill of quantities is [identify document]
11. If Options A, B, C or D is used
11.1. The tendered total of the Prices is [insert]
12. If Option F is used
12.1. Work which the Contractor will do himself is
Activity | Price
13. If Options A or B are used
13.1. Data for the Shorter Schedule of Cost Components
13.1.1. The percentage of people overheads is [insert] %
13.1.2. The published list of Equipment is the last edition of the list published by [insert]
13.1.3. The percentage for adjustment for Equipment in the published list is [insert] % (state plus or minus)
13.1.4. The rates for other Equipment are
Equipment | Size or Capacity | Rate
13.1.5. The hourly rates for Defined Cost of design outside the Working Areas are
Category of Employee | Hourly Rate
13.1.6. The percentage for design overheads is [insert]%
13.1.7. The categories of design employees whose travelling expenses to and from the Working Area are included in Defined Cost are [insert]
14. If Option C, D or E is used
14.1. Data for Schedule of Cost Components
14.1.1. The listed items of Equipment purchased for work on this contract, with an on cost charge, are
Equipment | Time Related Charge | Per time Period
14.1.2. The rates for special Equipment are
Equipment | Size or Capacity | Rate
14.1.3. The percentage for Working Area overheads is [insert] %
14.1.4. The hourly rates for Defined Cost of manufacture and fabrication outside the Working Areas are
Category of Employee | Hourly Rate
14.1.5. The percentage for manufacture and fabrication overheads is [insert] %
15. If Options C, D or E is used
15.1. Data for the Shorter Schedule of Cost Components
15.1.1. The percentage for people overheads is [insert] %
15.1.2. The published list of Equipment is the last edition of the list published by the [insert]
15.1.3. The percentage for adjustment for Equipment in the published list is [insert] % (plus/minus)
15.1.4. The rates for other Equipment are
Equipment | Size or Capacity | Rate

## Additional Conditions Contract
Better Homes Construction Framework
EEC Contract Additional Conditions of Contract
These are as set out in the Contract Data Part 1; refer to the scheduled Z clauses

## Form of Tender
Better Homes Construction Framework
Form of Tender
Date: | 9th June 2016
Tender Ref: Wave A | Wave A Packet 4 Flaxman Court
Lot: | Lot 4: Project Delivery Services
Return Date: | 21st April 2016
Consultancy
Form of Tender: (Bona Fide tender statement),
1. Having examined the Tender Document for the above named project, we offer herewith our tender for Works for the execution and completion of conformity with the said Tender Documents including the Tender Brief Information for the VAT exclusive, total of the Prices ……One Million, Three Hundred & Thirty Nine Thousand, Three Hundred & Thirty Six Pounds & Twenty Pence (£1,339,336.20) [Total of the tendered Price] 2. We further offer to complete the whole of the Works described within XX weeks from the Starting Date. 3. This tender shall remain open for a period of 60 weeks from the date hereon. Yours faithfully: Signature: ……………………… Name (In Printed Capitals): ANDREW GREEN Position:……………………………OPERATIONS DIRECTOR Address: Morgan Sindall Property Services Ltd, 45 Moorfields, Moorgate, London, EC2Y 9AE …………………………………………………………………………………………………... Telephone: 020 7448 7643 Email: ……………andrew.green@morgansindall.com Date: …………… 9 June 2016
Please confirm the following: |  | Yes
Non-Collusion We certify that this is a bona fide quote, intended to be competitive, and that I / We have not fixed or adjusted the amount of the quote by, under, or in accordance with any agreement or arrangement with any other person. |  | Yes
Non-Canvassing We have not canvassed or solicited any officer or employee of the Employer, or its appointed Consultants in connection with this procurement or the award of the contract for the above project. |  | Yes
We comply with the terms or the framework agreement. |  | Yes

## Sheet1
Lot 1A Small Commissions-General Construction
Lot 1B Small Commissions - Mechanical & Electrical
Lot 2 Internal & External Works
Lot 3 Lift Replacement & Major Upgrades
Lot 4 Electrical Systems Replacement & Major Upgrades
Lot 5 Mechanical Systems Replacement & Major Upgrades
Lot 6 New Build Accommodation
NEC3: Engineering and Construction Contract Option A: Priced contract with activity schedule.
NEC3: Engineering and Construction Contract Option B: Priced contract with bill of quantities.
NEC3: Engineering and Construction Contract Option C: Target contract with activity schedule.
NEC3: Engineering and Construction Contract Option D: Target contract with bill of quantities.
NEC3: Engineering and Construction Contract Option E: Cost reimbursable contract.
NEC3: Engineering and Construction Contract Option F: Management contract.