## Sheet1
Date of Deployment-11/1/2018
Application- Licensing
Time- 10:30-1pm
Version-1.6
Date | Time | Description | Assigned to | Completed (Yes/No) | Any Other Comments
2018-01-09 | Before 4 pm | RFC to be raised for the release | Duncan
2018-01-09 | Before 4pm | Notify the business and payments team (Sue,Say,Trudy) , SSI team about the date, time and content of the release. Also the possible downtime for the same and payment that would be involved as part of production testing. | Jahnavi
2018-01-09 | Before 4pm | Inform the service that we would be submitting one license application as part of production testing, "TEST" to be used as input for all fields where possible.Discuss with Andy the application which would be used | Jahnavi
2018-01-09 | Before 4 pm | Finalise the versions to be deployed in production for release 1.6 | Team Karma
2018-01-09 | Before 4pm | Patrick to sign off i.e. he is happy to deploy the contents of the release 1.6 | Patrick
2017-01-11 | 10:30-1 pm | Put the maintanence page up for Licensing in CA and business portal | Duncan
|  | Deploying the artefacts and making changes to environment properties | Duncan
|  | Do the SQL release (put SQL for vw_TensAutoApproveStatus in the Live Flare DB) for DTO-727 | Andy
|  | Testing Release | QA team
|  | Remove the maintanence page | Duncan
|  | Notify the business & Payments team ( with details to roll back the payment and also the reference number of application submitted) that the change has been implemented | Jahnavi