**Construction Management**

**Plan**

**pro forma** v2.1

**Contents**

**Revisions 3**

**Introduction 4**

**Timeframe 6**

**Contact 7**

**Site 9**

**Community liaison 12**

**Transport 15**

**Environment 25**

**Agreement 30**

**Revisions & additional material**

Please list all iterations here:

|  |  |  |
| --- | --- | --- |
| **Date** | **Version** | **Produced by** |
| **15th November 2017**  **12th January 2018**  **6th March 2018** | **1**  **V. 2**  **V.2.1** | **Jake Puddy**  **Jake Puddy**  **Jake Puddy** |

**Additional sheets**

Please note – the review process will be quicker if these are submitted as Word documents or searchable PDFs.

|  |  |  |
| --- | --- | --- |
| **Date** | **Version** | **Produced by** |
| **6th March 2018** | **Addendum CMR 2 Oakhill Avenue NW3 7RE copy** | **Nebojsa Rupar** |
| **6th March 2018** | **2 OAKHILL SET-UP-A** | **BDS** |

**Introduction**

The purpose of the **Construction Management Plan (CMP)** is to help developers to minimise construction impacts, and relates to both on site activity and the transport arrangements for vehicles servicing the site.

It is intended to be a live document whereby different stages will be completed and submitted for application as the development progresses.

The completed and signed CMP must address the way in which any impacts associated with the proposed works, and any **cumulative impacts of other nearby construction sites**, will be mitigated and managed. The level of detail required in a CMP will depend on the scale and kind of development. Further policy guidance is set out in Camden Planning Guidance [**(CPG)** 6: Amenity](http://www.camden.gov.uk/ccm/content/environment/planning-and-built-environment/two/planning-policy/supplementary-planning-documents/camden-planning-guidance.en) and [**(CPG)** 8: Planning Obligations](http://www.camden.gov.uk/ccm/content/environment/planning-and-built-environment/two/planning-policy/supplementary-planning-documents/camden-planning-guidance.en).

This CMP follows the best practice guidelines as described in [Transport for London’s](https://www.tfl.gov.uk/info-for/freight/safety-and-the-environment/improving-construction-safety) (TfL’s Standard for [Construction Logistics and Cyclist Safety](http://www.clocs.org.uk/standard-for-clocs/) (**CLOCS**) scheme) and [Camden’s Minimum Requirements for Building Construction](http://www.camden.gov.uk/ccm/cms-service/download/asset?asset_id=3257318) **(CMRBC)**.

The approved contents of this CMP must be complied with unless otherwise agreed with the Council in writing. The project manager shall work with the Council to review this CMP if problems arise in relation to the construction of the development. Any future revised plan must also be approved by the Council and complied with thereafter.

It should be noted that any agreed CMPdoes not prejudice or override the need to obtain any separate consents or approvals such as for road closures or hoarding licences.

If your scheme involves any demolition, you need to make an application to the Council’s Building Control Service. Please complete the “[**Demolition Notice**](http://www.camden.gov.uk/ccm/content/environment/building-control/file-storage-items/demolition-notice---the-building-act-1984-section-80-notice-bc104-.en)**.**”

Please complete the questions below with additional sheets, drawings and plans as required. The boxes will expand to accommodate the information provided, so please provide as much information as is necessary. **It is preferable if this document, and all additional documents, are completed electronically and submitted as Word files to allow comments to be easily documented. These should be clearly referenced/linked to from the CMP.**

Please notify that council when you intend to start work on site. Please also notify the council when works are approximately **3 months from completion.**

(Note the term 'vehicles' used in this document refers to all vehicles associated with the implementation of the development, e.g. demolition, site clearance, delivery of plant & materials, construction, etc.)

Revisions to this document may take place periodically. **Timeframe**

**DEVELOPER ACTIONS**

**COUNCIL ACTIONS**

**Post app submission**

**0ommunity liaison**

**Appoint principal contractor**

**Requirement to submit CMP**

**Begin community liaison**

**Work can commence if draft CMP is approved**

**Council response to second draft**

**Resubmission of CMP if first draft refused**

**2ommunity liaison**

**3ommunity liaison**

**1ommunity liaison**

INDICATIVE TIMEFRAME (MONTHS)

**4ommunity liaison**

**Council response to draft**

**Submit draft CMP**

**Contact**

1. Please provide the full postal address of the site and the planning reference relating to the construction works.

Address: 2 Oakhill Avenue NW3 7RE

Planning ref: 2013/6162/P

Type of CMP - Section 106 planning obligation/Major sites framework: Section 106 planning obligation.

2. Please provide contact details for the person responsible for submitting the CMP.

Name: Jake Puddy

Address: London Basement, Unit 4 Victory Business Centre, Fleming Way, Isleworth TW7 6DB

Email: jake.puddy@londonbasement.co.uk

Phone: 020 8847 9449

3. Please provide full contact details of the site project manager responsible for day-to-day management of the works and dealing with any complaints from local residents and businesses.

Name: **Nebojsa Rupar**

Address: 12a Aldred Road London NW6 1AN

Email:TBC

Phone: 07968857766

4. Please provide full contact details of the person responsible for community liaison and dealing with any complaints from local residents and businesses if different from question 3. In the case of [**Community Investment Programme (CIP)**](http://www.camden.gov.uk/ccm/content/environment/planning-and-built-environment/two/placeshaping/twocolumn/the-community-investment-programme.en), please provide contact details of the Camden officer responsible.

Name: **Nebojsa Rupar**

Address: 12a Aldred Road London NW6 1AN

Email: TBC

Phone: 07968857766

5. Please provide full contact details including the address where the main contractor accepts receipt of legal documents for the person responsible for the implementation of the CMP.

Name: **Nebojsa Rupar**

Address: 12a Aldred Road London NW6 1AN

Email: TBC

Phone: 07968857766

**Site**

6. Please provide a site location plan and a brief description of the site, surrounding area and development proposals for which the CMP applies.

Please see Appendix G – Site Location Plan (BDS 2Oakhill-OS).

The site is a post war 3 storey single dwelling set back from the road. The surrounding area is predominantly large single dwelling detached houses with private off street parking.

The proposed development is a retrofit basement under the footprint of the house and part rear garden.

7. Please provide a very brief description of the construction works including the size and nature of the development and details of the main issues and challenges (e.g. narrow streets, close proximity to residential dwellings etc).

The works include excavation of a basement under the existing building using reinforced concrete underpinning, retaining walls and structural steels to support the upper floors. The excavated area is approximately 130m² and will be formed using manual labour, mechanical plant and a conveyor to transport spoil to a skip on the street. The property has one adjoining owner but party wall agreements will be sought with both immediate neighbours. Fortunately Oakhill Avenue and the surround streets are wide and experience relatively light traffic outside of peak hours.

8. Please identify the nearest potential receptors (dwellings, business, etc.) likely to be affected by the activities on site (i.e. noise, vibration, dust, fumes, lighting etc.).

2c Oakhill Avenue (adjoining owner)

2b Oakhill Avenue (adjoins the AO 2c)

4 Oakhill Avenue (immediate neighbour)

1a, 1b, 1c and 1d Oakhill Avenue (immediately opposite)

9. Please provide a scaled plan detailing the local highway network layout in the vicinity of the site. This should include details of on-street parking bay locations, cycle lanes, footway extents and proposed site access locations.

Please see Appendices C (Site Set Up Plan) and G (Site Location Plan).

10. Please provide the proposed start and end dates for each phase of construction as well as an overall programme timescale. (A Gantt chart with key tasks, durations and milestones would be ideal).

Please see Appendix I (Site Programme).

11. Please confirm the standard working hours for the site, noting that the standard working hours for construction sites in Camden are as follows:

* 8.00am to 6pm on Monday to Friday
* 8.00am to 1.00pm on Saturdays
* No working on Sundays or Public Holidays

Working hours will be from 0800 to 1800 Monday to Friday and 0800 to 1300 on Saturdays. There will be no working on Sundays or Public Holidays.

12. Please indicate if any changes to services are proposed to be carried out that would be linked to the site during the works (i.e. connections to public utilities and/or statutory undertakers’ plant). Larger developments may require new utility services. If so, a strategy and programme for coordinating the connection of services will be required. If new utility services are required, please confirm which utility companies have been contacted (e.g. Thames Water, National Grid, EDF Energy, BT etc.) You must explore options for the utility companies to share the same excavations and traffic management proposals. Please supply details of your discussions.

It is not proposed that any changes to services will be required.

**Community Liaison**

**A neighbourhood consultation process must have been undertaken prior to submission of the CMP first draft. This consultation must relate to construction impacts, and should take place following the grant of planning permission in the lead up to the submission of the CMP. A consultation process specifically relating to construction impacts must take place regardless of any prior consultations relating to planning matters. This consultation must include all of those individuals that stand to be affected by the proposed construction works. These individuals should be provided with a copy of the draft CMP, or a link to an online document. They should be given adequate time with which to respond to the draft CMP, and any subsequent amended drafts. Contact details which include a phone number and email address of the site manager should also be provided.**

Significant time savings can be made by running an effective neighbourhood consultation process. This must be undertaken in the spirit of cooperation rather than one that is dictatorial and unsympathetic to the wellbeing of local residents and businesses.

These are most effective when initiated as early as possible and conducted in a manner that involves the local community. Involving locals in the discussion and decision making process helps with their understanding of what is being proposed in terms of the development process. **The consultation and discussion process should have already started, with the results incorporated into the CMP first draft submitted to the Council for discussion and sign off.**This communication should then be ongoing during the works, with neighbours and any community liaison groups being regularly updated with programmed works and any changes that may occur due to unforeseen circumstances through newsletters, emails and meetings.

Please note that for larger sites, details of a construction working group may be required as a separate S106 obligation. If this is necessary, it will be set out in the S106 Agreement as a separate requirement on the developer.

**Cumulative impact**

Sites located within high concentrations of construction activity that will attract large numbers of vehicle movements should consider establishing contact with other sites in the vicinity in order to manage traffic routeing and volumes. Developers in the Tottenham Court Road area have done this to great effect.

**The Council can advise on this if necessary.**

**13. Consultation**

The Council expects meaningful consultation. For large sites, this may mean two or more meetings with local residents **prior to submission of the first draft CMP**.

Evidence of who was consulted, how the consultation was conducted and a summary of the comments received in response to the consultation. Details of meetings including minutes, lists of attendees etc. must be included.

In response to the comments received, the CMP should then be amended where appropriate and, where not appropriate, a reason should be given. The revised CMP should also include a list of all the comments received. Developers are advised to check proposed approaches to consultation with the Council before carrying them out. If your site is on the boundary between boroughs then we would recommend contacting the relevant neighbouring planning authority.

Please provide details of consultation of draft CMP with local residents, businesses, local groups (e.g. residents/tenants and business associations) and Ward Councillors.

Meaningful consultation has been undertaken and is evidenced in Appendix L - Consult List and Responses. Whilst various addressees requested copies of the CMP or acknowledged receipt, no parties have made any comment on the proposals.

**14. Construction Working Group**

Please provide details of community liaison proposals including any Construction Working Group that will be set up, addressing the concerns of the community affected by the works, the way in which the contact details of the person responsible for community liaison will be advertised to the local community, and how the community will be updated on the upcoming works i.e. in the form of a newsletter/letter drop, or weekly drop in sessions for residents.

Prior to commencement onsite the Contractor will undertake to notify by letter all residents with 500m of the site in either direction and on both sides of Oakhill Avenue. This letter will contain details of the anticipated duration of the project, the agreed working hours of the site and the contact details of the Head Office, the Supervisory Staff and Health & Safety Officers.

The Contractor will also provide a regular newsletter to local resident to update them on progress and measures taken to protect their interests.

The Contractor will answer any queries in a timely fashion and endeavour to take all feedback into consideration throughout the full programme of works.

**15. Schemes**

Please provide details of any schemes such as the ‘Considerate Constructors Scheme’, such details should form part of the consultation and be notified to the Council. Contractors will also be required to follow the “[Guide for Contractors Working in Camden](http://www.camden.gov.uk/ccm/cms-service/download/asset?asset_id=799001)” also referred to as “[Camden’s Considerate Contractors Manual](http://www.camden.gov.uk/ccm/cms-service/download/asset?asset_id=799001)”.

London Basement is registered with the Considerate Constructors Scheme and always works within its guidelines. We also reviewed the Guide for Contractors Working in Camden and its contents has been considered in preparing this Construction Management Plan.

**16. Neighbouring sites**

Please provide a plan of existing or anticipated construction sites in the local area and please state how your CMP takes into consideration and mitigates the cumulative impacts of construction in the vicinity of the site. The council can advise on this if necessary.

Please refer to Appendix E – Oakhill Avenue (2) CTMP Rev 2

**Transport**

**This section must be completed in conjunction with your principal contractor. If one is not yet assigned, please leave the relevant sections blank until such time when one has been appointed.**

Camden is a CLOCS Champion, and is committed to maximising road safety for Vulnerable Road Users (VRUs) as well as minimising negative environmental impacts created by motorised road traffic. As such, all vehicles and their drivers servicing construction sites within the borough are bound by the conditions laid out in the [CLOCS Standard.](http://www.clocs.org.uk/wp-content/uploads/2014/09/CLOCS-Standard-v1.2.pdf)

This section requires details of the way in which you intend to manage traffic servicing your site, including your road safety obligations with regard to VRU safety. It is your responsibility to ensure that your principal contractor is fully compliant with the terms laid out in the CLOCS Standard. It is your principal contractor’s responsibility to ensure that all contractors and sub-contractors attending site are compliant with the terms laid out in the CLOCS Standard.

Checks of the proposed measures will be carried out by the council to ensure compliance. Please refer to the CLOCS Standard when completing this section. Guidance material which details CLOCS requirements can be accessed [here](http://www.camden.gov.uk/ccm/cms-service/stream/asset/?asset_id=3345819&), details of the monitoring process are available [here](http://www.camden.gov.uk/ccm/cms-service/stream/asset/?asset_id=3345820&).

Please contact [CLOCS@camden.gov.uk](mailto:CLOCS@camden.gov.uk) for further advice or guidance on any aspect of this section.

**Please refer to the CLOCS Overview and Monitoring Overview documents referenced above which give a breakdown of requirements.**

**CLOCS Considerations**

17. Name of Principal contractor:

London Basement

18. Please submit the proposed method for checking operational, vehicle and driver compliance with the CLOCS Standard throughout the duration of the contract (please refer to our CLOCS Overview document in the appendix and CLOCS Standard point 3.4.7).

* London Basement will at point of order ensure through written assurance that all supply and muck away contractors using vehicles over 3.5T are registered with FORS using the CLOCS Compliance check form and non-conformance report form. Non-conforming vehicles or operators will not be considered for employment.
* All vehicles attending site over 3.5T will be required to have blindspot minimisation equipment and audible left turn alerts
* Site managers will be issued with Compliance checking and monitoring process-diagram (fig.3 of CTMP)
* The site will display the CLOCS compliance poster A1 (fig.4 of CTMP) size in a prominent place on the site hoarding.

19. Please confirm that you as the client/developer and your principal contractor have read and understood the [CLOCS Standard](http://www.clocs.org.uk/wp-content/uploads/2015/05/CLOCS-Standard-v1.2-APRIL_15.pdf) and included it in your contracts. Please sign-up to join the [CLOCS Community](http://www.clocs.org.uk/links-to-partners/) to receive up to date information on the standard by expressing an interest online.

I confirm that I have included the requirement to abide by the CLOCS Standard in my contracts to my contractors and suppliers:

Confirmed.

Please contact [CLOCS@camden.gov.uk](mailto:CLOCS@camden.gov.uk) for further advice or guidance on any aspect of this section.

**Site Traffic**

**Sections below shown in blue directly reference the CLOCS Standard requirements. The CLOCS Standard should be read in conjunction with this section.**

**20. Traffic routing**: *“Clients shall ensure that a suitable, risk assessed vehicle route to the site is specified and that the route is communicated to all contractors and drivers. Clients shall make contractors and any other service suppliers aware that they are to use these routes at all times unless unavoidable diversions occur.”* (P19, 3.4.5)

Routes should be carefully considered and risk assessed, taking into account the need to avoid where possible any major cycle routes and trip generators such as schools, offices, public buildings,museums etc. Where appropriate, on routes that use high risk junctions (i.e. those that attract high volumes of cycling traffic) installing Trixi mirrors to aid driver visibility should be considered.

Consideration should also be given to weight restrictions, low bridges and cumulative impacts of construction (including neighbouring construction sites) on the public highway network. The route(s) to and from the site should be suitable for the size of vehicles that are to be used.

a. Please indicate routes on a drawing or diagram showing the public highway network in the vicinity of the site including details of links to the [Transport for London Road Network](http://www.lscp.org.uk/lrsu/engineering_tlrn.html) (TLRN).

Please see Appendix H. Routes have been carefully considered and avoid major cycle routes and trip generators.

b. Please confirm how contractors, delivery companies and visitors will be made aware of the route (to and from the site) and of any on-site restrictions, prior to undertaking journeys.

Contractors, delivery companies and visitors will be made aware of the route and that there is no parking available on site. All site operatives are encouraged to use public transport and a copy of the CMP will be kept on site for reference. The CMP will also be attached to all purchase orders thus altering delivery companies to the route. The foreman will ensure that drivers adhere to this and should any driver fail to follow the route and direction their head office will be advised and asked to take remedial action.

**21. Control of site traffic, particularly at peak hours**: “*Clients shall consider other options to plan and control vehicles and reduce peak hour deliveries”* (P20, 3.4.6)

Construction vehicle movements are generally acceptable between 9.30am to 4.30pm on weekdays and between 8.00am and 1.00pm on Saturdays). If there is a school in the vicinity of the site or on the proposed access and/or egress routes, then deliveries must be restricted to between 9.30am and 3pm on weekdays during term time. (Refer to the [*Guide for Contractors Working in Camden*](http://www.camden.gov.uk/ccm/cms-service/download/asset?asset_id=799001)).

A delivery plan should ensure that deliveries arrive at the correct part of site at the correct time. Instructions explaining such a plan should be sent to all suppliers and contractors**.** Consideration should be given to the location of any necessary holding areas for large sites with high volumes of traffic. Vehicles must not wait or circulate on the public highway. Whilst deliveries should be given set times to arrive, dwell and depart, no undue time pressures should be placed upon the driver at any time.

a. Please provide details of the typical sizes of all vehicles and the approximate frequency and times of day when they will need access to the site, for each phase of construction.You should estimate the average daily number of vehicles during each major phase of the work, including their dwell time at the site. High numbers of vehicles per day and/or long dwell times may require vehicle holding procedures.

Construction vehicle movements will be restricted to between 0930 and 1630 Monday to Friday. There are no schools within the immediate vicinity of the site or on the proposed access and/or egress routes.

A map of the route construction vehicles should take will be attached to purchase orders. London Basement follows a strict call off procedure detailed as follows:

**London Basement Call Off Procedure**

1. Materials will be ordered through the Head Office Purchasing Department at least 48 hours prior to their requirement onsite. Site foremen will be instructed to ensure orders are to be kept to a minimum to avoid delays in off load and double handling after being stored in our compound.

2. We use licensed contractors for the removal of our excavated material, which will be requested by site staff and scheduled by the Head Office Contracts Administrator a minimum of 24 hours prior to their requirement on site.

3. All delivery/collection drivers will be required to notify the site foreman at least 20 minutes before arrival.

4. All deliveries/collections will be arranged for between0930 and 1630 Monday to Friday. Any deliveries/collections out of the stipulated time boundaries will be refused.

5. Stacking of vehicles is not acceptable at any time.

b. Please provide details of other developments in the local area or on the route.

Please refer to Appendix E – Oakhill Avenue (2) CTMP Rev 2

c. Please outline the system that is to be used to ensure that the correct vehicle attends the correct part of site at the correct time.

The London Basement call off procedure is detailed in 21a above. All deliveries and collections will be to the front of the site next to the skip hoarding.

d. Please identify the locations of any off-site holding areas (an appropriate location outside the borough may need to be identified, particularly if a large number of delivery vehicles are expected) and any measures that will be taken to ensure the prompt admission of vehicles to site in light of time required for any vehicle/driver compliance checks. Please refer to question 24 if any parking bay suspensions will be required for the holding area.

This is a residential extension project and large numbers of delivery vehicles are not expected. There will be no requirement for off-site holding areas. There will be no double stacking of vehicles attending site and this will be managed through the London Basement call off procedure. Vehicles attending site outside of their allocated times will be sent away.

e. Please provide details of any other measures designed to reduce the impact of associated traffic (such as the use of [construction material consolidation centres](http://content.tfl.gov.uk/directory-of-london-consolidation-centres.pdf)).

Site operatives are encouraged to use public transport to get to work. By using grab lorries (rather than skip wagons or wait & load vehicles) we will minimise the number of spoil collections. All materials will be stored on site therefore consolidation centres will not be required.

**22. Site access and egress:** “*Clients shall ensure that access to and egress from the site is appropriately managed, clearly marked, understood and clear of obstacles.”* (P18, 3.4.3)

Vehicles entering and leaving the site should be carefully managed, using gates that are clearly marked and free from obstacles. Traffic Marshalls must ensure the safe passage of pedestrians, cyclists and other traffic when vehicles are entering and leaving site, particularly if reversing.

a. Please detail the proposed access and egress routes to and from the site

This is a pedestrian site and no vehicles will enter or leave.

b. Please describe how the access and egress arrangements for construction vehicles will be managed.

Although no vehicles will have access to or egress from site fully trained banksmen will be in attendance as necessary for all deliveries and collections.

c. Please provide swept path drawings for any tight manoeuvres on vehicle routes to and from the site including proposed access and egress arrangements at the site boundary (if necessary).

There are no tight manoeuvres on the proposed routes to and from site. There will be no vehicle access to or egress from the site.

d. Provision of wheel washing facilities should be considered if necessary. If so, please provide details of how this will be managed and any run-off controlled.

This is a pedestrian site with no vehicle access so wheel washing facilities will not be required.

**23. Vehicle loading and unloading:** *“Clients shall ensure that vehicles are loaded and unloaded on-site as far as is practicable.”* (P19, 3.4.4)

If this is not possible, Traffic Marshalls must ensure the safe passage of pedestrians, cyclists and motor traffic in the street when vehicles are being loaded or unloaded.

Please provide details of the parking and loading arrangements for construction vehicles with regard to servicing and deliveries associated with the site (e.g. delivery of materials and plant, removal of excavated material). This is required as a scaled site plan, showing all points of access and where materials, skips and plant will be stored, and how vehicles will access and egress the site. If loading is to take place off site, please identify where this is due to take place and outline the measures you will take to ensure that loading/unloading is carried out safely. Please outline in question 24 if any parking bay suspensions will be required.

Please see Appendix C – Site Set Up Plan. The site will have no vehicle access. All deliveries and collections will take place next to the hoarded skip on the street. Trained banksmen will be in attendance throughout and priority given to pedestrians and other road users. Deliveries will be immediately taken into the site itself and not stored on the highway. Parking bay suspensions will be required as detailed below.

**Highway interventions**

**Please note that Temporary Traffic Orders (TTOs) and hoarding/scaffolding licenses may be applied for prior to CMP submission but won’t be granted until the CMP is signed-off.**

**24. Parking bay suspensions and temporary traffic orders**

Please note, parking bay suspensions should only be requested where absolutely necessary. Parking bay suspensions are permitted for a maximum of 6 months, requirement of exclusive access to a bay for longer than 6 months you will be required to obtain [Temporary Traffic Order (TTO)](http://camden.gov.uk/ccm/content/transport-and-streets/traffic-management/temporary-road-restrictions/) for which there is a separate cost.

Please provide details of any proposed parking bay suspensions and TTO’s which would be required to facilitate construction. **Building materials and equipment must not cause obstructions on the highway as per your Considerate Contractors obligations unless the requisite permissions are secured.**

Information regarding parking suspensions can be found [here.](http://www.camden.gov.uk/ccm/navigation/transport-and-streets/parking/parking-bay-suspensions/)

The parking bay outside the property will be suspended during the working day for material deliveries. The single yellow line outside the property (which is in place to keep the dropped kerb clear) will be utilised for the hoarded skip. Towards the end of the works for the pouring of the floor slabs the skip and hoarding will be cleared and the yellow line / parking bay will be used for a concrete wagon and pump.

**25. Scaled drawings of highway works**

Please note that use of the public highway for storage, site accommodation or welfare facilities is at the discretion of the Council and is generally not permitted. If you propose such use you must supply full justification, setting out why it is impossible to allocate space on-site. You must submit a detailed (to-scale) plan showing the impact on the public highway that includes the extent of any hoarding, pedestrian routes, parking bay suspensions and remaining road width for vehicle movements. We prefer not to close footways but if this is unavoidable, you should submit a scaled plan of the proposed diversion route showing key dimensions.

a. Please provide accurate scaled drawings of any highway works necessary to enable construction to take place (e.g. construction of temporary vehicular accesses).

No highway works will be need for construction to take place.

b.Please provide details of all safety signage, barriers and accessibility measures such as ramps and lighting etc.

Please refer to Appendix C – Site Set Up Plan.

**26. Diversions**

Where applicable, please supply details of any diversion, disruption or other anticipated use of the public highway during the construction period (alternatively a plan may be submitted).

No diversions, disruptions or other uses of the public highway during the construction period are anticipated.

**27. VRU and pedestrian diversions, scaffolding and hoarding**

Pedestrians and/or cyclist safety must be maintained if diversions are put in place. Vulnerable footway users should also be considered. These include wheelchair users, the elderly, those with walking difficulties, young children, those with prams, the blind and partially sighted. Appropriate ramping must be used if cables, hoses, etc. are run across the footway.

Any work above ground floor level may require a covered walkway adjacent to the site. A licence must be obtained for scaffolding and gantries. The adjoining public highway must be kept clean and free from obstructions. Lighting and signage should be used on temporary structures/skips/hoardings etc.

A secure hoarding will generally be required at the site boundary with a lockable access.

a. Please provide details describing how pedestrian and cyclist safety will be maintained, including any proposed alternative routes (if necessary), and any Traffic Marshall arrangements.

Pedestrian and cyclist safety will be maintained at all times. The wide walkway will ensure pedestrian traffic is not limited by the works and care will be taken to ensure materials being carried into the site do not block pedestrian traffic. Power cables for the hoarding lights and the hose for concrete pours will be run along the overhead conveyor gantry. Trained banksmen will be present as required when construction vehicles are in attendance to supervise deliveries and collections.

b. Please provide details of any temporary structures which would overhang the public highway (e.g. scaffolding, gantries, cranes etc.) and details of hoarding requirements or any other occupation of the public highway.

A hoarded conveyor will cross the pavement with a minimum clearance of 2.4m. This will feed into a hoarded skip on the single yellow line in front of the dropped kerb. The adjoining public highway will be kept clean and free from obstructions. Appropriate lighting and signage will be used as necessary and the requisite licences in place.

SYMBOL IS FOR INTERNAL USE

**Environment**

To answer these sections please refer to the relevant sections of **Camden’s Minimum Requirements for Building Construction (**[**CMRBC**](http://www.camden.gov.uk/ccm/cms-service/download/asset?asset_id=3257318)**).**

28. Please list all [noisy operations](http://www.camden.gov.uk/ccm/content/environment/environmental-health--consumer-protection/noise/reducing-noise/noise-from-construction-sites.en?page=2)  and the construction method used, and provide details of the times that each of these are due to be carried out.

Please see Appendix D; 17078.NVDMP.01 Rev.A b KP Acoustics

29. Please confirm when the most recent noise survey was carried out (before any works were carried out) and provide a copy. If a noise survey has not taken place please indicate the date (before any works are being carried out) that the noise survey will be taking place, and agree to provide a copy.

A noise survey has not been undertaken but will be carried out approximately 1 month before works start on site. A copy of this survey will be provided to KP Acoustics for analysis and possible revisions to the NVDMP and the Local Authority for their records.

30. Please provide predictions for [noise](http://www.camden.gov.uk/ccm/content/environment/environmental-health--consumer-protection/noise/reducing-noise/noise-from-construction-sites.en?page=2) and vibration levels throughout the proposed works.

Please see Appendix D; 17078.NVDMP.01 Rev.A b KP Acoustics

31. Please provide details describing mitigation measures to be incorporated during the construction/[demolition](http://www.camden.gov.uk/ccm/navigation/environment/building-control/demolition/) works to prevent noise and vibration disturbances from the activities on the site, including the actions to be taken in cases where these exceed the predicted levels.

Please see Appendix D; 17078.NVDMP.01 Rev.A b KP Acoustics and Appendix F: Oakhill Avenue CMS.Rev 2

32. Please provide evidence that staff have been trained on BS 5228:2009

All staff receives ongoing training including regarding noise and vibration levels (BS 5228:2009). All site managers have taken the five day Site Managers Safety Training Scheme (SMSTS) course.

33. Please provide details on how dust nuisance arising from dusty activities, on site, will be prevented.

Please see Appendix D; 17078.NVDMP.01 Rev.A b KP Acoustics

34. Please provide details describing how any significant amounts of dirt or dust that may be spread onto the public highway will be prevented and/or cleaned.

Please see Appendix D; 17078.NVDMP.01 Rev.A b KP Acoustics

35. Please provide details describing arrangements for monitoring of [noise](http://www.camden.gov.uk/ccm/content/environment/environmental-health--consumer-protection/noise/reducing-noise/noise-from-construction-sites.en?page=2), vibration and dust levels.

Please see Appendix D; 17078.NVDMP.01 Rev.A b KP Acoustics

36. Please confirm that a [Risk Assessment](http://www.hse.gov.uk/risk/controlling-risks.htm) has been undertaken at planning application stage in line with the [GLA’s Control of Dust and Emissions Supplementary Planning Guidance](https://www.london.gov.uk/priorities/planning/publications/the-control-of-dust-and-emissions-during-construction-and) (SPG), and the risk level that has been identified, with evidence. Please attach the risk assessment as an appendix if not completed at the planning application stage.

Confirmed – Please see Appendix D; 17078.NVDMP.01 Rev.A b KP Acoustics

37. Please confirm that all of the GLA’s ‘highly recommended’ measures from the [SPG](https://www.london.gov.uk/priorities/planning/publications/the-control-of-dust-and-emissions-during-construction-and) document relative to the level of risk identified in question 36 have been addressed by completing the [GLA mitigation measures checklist.](https://www.camden.gov.uk/ccm/content/appendix-to-environment-section-question-37--dust-mitigation-measures.en)

Confirmed – Please see Appendix D; 17078.NVDMP.01 Rev.A b KP Acoustics

38. If the site is a ‘High Risk Site’, 4 real time dust monitors will be required. If the site is a ‘Medium Risk Site’, 2 real time dust monitors will be required. The risk assessment must take account of proximity to sensitive receptors (e.g. schools, care homes etc), as detailed in the [SPG](https://www.london.gov.uk/priorities/planning/publications/the-control-of-dust-and-emissions-during-construction-and). Please confirm the location, number and specification of the monitors in line with the SPG and confirm that these will be installed 3 months prior to the commencement of works, and that real time data and quarterly reports will be provided to the Council detailing any exceedances of the threshold and measures that were implemented to address these.

Please see Appendix D; 17078.NVDMP.01 Rev.A b KP Acoustics

Continual monitoring to be implemented by specialist prior to construction.

39. Please provide details about how rodents, including [rats](http://www.camden.gov.uk/ccm/content/environment/environmental-health--consumer-protection/pest-control/about-the-pest-control-service.en), will be prevented from spreading out from the site. You are required to provide information about site inspections carried out and present copies of receipts (if work undertaken).

Please see Appendix K: Service Report by Nightshift Pest Control Ltd and Appendix F: Oakhill Avenue (2) CMS Rev2.

40. Please confirm when an asbestos survey was carried out at the site and include the key findings.

We confirm that a Asbestos Survey was carried out on the 29th November 2017. The findings are detailed within Appendix M. L-00649 2 Oakhill Avenue Refurbishment Survey Report

41. Complaints often arise from the conduct of builders in an area. Please confirm steps being taken to minimise this e.g. provision of a suitable smoking area, tackling bad language and unnecessary shouting.

Please refer to Appendix F – Oakhill Avenue (2) CMS Rev 2

42. If you will be using non-road mobile machinery (NRMM) on site with net power between 37kW and 560kW it will be required to meet the standards set out below. The standards are applicable to both variable and constant speed engines and apply for both PM and NOx emissions.

**From 1st September 2015**

**(i) Major Development Sites** – NRMM used on the site of any major development will be required to meet Stage IIIA of EU Directive 97/68/EC

**(ii) Any development site within the Central Activity Zone -** NRMM used on any site within the Central Activity Zone will be required to meet Stage IIIB of EU Directive 97/68/EC

**From 1st September 2020**

**(iii) Any development site -** NRMM used on any site within Greater London will be required to meet Stage IIIB of EU Directive 97/68/EC

**(iv) Any development site within the Central Activity Zone -** NRMM used on any site within the Central Activity Zone will be required to meet Stage IV of EU Directive 97/68/EC

Please provide evidence demonstrating the above requirements will be met by answering the following questions:

1. Construction time period (mm/yy - mm/yy ): 03/2018 – 10/2018
2. Is the development within the CAZ? (Y/N): No
3. Will the NRMM with net power between 37kW and 560kW meet the standards outlined above? (Y/N): Yes
4. Please provide evidence to demonstrate that all relevant machinery will be registered on the NRMM Register, including the site name under which it has been registered: All relevant machinery will be registered on the NRMM Register and it will include the site name under which it has been registered.
5. Please confirm that an inventory of all NRMM will be kept on site and that all machinery will be regularly serviced and service logs kept on site for inspection: Confirmed
6. Please confirm that records will be kept on site which details proof of emission limits, including legible photographs of individual engine plates for all equipment, and that this documentation will be made available to local authority officers as required: Confirmed

SYMBOL IS FOR INTERNAL USE

**Agreement**

The agreed contents of this Construction Management Plan must be complied with unless otherwise agreed in writing by the Council. This may require the CMP to be revised by the Developer and reapproved by the Council. The project manager shall work with the Council to review this Construction Management Plan if problems arise in relation to the construction of the development. Any future revised plan must be approved by the Council in writing and complied with thereafter.

It should be noted that any agreed Construction Management Plan does not prejudice further agreements that may be required such as road closures or hoarding licences.

**Please notify that council when you intend to start work on site. Please also notify the council when works are approximately 3 months from completion.**

****

**Signed:** …………………………………………………………………

**Date:** 15th November 2017

**Print Name:** Jake Puddy

**Position:** Business Development Manager

Please submit to: [planningobligations@camden.gov.uk](mailto:planningobligations@camden.gov.uk)

End of form.