## Project Summary
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
Project Summary
|  | ORIGINAL CONTRACT SUM |  |  |  |  | PROJECTED FINAL ACCOUNT
| Property | Cost of Activities | Provisional Sums | Project Overheads | Central Overheads and Profit | TOTAL | Cost of Activities | Provisional Sums | Project Overheads | Central Overheads and Profit | TOTAL
0 | 1-44 Denyer House | 181652.9707 | 4000 | 56865.0339 | 9540.7202 | 248058.7248 | 109045.8007 | 0 | 25137.2935 | 5367.3238 | 139550.418
1 | 1-10 Lissenden Mansions | 75420.7934 | 30235.16 | 23609.8862 | 3961.2272 | 102991.9069 | 75420.7934 | 0 | 17386.0397 | 3712.2733 | 96519.1065
2 | 25 Troyes House | 85991.8093 | 68200 | 26919.0596 | 4516.4348 | 117427.3037 | 85426.7355 | 0 | 19692.6146 | 4204.774 | 109324.1241
3 | 11-20 Lissenden Mansions- | 75381.3074 | 0 | 23597.5255 | 3959.1533 | 102937.9862 | 75381.3074 | 0 | 17376.9374 | 3710.3298 | 96468.5746
4 | 5 Gillies Street | 7001.8317 | 1050 | 2191.8683 | 367.748 | 9561.448 | 7001.8317 | 0 | 1614.0658 | 344.6359 | 8960.5333
5 | 8 Dale Road | 10788.9668 | 2150 | 3377.4012 | 566.6547 | 14733.0227 | 10788.9668 | 0 | 2487.0781 | 531.0418 | 13807.0867
6 | 11 Gillies Street A-B | 17176.1603 | 3650 | 5376.8619 | 902.1209 | 23455.1431 | 17176.1603 | 0 | 3959.4572 | 845.4247 | 21981.0423
7 | 30 Grove Terrace Flats A-C | 14003.5347 | 1700 | 4383.6964 | 735.4892 | 19122.7203 | 14003.5347 | 0 | 3228.1019 | 689.2655 | 17920.9021
8 | 25 Elaine Grove | 15466.5622 | 2150 | 4841.6857 | 812.3299 | 21120.5778 | 15466.5622 | 0 | 3565.3598 | 761.2769 | 19793.1989
9 | 130 Prince of Wales Road | 16297.9675 | 8390 | 5101.9506 | 855.9967 | 22255.9148 | 16297.9675 | 0 | 3757.0158 | 802.1993 | 20857.1827
10 | 25 Herbert Street Flats A-B | 8164.8634 | 2550 | 2555.9463 | 428.8324 | 11149.642 | 8164.8634 | 0 | 1882.1685 | 401.8813 | 10448.9131
11 | 128 Prince of Wales | 8106.5147 | 2150 | 2537.6807 | 425.7678 | 11069.9633 | 8106.5147 | 0 | 1868.7179 | 399.0093 | 10374.242
12 | 10 Gillies Street | 6106.8112 | 0 | 1911.6892 | 320.74 | 8339.2404 | 6106.8112 | 0 | 1407.7452 | 300.5823 | 7815.1386
13 | 17 Ascham Street | 12170.9145 | 2550 | 3810.0091 | 639.2369 | 16620.1605 | 12170.9145 | 0 | 2805.6454 | 599.0624 | 15575.6223
14 | 13 Doynton Street | 7669.402 | 3066.8 | 2400.846 | 402.8099 | 10473.0579 | 7669.402 | 0 | 1767.9545 | 377.4943 | 9814.8507
15 | 111 Chetwynd Road | 29788.8504 | 3530 | 9325.1653 | 1564.5606 | 40678.5764 | 29788.8504 | 0 | 6866.941 | 1466.2317 | 38122.023
16 | 19 Ascham Street Flats A-B | 13016.5097 | 5100 | 4074.716 | 683.649 | 17774.8747 | 13016.5097 | 0 | 3000.5724 | 640.6833 | 16657.7654
17 | 66 LevertonStreet(Flats A-B) | 17284.3926 | 500 | 5410.7432 | 907.8054 | 23602.9412 | 17284.3926 | 0 | 3984.407 | 850.752 | 22119.5516
18 | 13 Oseney Crescent | 13331.4148 | 6720 | 4173.2946 | 700.1884 | 18204.8978 | 13331.4148 | 0 | 3073.1645 | 656.1832 | 17060.7625
19 | 29 Grove TerraceFlatsA-C- | 13952.1649 | 2100 | 4367.6155 | 732.7912 | 19052.5716 | 13952.1649 | 0 | 3216.2602 | 686.737 | 17855.1621
20 | 28 Leighton Road Flats A-B | 17108.6909 | 2750 | 5355.7411 | 898.5773 | 23363.0093 | 17108.6909 | 0 | 3943.9041 | 842.1038 | 21894.6988
21 | 13 Mortimer Terrace | 9517.2741 | 2150 | 2979.3078 | 499.8633 | 12996.4452 | 9517.2741 | 0 | 2193.9269 | 468.448 | 12179.649
22 | 13 Winscombe Terrace | 7955.1512 | 2150 | 2490.2975 | 417.818 | 10863.2667 | 7955.1512 | 0 | 1833.8255 | 391.5591 | 10180.5358
| Contingency for Scope Creep | [5 empty] | 590182.6147 |  |  | 23607.3046 | 613789.9193
| TOTAL | 663354.8585 | 156841.96 | 207658.0215 | 34840.5152 | 905853.3952 | 1180365.2295 | 0 | 136049.197 | 52656.5771 | 1369071.0035

## Valuation Summary
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
Valuation No.2
Property | MCL Gross Cumulative Valuation | Gross Certified Valuation | Difference
1-44 Denyer House | 52870.989 | 0 | 52870.989
1-10 Lissenden Mansions | 0 | 0 | 0
25 Troyes House | 8614.41 | 0 | 8614.41
11-20 Lissenden Mansions- | 0 | 0 | 0
5 Gillies Street | 2044.8016 | 0 | 2044.8016
8 Dale Road | 0 | 0 | 0
11 Gillies Street A-B | 2845.5315 | 0 | 2845.5315
30 Grove Terrace Flats A-C | 0 | 0 | 0
25 Elaine Grove | 3887.1144 | 0 | 3887.1144
130 Prince of Wales Road | 0 | 0 | 0
25 Herbert Street Flats A-B | 0 | 0 | 0
128 Prince of Wales | 0 | 0 | 0
10 Gillies Street | 2645.664 | 0 | 2645.664
17 Ascham Street | 0 | 0 | 0
13 Doynton Street | 1345.5904 | 0 | 1345.5904
111 Chetwynd Road | 0 | 0 | 0
19 Ascham Street Flats A-B | 0 | 0 | 0
66 LevertonStreet(Flats A-B) | 2868.8182 | 0 | 2868.8182
13 Oseney Crescent | 0 | 0 | 0
29 Grove TerraceFlatsA-C- | 0 | 0 | 0
28 Leighton Road Flats A-B | 0 | 0 | 0
13 Mortimer Terrace | 0 | 0 | 0
13 Winscombe Terrace | 0 | 0 | 0
Project Overheads & Scaffold | 118410.2571 | 0 | 118410.2571
Central Overhead & Profit @ 4.0% | 7821.3271 | 0 | 7821.3271
TOTAL | 203354.5033 | 0 | 203354.5033

## Project Overheads & Scaffold
[6 empty] | Original Contract Sum | [5 empty] | Projected Final Account | [5 empty] | MCL Application |  | Pellings Assessment
Requirement | Requirement Type | Rowtype (H= Header, D = Detail) | Description | SOR Code | SOR Unit | No Units | Allocation | No Months | Tendered rate | Improved rate | Total Cost | No Units | Allocation | No Months | Tendered rate | Improved rate | Total Cost | Percentage Complete | Total Cost | Percentage Complete | Total Cost
| PROJECT OVERHEADS - Staffing | H
| PROJECT OVERHEADS - Staffing | D | Project Manager | 1.01 | Unit/Month |  |  |  | 6098.25 |  | 0 |  |  |  | 6098.25 |  | 0 |  | 0 |  | 0
| PROJECT OVERHEADS - Staffing | D | Senior Contract Manager | 1.02 | Unit/Month |  |  |  | 7355 |  | 0 |  |  |  | 7355 |  | 0 |  | 0 |  | 0
| PROJECT OVERHEADS - Staffing | D | Contract Manager | 1.03 | Unit/Month | 1 | 40% | 3.25 | 5427 |  | 7055.1 | 1 | 40% | 5.3214 | 5427 |  | 11551.7571 | 44.97% | 5194.4143 |  | 0
| PROJECT OVERHEADS - Staffing | D | Senior Site Manager | 1.04 | Unit/Month |  |  |  | 4996.75 |  | 0 |  |  |  | 4996.75 |  | 0 |  | 0 |  | 0
| PROJECT OVERHEADS - Staffing | D | Site Manager | 1.05 | Unit/Month | 2 | 100% | 3.25 | 4471.5 |  | 29064.75 | 2 | 100% | 5.3214 | 4471.5 |  | 47589.5357 | 44.97% | 21399.3214 |  | 0
| PROJECT OVERHEADS - Staffing | D | Assistant Site Manager | 1.06 | Unit/Month |  |  |  | 3910.5 |  | 0 |  |  |  | 3910.5 |  | 0 |  | 0 |  | 0
| PROJECT OVERHEADS - Staffing | D | Site Supervisor | 1.07 | Unit/Month |  |  |  | 2903.8 |  | 0 |  |  |  | 2903.8 |  | 0 |  | 0 |  | 0
| PROJECT OVERHEADS - Staffing | D | Technical (Lifts, Electrical, Etc) Supervisor | 1.08 | Unit/Month |  |  |  | 3693.5 |  | 0 |  |  |  | 3693.5 |  | 0 |  | 0 |  | 0
| PROJECT OVERHEADS - Staffing | D | Co-ordinator / RLO / TLO | 1.09 | Unit/Month | 2 | 100% | 3.25 | 2479.4 |  | 16116.1 | 2 | 100% | 5.3214 | 2479.4 |  | 26387.9 | 44.97% | 11865.7 |  | 0
| PROJECT OVERHEADS - Staffing | D | Senior QS | 1.1 | Unit/Month |  |  |  | 6388 |  | 0 |  |  |  | 6388 |  | 0 |  | 0 |  | 0
| PROJECT OVERHEADS - Staffing | D | QS | 1.11 | Unit/Month | 1 | 50% | 3.25 | 5935.5 |  | 9645.1875 | 1 | 50% | 5.3214 | 5935.5 |  | 15792.6696 | 44.97% | 7101.4018 |  | 0
| PROJECT OVERHEADS - Staffing | D | Assistant QS | 1.12 | Unit/Month |  |  |  | 2389.75 |  | 0 |  |  |  | 2389.75 |  | 0 |  | 0 |  | 0
| PROJECT OVERHEADS - Staffing | D | Ad Hoc Site Administrator | 1.13 | Unit/Month |  |  |  | 1694.55 |  | 0 |  |  |  | 1694.55 |  | 0 |  | 0 |  | 0
| PROJECT OVERHEADS - Other | H
| PROJECT OVERHEADS - Other | D | Site Office Cabin (At Site Office Location with furniture) (Drop off, pick up included) | 2.01 | Unit/Month | 1 | 100% | 3.25 | 142.56 |  | 463.32 | 1 | 100% | 5.3214 | 142.56 |  | 758.6229 | 44.97% | 341.1257 |  | 0
| PROJECT OVERHEADS - Other | D | Site Office Cabin (At Site Office Location) (Drop off, pick up included) | 2.02 | Unit/Month | 2 | 100% | 3.25 | 39.1 |  | 254.15 | 2 | 100% | 5.3214 | 39.1 |  | 416.1357 | 44.97% | 187.1214 |  | 0
| PROJECT OVERHEADS - Other | D | Site portable toilet and shower block ( drop off, pick up included) | 2.03 | Unit/Month |  |  |  | 928.8 |  | 0 |  |  |  | 928.8 |  | 0 |  | 0 |  | 0
| PROJECT OVERHEADS - Other | D | Site portable toilet 3+1 ( drop off, pick up, included) | 2.04 | Unit/Month | 1 | 100% | 3.25 | 928.8 |  | 3018.6 | 1 | 100% | 5.3214 | 928.8 |  | 4942.5429 | 44.97% | 2222.4857 |  | 0
| PROJECT OVERHEADS - Other | D | Site portable changing/ canteen/drying (drop off, pick up, included) | 2.05 | Unit/Month |  |  |  | 129.6 |  | 0 |  |  |  | 129.6 |  | 0 |  | 0 |  | 0
| PROJECT OVERHEADS - Other | D | Portaloo (drop off, pick up, included | 2.06 | Unit/Month | 6 | 100% | 3.25 | 86.4 |  | 1684.8 | 6 | 100% | 5.3214 | 86.4 |  | 2758.6286 | 44.97% | 1240.4571 |  | 0
| PROJECT OVERHEADS - Other | D | Site accomodation general waste per site set up | 2.07 | Unit/Month | 1 | 100% | 3.25 | 250 |  | 812.5 | 1 | 100% | 5.3214 | 250 |  | 1330.3571 | 44.97% | 598.2143 |  | 0
| PROJECT OVERHEADS - Other | D | Fencing / hoarding per set up | 2.08 | Unit/Month | 23 | 100% | 3.25 | 129.6 |  | 9687.6 | 23 | 100% | 5.3214 | 129.6 |  | 15862.1143 | 44.97% | 7132.6286 |  | 0
| PROJECT OVERHEADS - Other | D | Power per site set up | 2.09 | Unit/Month | 1 | 100% | 3.25 | 90 |  | 292.5 | 1 | 100% | 5.3214 | 90 |  | 478.9286 | 44.97% | 215.3571 |  | 0
| PROJECT OVERHEADS - Other | D | Telephone, communications for remote office Etc. Per site set up | 2.1 | Unit/Month | 1 | 100% | 3.25 | 80 |  | 260 | 1 | 100% | 5.3214 | 80 |  | 425.7143 | 44.97% | 191.4286 |  | 0
| PROJECT OVERHEADS - Other | D | Site set up safety (health & safety pack, first aid pack,fire extinguishers, Etc.) per site set up | 2.11 | Unit/Month | 1 | 100% | 3.25 | 200 |  | 650 | 1 | 100% | 5.3214 | 200 |  | 1064.2857 | 44.97% | 478.5714 |  | 0
| PROJECT OVERHEADS - Other | D | Set up signage | 2.12 | Unit/Month | 1 | 100% | 3.25 | 300 |  | 975 | 1 | 100% | 5.3214 | 300 |  | 1596.4286 | 44.97% | 717.8571 |  | 0
| PROJECT OVERHEADS - Other | D | Cleaning per site set up | 2.13 | Unit/Month | 1 | 100% | 3.25 | 301 |  | 978.25 | 1 | 100% | 5.3214 | 301 |  | 1601.75 | 44.97% | 720.25 |  | 0
| PROJECT OVERHEADS - Other | D | Sundries (office stationary, printers, water, etc) per site set up | 2.14 | Unit/Month | 1 | 100% | 3.25 | 129 |  | 419.25 | 1 | 100% | 5.3214 | 129 |  | 686.4643 | 44.97% | 308.6786 |  | 0
The contractor has set out below costs for any items such as, site security; watching the works; lifting, access or debris removal equipment, car parking suspension bay costs, licenses hoarding; fencing, power, water, additional staff, resources, etc. and all matters covered by the works information Scope of Works and section A EmployersRequirements not allowed elsewhere. The contractor is instructed to use the priced rates for builders works as submitted with the framework tender to price for items covered in that schedule.
| ADDITIONAL COSTs | D | Site labourer |  |  | 2 | 100% | 3.25 | 1760 |  | 11440 | 2 | 100% | 5.3214 | 1760 |  | 18731.4286 | 44.97% | 8422.8571 |  | 0
| ADDITIONAL COSTs | D | Building control |  |  | 1 | 100% | 1 | 6000 |  | 6000 | 1 | 100% | 1 | 6000 |  | 6000 | 0% | 0 |  | 0
| ADDITIONAL COSTs | D | Safety officer |  |  | 1 | 100% | 1 | 5720 |  | 5720 | 1 | 100% | 1 | 5720 |  | 5720 | 20% | 1144 |  | 0
| ADDITIONAL COSTs | D | Considerate constructor |  |  | 1 | 100% | 1 | 425 |  | 425 | 1 | 100% | 1 | 425 |  | 425 | 0% | 0 |  | 0
| ADDITIONAL COSTs | D | Nameboards/ Signage |  |  | 1 | 100% | 1 | 1000 |  | 1000 | 1 | 100% | 1 | 1000 |  | 1000 | 0% | 0 |  | 0
| ADDITIONAL COSTs | D | Hoist 1-44 Denyer House |  |  | 0 | 100% | 1 | 3275.5 |  | 0 | 0 | 100% | 1 | 3275.5 |  | 0 | 0% | 0 |  | 0
| ADDITIONAL COSTs | D | Transport |  |  | 1 | 100% | 1 | 3000 |  | 3000 | 1 | 100% | 1 | 3000 |  | 3000 | 25% | 750 |  | 0
| ADDITIONAL COSTs | D | Parking permits and skip licences |  |  | 1 | 100% | 1 | 7432.47 |  | 7432.47 | 1 | 100% | 1 | 7432.47 |  | 7432.47 | 25% | 1858.1175 |  | 0
| ADDITIONAL COSTs | D | Additional Scaffold and safety costs associated with wide spread isolated properties |  |  | 1 | 100% | 1 | 72716.01 |  | 72716.01 | 1 | 100% | 1 | 72716.01 |  | 72716.01 | 44.97% | 32697.8032 |  | 0
| ADDITIONAL COSTs | D | Uneconomical working |  |  | 1 | 100% | 1 | 18547.2 |  | 18547.2 | 1 | 100% | 1 | 18547.2 |  | 18547.2 | 44.97% | 8340.0161 |  | 0
| ADDITIONAL COSTs | D | LBC contribution to Denyer House TRA Office Refurbishment | [8 empty] | 1 | 100% | 1 | 5282.45 |  | 5282.45 | 100% | 5282.45 |  | 0
| ADDITIONAL COSTs | D
| ADDITIONAL COSTs | D
| ADDITIONAL COSTs | D
| ADDITIONAL COSTs | D
| ADDITIONAL COSTs | D
[10 empty] | TOTAL | 207657.7875 |  |  |  |  | TOTAL | 272098.3939 |  | 118410.2571 |  | 0
|  | 2017-02-20 | Original Start Date
|  | 2017-05-22 | Original Completion Date
|  | 13 | Total nr of weeks
|  | 3.25 | Total nr of months
|  | 2017-02-20 | Actual Start Date
|  | 2017-07-19 | Projected/Actual Completion Date
|  | 21.2857 | Total nr of weeks
|  | 5.3214 | Total nr of months
|  | 2017-04-28 | Valuation Date
|  | 9.5714 | Nr of weeks passed
|  | 2.3929 | Nr of months passed
|  | 44.97% | Percentage Complete

## 1-44 Denyer House
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
1-44 Denyer House
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB14020 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB14020 | ASBESTOS | H
| REPB14020 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 2 | 234 | 468 | #VALUE! | #VALUE! | 0 | 222.3 | 444.6 | Item | 2 | 222.3 | 444.6 | 0% | 0 | 0% | 0 | 0
| REPB14020 | COMMUNAL WORKS | H
| REPB14020 | COMMUNAL WORKS | D | Hall: Thoroughly clean down all wall and ceiling surfaces to common areas to remove dirt, grease and surface containments, scrape and remove all loose and defective coatings, prime bare areas with one coat of fire retardant primer and apply two coats of Class ‘O’ fire retardant matt paint, prepare and apply two coats of polyurethane lacquer or one undercoat and one gloss coat to all previously decorated timber surfaces to lobby, hall or corridor over 3.00sm ceiling area complete (classified as a single area). |  |  | 5.1 |  | 4540AC | IT | 2 | 480 | 960 | #VALUE! | #VALUE! | 0 | 408 | 816 | IT | 2 | 408 | 816 | 0% | 0 | 0% | 0 | 0
| REPB14020 | COMMUNAL WORKS | D | PROVISIONAL SUM: Replace or install post boxes with new vandal-resistant lockable post boxes. |  |  | 5.386 |  | PROV SUM | SUM | 1 | 200 | 200 | #VALUE! | 200 |  |  | 200 | SUM | 1 |  | 200 | 0% | 0 | 0% | 0 | 0
| REPB14020 | COMMUNAL WORKS | D | PROVISIONAL SUM: Secure storage area for bicycles (bike stands). |  |  | 5.387 |  | PROV SUM | SUM | 1 | 500 | 500 | #VALUE! | 500 |  |  | 500 | SUM | 1 |  | 500 | 0% | 0 | 0% | 0 | 0
| REPB14020 | EXTREP | H | [23 empty] | 0
| REPB14020 | EXTREP | D | Cills: Prepare, clean off all dust and debris, fill in or resurface cracks or spalled surfaces of concrete with epoxy mortar in surfaces of cills, not exceeding 300mm girth, repair over 5 and ne 10mm deep, and remove waste and debris. |  |  | 6.161 |  | 1460AF | LM | 100 | 38.25 | 3825 | #VALUE! | #VALUE! | 0 | 27.7312 | 2773.125 | LM | 100 | 27.7312 | 2773.125 | 0% | 0 | 0% | 0 | 0
| REPB14020 | EXTREP | D | Walls:Wash down, fill in cracks and holes, sand down and apply two coats of smooth or textured masonry paint to rendered or concrete walls. |  |  | 6.181 |  | 4356AC | SM | 28 | 9.55 | 267.4 | #VALUE! | #VALUE! | 0 | 8.1175 | 227.29 | SM | 28 | 8.1175 | 227.29 | 0% | 0 | 0% | 0 | 0
| REPB14020 | EXTREP | D | Gates: Wire brush, prepare for, and apply one coat primer, one undercoat, two coats of gloss paint to both sides of any size type single metal gate including all edges and all surfaces of posts. |  |  | 6.203 |  | 4362DA | IT | 2 | 21.61 | 43.22 | #VALUE! | #VALUE! | 0 | 18.3685 | 36.737 | IT | 2 | 18.3685 | 36.737 | 0% | 0 | 0% | 0 | 0
| REPB14020 | EXTREP | D | Balustrading: Wire brush, prepare for and apply one undercoat and two coats of gloss paint on existing painted surfaces ornamental metal balustrading, railings or gates (measured both sides). |  |  | 6.215 |  | 4363EA | SM | 425 | 16.08 | 6834 | #VALUE! | #VALUE! | 0 | 13.668 | 5808.9 | SM | 425 | 13.668 | 5808.9 | 0% | 0 | 0% | 0 | 0
| REPB14020 | EXTREP | D | Pipework: Wire brush, prepare for and apply one undercoat and one coat of gloss paint to existing painted surfaces of external pipework ne 300mm girth including brackets. |  |  | 6.228 |  | 4364GA | LM | 192 | 1.21 | 232.32 | #VALUE! | #VALUE! | 0 | 1.0285 | 197.472 | LM | 192 | 1.0285 | 197.472 | 0% | 0 | 0% | 0 | 0
| REPB14020 | ROOF | H | [23 empty] | 0
| REPB14020 | ROOF | D | Tile: Overhaul clay plain tile roof, refix loose tiles, renew broken or missing tiles to match existing, redress, rewedge and repoint all flashings, aprons, chimney gutters etc., cut out and make good cement weather fillets, repoint in cement mortar (1:3) to all hips, ridges and verges, make good, clear away debris. |  |  | 3.88 |  | 2013EA | SM | 580 | 30.56 | 17724.8 | #VALUE! | #VALUE! | 0 | 24.448 | 14179.84 | SM | 580 | 24.448 | 14179.84 | 0% | 0 | 0% | 0 | 0
| REPB14020 | ROOF | D | Moss: Carefully remove moss/lichen growth on roof covering of any kind and dispose of debris off site, reistate all disturbed surfaces, replace broken tiles, slates and the like, thoroughly clean out valleys, gutters, downpipes, hoppers etc, prepare and treat the complete roof area with a diluted fungicide solution AKZO or other equal and approved applied strictly in accordance with the manufacturer’s instructions, thoroughly clean out all gutters and the like to remove all chemical residue arising upon completion of the works, and remove waste and debris. |  |  | 3.18 |  | 2115AA | SM | 580 | 10.17 | 5898.6 | #VALUE! | #VALUE! | 0 | 8.136 | 4718.88 | SM | 580 | 8.136 | 4718.88 | 0% | 0 | 0% | 0 | 0
| REPB14020 | WINDOWS | H | [23 empty] | 0
| REPB14020 | WINDOWS | D | Double Glazed Unit: Reglaze unit upto 1.00sm, hermatically sealed with 4mm obscure low emissity (Low E) glass flush edge unit, including remove beads etc. hack out glass and glaze new unit to wood, metal or PVCu frames. |  |  | 4.184 |  | 5501AC | NO | 2 | 81.08 | 162.16 | #VALUE! | #VALUE! | 0 | 66.5991 | 133.1982 | NO | 2 | 66.5991 | 133.1982 | 0% | 0 | 0% | 0 | 0
| REPB14020 | WINDOWS | D | PROVISIONAL SUM: Windows Pvcu: Washdown windows at rear and flank elevations (No 175). |  |  | 4.293 |  | PROV SUM | SUM | 1 | 1500 | 1500 | #VALUE! | 1500 |  |  | 1500 | SUM | 1 |  | 1500 | 0% | 0 | 0% | 0 | 0
| REPB14020 | SCAFFOLD | H | [23 empty] | 0
| REPB14020 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 8850 | 12.92 | 114342 | #VALUE! | #VALUE! | 0 | 16.4084 | 145214.34 | M2 | 4425 | 16.4084 | 72607.17 | 70% | 50825.019 | 0% | 0 | 50825.019
| REPB14020 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 80% | 426.72 | 0% | 0 | 426.72
| REPB14020 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 3 | 50 | 150 | #VALUE! | #VALUE! | 0 | 63.5 | 190.5 | unit | 3 | 63.5 | 190.5 | 80% | 152.4 | 0% | 0 | 152.4
| REPB14020 | SCAFFOLD | D | Satellite Dish, reposition |  |  | 2.22 |  | SC022 | Nr | 14 | 82.5 | 1155 | #VALUE! | #VALUE! | 0 | 104.775 | 1466.85 | Nr | 14 | 104.775 | 1466.85 | 100% | 1466.85 | 0% | 0 | 1466.85
| REPB14020 | SCAFFOLD | D | supply cherry picker per day incl delivery and driver |  |  | 2.3 |  | SC030 |  | 1 | 695 | 695 | #VALUE! | #VALUE! | 0 | 882.65 | 882.65 |  | 1 | 882.65 | 882.65 | 0% | 0 | 0% | 0 | 0
| REPB14020 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB14020 | ESTATE WORKS | H | [23 empty] | 0
| REPB14020 | ESTATE WORKS | D | Wall: Rake out existing joints of brickwork min 12mm and repoint brickwork in mortar to match existing and remove waste and debris. |  |  | 7.253 |  | 1021AA | SM | 2 | 20.13 | 40.26 | #VALUE! | #VALUE! | 0 | 14.5942 | 29.1885 | SM | 2 | 14.5942 | 29.1885 | 0% | 0 | 0% | 0 | 0
| REPB14020 | ESTATE WORKS | D | PROVISIONAL SUM: Renew gates to external sheds (NO 35). |  |  | 7.316 |  | PROV SUM | SUM | 1 | 1800 | 1800 | #VALUE! | 1800 |  |  | 1800 | SUM | 1 |  | 1800 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 181652.9707 |  |  | TOTAL | 109045.8007 |  | 52870.989 |  | 0 | 52870.989

## 1-10 Lissenden Mansions
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
1-10 Lissenden Mansions
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB04223 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB04223 | ASBESTOS | H
| REPB04223 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 2 | 234 | 468 | #VALUE! | #VALUE! | 0 | 222.3 | 444.6 | Item | 2 | 222.3 | 444.6 | 0% | 0 | 0% | 0 | 0
| REPB04223 | COMMUNAL WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0
| REPB04223 | COMMUNAL WORKS | D | PROVISIONAL SUM: Replace or install post boxes with new vandal-resistant lockable post boxes. |  |  | 5.386 |  | PROV SUM | SUM | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | SUM | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB04223 | COMMUNAL WORKS | D | PROVISIONAL SUM: Secure storage area for bicycles (bike stands). |  |  | 5.387 |  | PROV SUM | SUM | 1 | 500 | 500 | #VALUE! | 500 |  |  | 500 | SUM | 1 |  | 500 | 0% | 0 | 0% | 0 | 0
| REPB04223 | EXTREP | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB04223 | EXTREP | D | Fracture: Remove any applied finish and cut out bricks as necessary to either side of fracture, one face only, stitch in new bricks, bed and point to match existing in cement lime mortar (1:1:6), and make good any applied finishes, and remove waste and debris (measured over mean general line of fracture). |  |  | 6.82 |  | 1019AA | LM | 3 | 44.12 | 132.36 | #VALUE! | #VALUE! | 0 | 31.987 | 95.961 | LM | 3 | 31.987 | 95.961 | 0% | 0 | 0% | 0 | 0
| REPB04223 | EXTREP | D | Wall: Cut out bricks from face of wall, clean and clear away, lay upto 15 No. new facing bricks in cement lime mortar (1:1:6), bond, bed and point to match existing and remove waste and debris. |  |  | 6.85 |  | 1019BA | IT | 12 | 21.92 | 263.04 | #VALUE! | #VALUE! | 0 | 15.892 | 190.704 | IT | 12 | 15.892 | 190.704 | 0% | 0 | 0% | 0 | 0
| REPB04223 | EXTREP | D | Wall: Rake out existing joints of brickwork min 12mm and repoint brickwork in mortar to match existing and remove waste and debris. |  |  | 6.91 |  | 1021AA | SM | 16 | 20.13 | 322.08 | #VALUE! | #VALUE! | 0 | 14.5942 | 233.508 | SM | 16 | 14.5942 | 233.508 | 0% | 0 | 0% | 0 | 0
| REPB04223 | EXTREP | D | Cill: Hack off defective area of concrete cill clean and treat any exposed reinforcement, drill into cill and insert 6mm diameter reinforcing bars at 150mm centres, apply bonding agent and reform cill with fine concrete to match existing profiles including all necessary formwork, make good to structure and all finishes and fillets and remove waste and debris. |  |  | 6.116 |  | 1031BA | NO | 12 | 38.74 | 464.88 | #VALUE! | #VALUE! | 0 | 28.0865 | 337.038 | NO | 12 | 28.0865 | 337.038 | 0% | 0 | 0% | 0 | 0
| REPB04223 | EXTREP | D | Walls: Wash down, fill in cracks and holes, sand down and apply one coat of stabilising solution and two coats of smooth or textured masonry paint to brickwork surfaces of walls. |  |  | 6.186 |  | 4356BD | SM | 315 | 11.63 | 3663.45 | #VALUE! | #VALUE! | 0 | 9.8855 | 3113.9325 | SM | 315 | 9.8855 | 3113.9325 | 0% | 0 | 0% | 0 | 0
| REPB04223 | EXTREP | D | Soffit: Wash down, fill in cracks and holes, sand smooth and apply one coat of sealer and two coats of smooth or textured masonry paint to rendered or concrete soffits. |  |  | 6.188 |  | 4356CB | SM | 12 | 9.82 | 117.84 | #VALUE! | #VALUE! | 0 | 8.347 | 100.164 | SM | 12 | 8.347 | 100.164 | 0% | 0 | 0% | 0 | 0
| REPB04223 | EXTREP | D | Balustrading: Wire brush, prepare for and apply one undercoat, one coat of gloss paint on existing painted surfaces of ornamental metal balustrading, railings or gates (measured both sides). |  |  | 6.225 |  | 4364DA | SM | 12 | 11.66 | 139.92 | #VALUE! | #VALUE! | 0 | 9.911 | 118.932 | SM | 12 | 9.911 | 118.932 | 0% | 0 | 0% | 0 | 0
| REPB04223 | EXTREP | D | Window:Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on surfaces of wooden windowsl (one side and edges). |  |  | 6.236 |  | 4380BA | SM | 177 | 25.87 | 4578.99 | #VALUE! | #VALUE! | 0 | 21.9895 | 3892.1415 | SM | 177 | 21.9895 | 3892.1415 | 0% | 0 | 0% | 0 | 0
| REPB04223 | EXTREP | D | Frame:Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on timber frame ne 300mm girth. |  |  | 6.237 |  | 4380CA | LM | 50 | 6.28 | 314 | #VALUE! | #VALUE! | 0 | 5.338 | 266.9 | LM | 50 | 5.338 | 266.9 | 0% | 0 | 0% | 0 | 0
| REPB04223 | EXTREP | D | Door:Rub down, prepare for and apply one coat of primer, one undercoat and two coats of gloss paint to all surfaces of any size or type of single glazed timber door. (one sides and edges). |  |  | 6.238 |  | 4380DA | IT | 9 | 20.71 | 186.39 | #VALUE! | #VALUE! | 0 | 17.6035 | 158.4315 | IT | 9 | 17.6035 | 158.4315 | 0% | 0 | 0% | 0 | 0
| REPB04223 | EXTREP | D | Gates: Rub down, prepare for, and apply one undercoat, two coats of gloss paint on existing painted surfaces of gates and posts (measured both sides). |  |  | 6.258 |  | 4381FA | SM | 2 | 12.41 | 24.82 | #VALUE! | #VALUE! | 0 | 10.5485 | 21.097 | SM | 2 | 10.5485 | 21.097 | 0% | 0 | 0% | 0 | 0
| REPB04223 | EXTREP | D | Fascias, soffits, Bargeboards and the like:Rub down, prepare for, and apply one undercoat, two coats of gloss paint on existing painted surfaces of facias, soffits, bargeboards and the like ne 300mm girth. |  |  | 6.26 |  | 4381HB | LM | 12 | 3.74 | 44.88 | #VALUE! | #VALUE! | 0 | 3.179 | 38.148 | LM | 12 | 3.179 | 38.148 | 0% | 0 | 0% | 0 | 0
| REPB04223 | EXTREP | D | PROVISIONAL SUM: S/F pull handle to side gates. |  |  | 6.399 |  | PROV SUM | SUM | 1 | 50 | 50 | #VALUE! | 50 |  |  | 50 | SUM | 1 |  | 50 | 0% | 0 | 0% | 0 | 0
| REPB04223 | ROOF | H | [19 empty] | 0% | 0 | 0% | 0 | 0
| REPB04223 | ROOF | D | PROV SUM: Overlay with BAUDER Bauderflex System or equivalent inclusive of 15 year guarantee. Voids 1m2 to be deducted Overlay existing mineral surfaced felt with 2 layer torch-on built up felt roofing (including preparation). Code RF154 Up to 200 m2* |  |  | 3.434 |  | PROV SUM | M2 | 250 | 52 | 13000 | #VALUE! | 13000 |  |  | 13000 | M2 | 250 |  | 13000 | 0% | 0 | 0% | 0 | 0
| REPB04223 | ROOF | D | PROV SUM: Supply & lay vapour barrier felt incl enveloping insulation board Up to 200 m2* Code RF171 |  |  | 3.435 |  | PROV SUM | M2 | 250 | 17 | 4250 | #VALUE! | 4250 |  |  | 4250 | M2 | 250 |  | 4250 | 0% | 0 | 0% | 0 | 0
| REPB04223 | ROOF | D | PROV SUM: Supply & lay 120mm thick PIR insulation bonded to vapour barrier (in line with current building regulations) Code RF175 Up to 200 m2* |  |  | 3.436 |  | PROV SUM | M2 | 250 | 32 | 8000 | #VALUE! | 8000 |  |  | 8000 | M2 | 250 |  | 8000 | 0% | 0 | 0% | 0 | 0
| REPB04223 | ROOF | D | PROV SUM: Prepare & clean existing Rainwater Outlet and dress to same Code RF181 |  |  | 3.437 |  | PROV SUM | Nr | 10 | 35 | 350 | #VALUE! | 350 |  |  | 350 | Nr | 10 |  | 350 | 0% | 0 | 0% | 0 | 0
| REPB04223 | ROOF | D | PROV SUM: Asphalt: Renew 20mm asphalt roof finish comprising isolating membrane, asphalt laid in two layers and bond to existing asphalt and finish smooth to match existing levels, and remove waste and debris. Code 2190AA |  |  | 3.438 |  | PROV SUM | SM | 25 | 85.24 | 2131 | #VALUE! | 2131 |  |  | 2131 | SM | 25 |  | 2131 | 0% | 0 | 0% | 0 | 0
| REPB04223 | ROOF | D | PROV SUM: Tile: Overhaul clay plain tile roof, refix loose tiles, renew broken or missing tiles to match existing, redress, rewedge and repoint all flashings, aprons, chimney gutters etc., cut out and make good cement weather fillets, repoint in cement mortar (1:3) to all hips, ridges and verges, make good, clear away debris. Code 2013EA |  |  | 3.439 |  | PROV SUM | SM | 30 | 30.56 | 916.8 | #VALUE! | 916.8 |  |  | 916.8 | SM | 30 |  | 916.8 | 0% | 0 | 0% | 0 | 0
| REPB04223 | ROOF | D | PROV SUM: Roof Covering: Extra over any renewal or refixing of plain concrete roof tiles for renew roofing felt and battens. Code 2013RR |  |  | 3.44 |  | PROV SUM | SM | 10 | 21.88 | 218.8 | #VALUE! | 218.8 |  |  | 218.8 | SM | 10 |  | 218.8 | 0% | 0 | 0% | 0 | 0
| REPB04223 | ROOF | D | PROV SUM: Slate: Renew any size natural slates to roof fixed with clips or copper nails including double courses at eaves, verges cuttings, all labours renewing roofing felt and battens, and remove waste and debris. Code 2033AA |  |  | 3.441 |  | PROV SUM | SM | 6 | 119.76 | 718.56 | #VALUE! | 718.56 |  |  | 718.56 | SM | 6 |  | 718.56 | 0% | 0 | 0% | 0 | 0
| REPB04223 | WINDOWS | H | [19 empty] | 0% | 0 | 0% | 0
| REPB04223 | WINDOWS | D | Soft wood timber splice with resin; face splice repair method no. 5. Remove old and loose paint as necessary. Cut out decayed timber from windows and frames, piecing in or frame in new wrought softwood with resin to match existing. Leave ready to decorate. Splice not exc 500 to 1000mm |  |  | 4.11 |  | WIND017 | Nr | 22 | 36.75 | 808.5 | #VALUE! | #VALUE! | 0 | 34.9125 | 768.075 | Nr | 22 | 34.9125 | 768.075 | 0% | 0 | 0% | 0 | 0
| REPB04223 | WINDOWS | D | 7. Timber repair system; using window care dry fix/dry flex RP; Conservation Joint; Up to 50mm |  |  | 4.13 |  | WIND022 | Nr | 170 | 4.25 | 722.5 | #VALUE! | #VALUE! | 0 | 4.0375 | 686.375 | Nr | 170 | 4.0375 | 686.375 | 0% | 0 | 0% | 0
| REPB04223 | WINDOWS | D | 7. Timber repair system; using window care dry fix/dry flex RP; Conservation Joint; up to 100mm |  |  | 4.14 |  | WIND023 | Nr | 28 | 6.75 | 189 | #VALUE! | #VALUE! | 0 | 6.4125 | 179.55 | Nr | 28 | 6.4125 | 179.55 | 0% | 0 | 0% | 0
| REPB04223 | WINDOWS | D | Window: Overhaul timber sash window, renew staff and parting beads, take out sashes and later rehang on appropriate sized new undyed plaited nylon sash cords, renew pocket pieces, wedge and cramp loose sash frames, oil pulleys, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.9 |  | 3150CA | NO | 19 | 35.61 | 676.59 | #VALUE! | #VALUE! | 0 | 31.5683 | 599.797 | NO | 19 | 31.5683 | 599.797 | 0% | 0 | 0% | 0
| REPB04223 | SCAFFOLD | H | [18 empty] | 0 | 0% | 0 | 0% | 0
| REPB04223 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 1124 | 12.92 | 14522.08 | #VALUE! | #VALUE! | 0 | 16.4084 | 18443.0416 | M2 | 1124 | 16.4084 | 18443.0416 | 0% | 0 | 0% | 0
| REPB04223 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 0% | 0 | 0% | 0
| REPB04223 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 3 | 50 | 150 | #VALUE! | #VALUE! | 0 | 63.5 | 190.5 | unit | 3 | 63.5 | 190.5 | 0% | 0 | 0% | 0
| REPB04223 | SCAFFOLD | D | Installation of rubbish chute |  |  | 2.18 |  | SC018 | lm | 1 | 45 | 45 | #VALUE! | #VALUE! | 0 | 57.15 | 57.15 | lm | 1 | 57.15 | 57.15 | 0% | 0 | 0% | 0
| REPB04223 | SCAFFOLD | D | Erecting hoist mast- per unit- up to 5 storeys (including delivery, dismantle and gates) |  |  | 2.26 |  | SC026 | unit | 1 | 1127.5 | 1127.5 | #VALUE! | #VALUE! | 0 | 1431.925 | 1431.925 | unit | 1 | 1431.925 | 1431.925 | 0% | 0 | 0% | 0
| REPB04223 | SCAFFOLD | D | Parking bay suspensions per 2 bays fee. |  |  | 2.28 |  | SC028 | day | 120 | 77.26 | 9271.2 | #VALUE! | #VALUE! | 0 | 98.1202 | 11774.424 | day | 120 | 98.1202 | 11774.424 | 0% | 0 | 0% | 0
| REPB04223 | SCAFFOLD | D | Suspension of Parking Bays administration Fee |  |  | 2.29 |  | SC029 | item | 1 | 61.29 | 61.29 | #VALUE! | #VALUE! | 0 | 77.8383 | 77.8383 | item | 1 | 77.8383 | 77.8383 | 0% | 0 | 0% | 0
| REPB04223 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0
| REPB04223 | SCAFFOLD | D | Weekly hire (in event of programme extension in line with NEC opt A compensation event agreed). Hoist hire |  |  |  |  | SC027 | week |  |  | 1432 | #VALUE! | #VALUE! | #N/A | #N/A | 1432 | week |  | #N/A | 1432 | 0% | 0 | 0% | 0
[17 empty] | TOTAL | 75420.7934 |  |  | TOTAL | 75420.7934 |  | 0 |  | 0

## 25 Troyes House
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
25 Troyes House
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB11024 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB11024 | ENERGY EFFICIENY | H
| REPB11024 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! | 0 | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB11024 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0
| REPB11024 | ASBESTOS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB11024 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB11024 | COMMUNAL WORKS | H | [19 empty] | 0% | 0 | 0% | 0 | 0
| REPB11024 | EXTREP | H | [19 empty] | 0% | 0 | 0% | 0 | 0
| REPB11024 | EXTREP | D | Soffit:Wash down, fill in cracks and holes, sand smooth and apply two coats of smooth or textured masonry paint to rendered or concrete canopies or soffits. |  |  | 6.187 |  | 4356CA | SM | 20 | 8.58 | 171.6 | #VALUE! | #VALUE! | 0 | 7.293 | 145.86 | SM | 20 | 7.293 | 145.86 | 0% | 0 | 0% | 0 | 0
| REPB11024 | EXTREP | D | Balustrading:Wire brush, prepare for and apply one undercoat and two coats of gloss paint on existing painted surfaces ornamental metal balustrading, railings or gates (measured both sides). |  |  | 6.215 |  | 4363EA | SM | 160 | 16.08 | 2572.8 | #VALUE! | #VALUE! | 0 | 13.668 | 2186.88 | SM | 160 | 13.668 | 2186.88 | 0% | 0 | 0% | 0 | 0
| REPB11024 | EXTREP | D | PROVISIONAL SUM: Unidentified concrete repairs |  |  | 6.399 |  | PROV SUM | SUM | 1 | 1000 | 1000 | #VALUE! | 1000 |  |  | 1000 | SUM | 1 |  | 1000 | 0% | 0 | 0% | 0 | 0
| REPB11024 | ROOF | H | [19 empty] | 0% | 0 | 0% | 0 | 0
| REPB11024 | ROOF | D | PROVISIONAL SUM: Overlay with BAUDER Bauderflex System or equivalent |  |  | 3.434 |  | PROV SUM | M2 | 1 | 41600 | 41600 | #VALUE! | 41600 |  | 0 | 41600 | M2 | 1 | 0 | 41600 | 0% | 0 | 0% | 0 | 0
| REPB11024 | ROOF | D | PROVISIONAL SUM: Supply & lay 120mm thick PIR insulation bonded to vapour barrier (in line with current building regulations) |  |  | 3.435 |  | PROV SUM | M2 | 1 | 25600 | 25600 | #VALUE! | 25600 |  |  | 25600 | M2 | 1 |  | 25600 | 0% | 0 | 0% | 0 | 0
| REPB11024 | WINDOWS | H | [19 empty] | 0% | 0 | 0% | 0 | 0
| REPB11024 | [21 empty] | 0% | 0 | 0% | 0 | 0
| REPB11024 | SCAFFOLD | H | [19 empty] | 0% | 0 | 0% | 0 | 0
| REPB11024 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 40 | 12.92 | 516.8 | #VALUE! | #VALUE! | 0 | 16.4084 | 656.336 | M2 | 750 | 16.4084 | 12306.3 | 70% | 8614.41 | 0% | 0 | 8614.41
| REPB11024 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 0% | 0 | 0% | 0 | 0
| REPB11024 | SCAFFOLD | D | Installation of rubbish chute |  |  | 2.18 |  | SC018 | lm | 1 | 45 | 45 | #VALUE! | #VALUE! | 0 | 57.15 | 57.15 | lm | 0 | 57.15 | 0 | 0% | 0 | 0% | 0 | 0
| REPB11024 | SCAFFOLD | D | Double handrail as edge protection to party walls on mid-terraced property |  |  | 2.21 |  | SC021 | lm | 150 | 16.25 | 2437.5 | #VALUE! | #VALUE! | 0 | 20.6375 | 3095.625 | lm | 0 | 20.6375 | 0 | 0% | 0 | 0% | 0 | 0
| REPB11024 | SCAFFOLD | D | Construction hoist tower- per storey |  |  | 2.25 |  | SC025 | storey | 1 | 185.64 | 185.64 | #VALUE! | #VALUE! | 0 | 235.7628 | 235.7628 | storey | 0 | 235.7628 | 0 | 0% | 0 | 0% | 0 | 0
| REPB11024 | SCAFFOLD | D | supply cherry picker per day incl delivery and driver |  |  | 2.3 |  | SC030 |  | 10 | 695 | 6950 | #VALUE! | #VALUE! | 0 | 882.65 | 8826.5 |  | 0 | 882.65 | 0 | 0% | 0 | 0% | 0 | 0
| REPB11024 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB11024 | SCAFFOLD | D | Weekly hire (in event of programme extension in line with NEC opt A compensation event agreed). Hoist hire |  |  |  |  | SC027 | week |  |  | 1432 | #VALUE! | #VALUE! | #N/A | #N/A | 1432 | week |  | #N/A | 1432 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 85991.8093 |  |  | TOTAL | 85426.7355 |  | 8614.41 |  | 0 | 8614.41

## 11-20 Lissenden Mansions
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
11-20 Lissenden Mansions
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB04224 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB04224 | ASBESTOS | H
| REPB04224 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 2 | 234 | 468 | #VALUE! | #VALUE! | 0 | 222.3 | 444.6 | Item | 2 | 222.3 | 444.6 | 0% | 0 | 0% | 0 | 0
| REPB04224 | COMMUNAL WORKS | H
REPB04224
| REPB04224 | EXTREP | H
| REPB04224 | EXTREP | D | Wall: Cut out bricks from face of wall, clean and clear away, lay upto 15 No. new facing bricks in cement lime mortar (1:1:6), bond, bed and point to match existing and remove waste and debris. |  |  | 6.85 |  | 1019BA | IT | 5 | 21.92 | 109.6 | #VALUE! | #VALUE! | 0 | 15.892 | 79.46 | IT | 5 | 15.892 | 79.46 | 0% | 0 | 0% | 0 | 0
| REPB04224 | EXTREP | D | Wall: Rake out existing joints of brickwork min 12mm and repoint brickwork in mortar to match existing and remove waste and debris. |  |  | 6.91 |  | 1021AA | SM | 8 | 20.13 | 161.04 | #VALUE! | #VALUE! | 0 | 14.5942 | 116.754 | SM | 8 | 14.5942 | 116.754 | 0% | 0 | 0% | 0 | 0
| REPB04224 | EXTREP | D | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris. |  |  | 6.116 |  | 1031BA | NO | 8 | 38.74 | 309.92 | #VALUE! | #VALUE! | 0 | 28.0865 | 224.692 | NO | 8 | 28.0865 | 224.692 | 0% | 0 | 0% | 0 | 0
| REPB04224 | EXTREP | D | Walls: Wash down, fill in cracks and holes, sand down and apply one coat of stabilising solution and two coats of smooth or textured masonry paint to brickwork surfaces of walls. |  |  | 6.186 |  | 4356BD | SM | 25 | 11.63 | 290.75 | #VALUE! | #VALUE! | 0 | 9.8855 | 247.1375 | SM | 25 | 9.8855 | 247.1375 | 0% | 0 | 0% | 0 | 0
| REPB04224 | EXTREP | D | Soffit: Wash down, fill in cracks and holes, sand smooth and apply one coat of sealer and two coats of smooth or textured masonry paint to rendered or concrete soffits. |  |  | 6.188 |  | 4356CB | SM | 40 | 9.82 | 392.8 | #VALUE! | #VALUE! | 0 | 8.347 | 333.88 | SM | 40 | 8.347 | 333.88 | 0% | 0 | 0% | 0 | 0
| REPB04224 | EXTREP | D | Balustrading: Wire brush, prepare for and apply one undercoat, one coat of gloss paint on existing painted surfaces of ornamental metal balustrading, railings or gates (measured both sides). |  |  | 6.225 |  | 4364DA | SM | 36 | 11.66 | 419.76 | #VALUE! | #VALUE! | 0 | 9.911 | 356.796 | SM | 36 | 9.911 | 356.796 | 0% | 0 | 0% | 0 | 0
| REPB04224 | EXTREP | D | Window: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on surfaces of wooden windowsl (one side and edges). |  |  | 6.236 |  | 4380BA | SM | 165 | 25.87 | 4268.55 | #VALUE! | #VALUE! | 0 | 21.9895 | 3628.2675 | SM | 165 | 21.9895 | 3628.2675 | 0% | 0 | 0% | 0 | 0
| REPB04224 | EXTREP | D | Frame: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on timber frame ne 300mm girth. |  |  | 6.237 |  | 4380CA | LM | 12 | 6.28 | 75.36 | #VALUE! | #VALUE! | 0 | 5.338 | 64.056 | LM | 12 | 5.338 | 64.056 | 0% | 0 | 0% | 0 | 0
| REPB04224 | EXTREP | D | Door: Rub down, prepare for and apply one coat of primer, one undercoat and two coats of gloss paint to all surfaces of any size or type of single glazed timber door. (one sides and edges). |  |  | 6.238 |  | 4380DA | IT | 1 | 20.71 | 20.71 | #VALUE! | #VALUE! | 0 | 17.6035 | 17.6035 | IT | 1 | 17.6035 | 17.6035 | 0% | 0 | 0% | 0 | 0
| REPB04224 | EXTREP | D | Gates: Rub down, prepare for, and apply one undercoat, two coats of gloss paint on existing painted surfaces of gates and posts (measured both sides). |  |  | 6.258 |  | 4381FA | SM | 2 | 12.41 | 24.82 | #VALUE! | #VALUE! | 0 | 10.5485 | 21.097 | SM | 2 | 10.5485 | 21.097 | 0% | 0 | 0% | 0 | 0
| REPB04224 | EXTREP | D | Fascias, soffits, Bargeboards and the like: Rub down, prepare for, and apply one undercoat, two coats of gloss paint on existing painted surfaces of facias, soffits, bargeboards and the like ne 300mm girth. |  |  | 6.26 |  | 4381HB | LM | 12 | 3.74 | 44.88 | #VALUE! | #VALUE! | 0 | 3.179 | 38.148 | LM | 12 | 3.179 | 38.148 | 0% | 0 | 0% | 0 | 0
| REPB04224 | ROOF | H | [19 empty] | 0% | 0 | 0% | 0 | 0
| REPB04224 | ROOF | D | Supply & lay 2 lay built up felt roofing to insulation board (to BR standards) Up to 100 m2* |  |  | 3.26 |  | RF178 | m2 | 210 | 34.5 | 7245 | #VALUE! | #VALUE! | 0 | 26.6685 | 5600.385 | m2 | 210 | 26.6685 | 5600.385 | 0% | 0 | 0% | 0 | 0
| REPB04224 | ROOF | D | Remove existing cable tray, lower to ground level and dispose. Supply and install new 0 - 150mm cable tray including cable ties. Including electrical work. |  |  | 3.42 |  | RF194 | l/m | 50 | 21 | 1050 | #VALUE! | #VALUE! | 0 | 16.233 | 811.65 | l/m | 50 | 16.233 | 811.65 | 0% | 0 | 0% | 0 | 0
| REPB04224 | ROOF | D | Asphalt: Renew 20mm asphalt lining to sole and sides of rainwater outlet opening through one brick wall including internal angle fillets, lead dressing into hopper head and any necessary expanded metal lathing reinforcement, and remove waste and debris. |  |  | 3.71 |  | 2190EA | SM | 10 | 149.09 | 1490.9 | #VALUE! | #VALUE! | 0 | 119.272 | 1192.72 | SM | 10 | 119.272 | 1192.72 | 0% | 0 | 0% | 0 | 0
| REPB04224 | ROOF | D | Asphalt: Prepare and apply solar reflective paint to asphalt roofing (per coat). |  |  | 3.72 |  | 2190FA | SM | 450 | 10.6 | 4770 | #VALUE! | #VALUE! | 0 | 8.48 | 3816 | SM | 450 | 8.48 | 3816 | 0% | 0 | 0% | 0 | 0
| REPB04224 | ROOF | D | Roof: Renew asphalt and boarding complete, strip off existing roof covering and boarding, clear away to tip, fix 19mm WBP plywood boarding to roof joist, including 50x50mm softwood noggins, tape joints lay one layer of vapour barrier, lay 100mm insulation board, lay isolating membrane, fix galvanised eml to and including tanalised softwood kerbs etc., lay 20mm asphalt in two equal layers dress over and form kerbs, upstands, downstands, drips, angles, dressing into outlets, around pipes etc., supply and fix new code 4 lead cover flashing to wall abutments, and remove waste and debris. |  |  | 3.75 |  | 2191AA | SM | 210 | 140.96 | 29601.6 | #VALUE! | #VALUE! | 0 | 112.768 | 23681.28 | SM | 210 | 112.768 | 23681.28 | 0% | 0 | 0% | 0 | 0
| REPB04224 | ROOF | D | Tile: Remove plain tiles and carefully stack, renew roofing felt and battens and refix tiles (exc 10 No. in one location) and cart away debris to tip. |  |  | 3.87 |  | 2013DA | SM | 90 | 108.19 | 9737.1 | #VALUE! | #VALUE! | 0 | 86.552 | 7789.68 | SM | 90 | 86.552 | 7789.68 | 0% | 0 | 0% | 0 | 0
| REPB04224 | ROOF | D | Tile: Overhaul clay plain tile roof, refix loose tiles, renew broken or missing tiles to match existing, redress, rewedge and repoint all flashings, aprons, chimney gutters etc., cut out and make good cement weather fillets, repoint in cement mortar (1:3) to all hips, ridges and verges, make good, clear away debris. |  |  | 3.88 |  | 2013EA | SM | 90 | 30.56 | 2750.4 | #VALUE! | #VALUE! | 0 | 24.448 | 2200.32 | SM | 90 | 24.448 | 2200.32 | 0% | 0 | 0% | 0 | 0
| REPB04224 | ROOF | D | Roof Covering: Extra over any renewal or refixing of plain concrete roof tiles for renew roofing felt and battens. |  |  | 3.89 |  | 2013RR | SM | 90 | 21.88 | 1969.2 | #VALUE! | #VALUE! | 0 | 17.504 | 1575.36 | SM | 90 | 17.504 | 1575.36 | 0% | 0 | 0% | 0 | 0
| REPB04224 | ROOF | D | Dormers: Renew lead covering to dormers including remove old lead, cut, fit and dress new covering including all nailing and caps, drips, welted edges, bossed ends and intersections and all labours and remove waste and debris. |  |  | 3.176 |  | 2310EC | SM | 25 | 156.5 | 3912.5 | #VALUE! | #VALUE! | 0 | 125.2 | 3130 | SM | 25 | 125.2 | 3130 | 0% | 0 | 0% | 0 | 0
| REPB04224 | ROOF | D | Canopy: Renew lead covering to canopies (measured on plan) including remove old lead, cut, fit and dress new covering including all nailing and caps, drips, welted edges, bossed ends and intersections, dressing to upstands and kerbs, clean out/reform grooves and wedge upstands with lead and repoint in mastic, cut and dress lead around rainwater outlets. |  |  | 3.179 |  | 2310GA | SM | 10 | 147.56 | 1475.6 | #VALUE! | #VALUE! | 0 | 118.048 | 1180.48 | SM | 10 | 118.048 | 1180.48 | 0% | 0 | 0% | 0 | 0
| REPB04224 | ROOF | D | Flat Roof Outlet: Clear out blocked flat roof outlet including rod if necessary, flush out and test and remove debris from site on completion, and remove waste and debris. |  |  | 3.362 |  | 6039AC | IT | 10 | 11.18 | 111.8 | #VALUE! | #VALUE! | 0 | 8.2855 | 82.855 | IT | 10 | 8.2855 | 82.855 | 0% | 0 | 0% | 0 | 0
| REPB04224 | ROOF | D | Gutter: Clean out debris from gutters to any type of property including flush out and test, rod downpipe including clean out gulley and remove debris from site on completion (per elevation). |  |  | 3.364 |  | 6039BA | IT | 30 | 20.13 | 603.9 | #VALUE! | #VALUE! | 0 | 14.9183 | 447.5503 | IT | 30 | 14.9183 | 447.5503 | 0% | 0 | 0% | 0 | 0
| REPB04224 | ROOF | D | Chimney: Rake out joints to brickwork to chimney stack, min 12mm, and repoint in cement lime mortar (1:1:6) to match existing and remove waste and debris. |  |  | 3.423 |  | 1200AO | SM | 30 | 22.29 | 668.7 | #VALUE! | #VALUE! | 0 | 16.1602 | 484.8075 | SM | 30 | 16.1602 | 484.8075 | 0% | 0 | 0% | 0 | 0
| REPB04224 | WINDOWS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB04224 | WINDOWS | D | Soft wood timber splice with resin; face splice repair method no. 5. Remove old and loose paint as necessary. Cut out decayed timber from windows and frames, piecing in or frame in new wrought softwood with resin to match existing. Leave ready to decorate. Splice not exc 500 to 1000mm |  |  | 4.11 |  | WIND017 | Nr | 16 | 36.75 | 588 | #VALUE! | #VALUE! | 0 | 34.9125 | 558.6 | Nr | 16 | 34.9125 | 558.6 | 0% | 0 | 0% | 0 | 0
| REPB04224 | WINDOWS | D | 7. Timber repair system; using window care dry fix/dry flex RP; Conservation Joint; Up to 50mm |  |  | 4.13 |  | WIND022 | Nr | 100 | 4.25 | 425 | #VALUE! | #VALUE! | 0 | 4.0375 | 403.75 | Nr | 100 | 4.0375 | 403.75 | 0% | 0 | 0% | 0 | 0
| REPB04224 | WINDOWS | D | 7. Timber repair system; using window care dry fix/dry flex RP; Conservation Joint; up to 100mm |  |  | 4.14 |  | WIND023 | Nr | 16 | 6.75 | 108 | #VALUE! | #VALUE! | 0 | 6.4125 | 102.6 | Nr | 16 | 6.4125 | 102.6 | 0% | 0 | 0% | 0 | 0
| REPB04224 | WINDOWS | D | Window: Overhaul timber sash window, renew staff and parting beads, take out sashes and later rehang on appropriate sized new undyed plaited nylon sash cords, renew pocket pieces, wedge and cramp loose sash frames, oil pulleys, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.9 |  | 3150CA | NO | 12 | 35.61 | 427.32 | #VALUE! | #VALUE! | 0 | 31.5683 | 378.8192 | NO | 12 | 31.5683 | 378.8192 | 0% | 0 | 0% | 0 | 0
| REPB04224 | SCAFFOLD | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB04224 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 750 | 12.92 | 9690 | #VALUE! | #VALUE! | 0 | 16.4084 | 12306.3 | M2 | 750 | 16.4084 | 12306.3 | 0% | 0 | 0% | 0 | 0
| REPB04224 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 0% | 0 | 0% | 0 | 0
| REPB04224 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 1 | 50 | 50 | #VALUE! | #VALUE! | 0 | 63.5 | 63.5 | unit | 1 | 63.5 | 63.5 | 0% | 0 | 0% | 0 | 0
| REPB04224 | SCAFFOLD | D | Installation of rubbish chute |  |  | 2.18 |  | SC018 | lm | 15 | 45 | 675 | #VALUE! | #VALUE! | 0 | 57.15 | 857.25 | lm | 15 | 57.15 | 857.25 | 0% | 0 | 0% | 0 | 0
| REPB04224 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  | 2.24 |  | SC024 | % | 16 | 0.05 | 0.77 | #VALUE! | #VALUE! | #N/A | #N/A | 0.77 | % | 16 | #N/A | 0.77 | 0% | 0 | 0% | 0 | 0
| REPB04224 | SCAFFOLD | D | Construction hoist tower- per storey |  |  | 2.25 |  | SC025 | storey | 5 | 185.64 | 928.2 | #VALUE! | #VALUE! | 0 | 235.7628 | 1178.814 | storey | 5 | 235.7628 | 1178.814 | 0% | 0 | 0% | 0 | 0
| REPB04224 | SCAFFOLD | D | Erecting hoist mast- per unit- up to 5 storeys (including delivery, dismantle and gates) |  |  | 2.26 |  | SC026 | unit | 1 | 1127.5 | 1127.5 | #VALUE! | #VALUE! | 0 | 1431.925 | 1431.925 | unit | 1 | 1431.925 | 1431.925 | 0% | 0 | 0% | 0 | 0
| REPB04224 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | 0.0483 | 0 | unit |  | 0.0483 |  | 0% | 0 | 0% | 0 | 0
| REPB04224 | SCAFFOLD | D | Weekly hire (in event of programme extension in line with NEC opt A compensation event agreed). Hoist hire |  |  |  |  | SC027 | week |  |  | 1432 | #VALUE! | #VALUE! | #N/A |  |  | week |  |  | 0 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 75381.3074 |  |  | TOTAL | 75381.3074 |  | 0 |  | 0 | 0

## 5 Gillies Street
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
5 Gillies Street
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB42150 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB42150 | ENERGY EFFICIENY | H
| REPB42150 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! |  | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB42150 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0 | 0
| REPB42150 | ASBESTOS | H | [18 empty] | 0
| REPB42150 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB42150 | COMMUNAL WORKS | H
REPB42150
| REPB42150 | EXTREP | H | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris.
| REPB42150 | EXTREP | D | Moulding Repairs 0-5no. per property Fosroc repair mortar or equivalent Insitu repairs using straight edge to form moulding repair. (Girth NE300mm Length NE300mm) |  |  | 6.11 |  | FAB071 | no | 1 | 79.14 | 79.14 | #VALUE! | #VALUE! | 0 | 63.312 | 63.312 | no | 1 | 63.312 | 63.312 | 0% | 0 | 0% | 0 | 0
| REPB42150 | EXTREP | D | Fracture: Remove any applied finish and cut out bricks as necessary to either side of fracture, one face only, stitch in new bricks, bed and point to match existing in cement lime mortar (1:1:6), and make good any applied finishes, and remove waste and debris (measured over mean general line of fracture). |  |  | 6.82 |  | 1019AA | LM | 8 | 44.12 | 352.96 | #VALUE! | #VALUE! | 0 | 31.987 | 255.896 | LM | 8 | 31.987 | 255.896 | 0% | 0 | 0% | 0 | 0
| REPB42150 | EXTREP | D | Cills:Prepare, clean off all dust and debris, fill in or resurface cracks or spalled surfaces of concrete with epoxy mortar in surfaces of cills, not exceeding 300mm girth, repair over 5 and ne 10mm deep, and remove waste and debris. |  |  | 6.161 |  | 1460AF | LM | 10 | 38.25 | 382.5 | #VALUE! | #VALUE! | 0 | 27.7312 | 277.3125 | LM | 10 | 27.7312 | 277.3125 | 0% | 0 | 0% | 0 | 0
| REPB42150 | EXTREP | D | Walls:Wash down, fill in cracks and holes, sand down and apply one coat of stabilising solution and two coats of smooth or textured masonry paint to rendered or concrete walls. |  |  | 6.185 |  | 4356BC | SM | 35 | 11.01 | 385.35 | #VALUE! | #VALUE! | 0 | 9.3585 | 327.5475 | SM | 35 | 9.3585 | 327.5475 | 0% | 0 | 0% | 0 | 0
| REPB42150 | EXTREP | D | Window:Rub down, prepare and apply one undercoat and one coat of gloss paint on existing painted surfaces of wooden windows (one side and edges). |  |  | 6.262 |  | 4381JB | SM | 10 | 16.86 | 168.6 | #VALUE! | #VALUE! | 0 | 14.331 | 143.31 | SM | 10 | 14.331 | 143.31 | 0% | 0 | 0% | 0 | 0
| REPB42150 | EXTREP | D | Gates:Rub down, prepare for, and apply one undercoat, one coat of gloss paint on existing painted surfaces of gates and posts (measured both sides). |  |  | 6.271 |  | 4381NA | SM | 1 | 8.17 | 8.17 | #VALUE! | #VALUE! | 0 | 6.9445 | 6.9445 | SM | 1 | 6.9445 | 6.9445 | 0% | 0 | 0% | 0 | 0
| REPB42150 | EXTREP | D | Door:Rub down, prepare for, and apply three coats decorative wood stain on external surfaces of any size/type of single door(both sides and edges) |  |  | 6.276 |  | 4382DB | IT | 1 | 33.52 | 33.52 | #VALUE! | #VALUE! | 0 | 28.492 | 28.492 | IT | 1 | 28.492 | 28.492 | 0% | 0 | 0% | 0 | 0
| REPB42150 | EXTREP | D | Render Repairs:Repair crack in any external render including carefully hack out and make good with cement and sand including applying finish to match existing, and remove waste and debris. |  |  | 6.306 |  | 4230ZA | LM | 35 | 6.87 | 240.45 | #VALUE! | #VALUE! | 0 | 4.9807 | 174.3262 | LM | 35 | 4.9807 | 174.3262 | 0% | 0 | 0% | 0 | 0
| REPB42150 | EXTREP | D | PROVISIONAL SUM: Allow provisional sum for window cills. |  |  | 6.399 |  | PROV SUM | SUM | 1 | 300 | 300 | #VALUE! | 300 |  |  | 300 | SUM | 1 |  | 300 | 0% | 0 | 0% | 0 | 0
| REPB42150 | ROOF | H | [19 empty] | 0% | 0 | 0% | 0 | 0
| REPB42150 | ROOF | D | Moss:Carefully remove moss/lichen growth on roof covering of any kind and dispose of debris off site, reistate all disturbed surfaces, replace broken tiles, slates and the like, thoroughly clean out valleys, gutters, downpipes, hoppers etc, prepare and treat the complete roof area with a diluted fungicide solution AKZO or other equal and approved applied strictly in accordance with the manufacturer’s instructions, thoroughly clean out all gutters and the like to remove all chemical residue arising upon completion of the works, and remove waste and debris. |  |  | 3.18 |  | 2115AA | SM | 50 | 10.17 | 508.5 | #VALUE! | #VALUE! | 0 | 8.136 | 406.8 | SM | 50 | 8.136 | 406.8 | 0% | 0 | 0% | 0 | 0
| REPB42150 | ROOF | D | Gutter:Clean out gutter, rake out and apply sealant to joints and prepare and apply two coats of proprietary waterproof sealing compound to inside surfaces of finlock gutter, and remove waste and debris. |  |  | 3.186 |  | 2150EA | LM | 10 | 17.43 | 174.3 | #VALUE! | #VALUE! | 0 | 13.944 | 139.44 | LM | 10 | 13.944 | 139.44 | 0% | 0 | 0% | 0 | 0
| REPB42150 | ROOF | D | Gutter:Take down any PVCu gutter outlet and refix and remake joints. |  |  | 3.33 |  | 6031CG | NO | 1 | 6.76 | 6.76 | #VALUE! | #VALUE! | 0 | 5.0098 | 5.0098 | NO | 1 | 5.0098 | 5.0098 | 0% | 0 | 0% | 0 | 0
| REPB42150 | ROOF | D | PROVISIONAL SUM: Clear rainwater downpipes |  |  | 3.434 |  | PROV SUM | SUM | 1 | 150 | 150 | #VALUE! | 150 |  |  | 150 | SUM | 1 |  | 150 | 0% | 0 | 0% | 0 | 0
| REPB42150 | ROOF | D | PROVISIONAL SUM: Gutter from left neighbouring property has not been properly joined together to property gutter. |  |  | 3.435 |  | PROV SUM | SUM | 1 | 200 | 200 | #VALUE! | 200 |  |  | 200 | SUM | 1 |  | 200 | 0% | 0 | 0% | 0 | 0
| REPB42150 | WINDOWS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42150 | WINDOWS | D | 7. Timber repair system; using window care dry fix/dry flex RP; Conservation Joint; up to 100mm |  |  | 4.14 |  | WIND023 | Nr | 10 | 6.75 | 67.5 | #VALUE! | #VALUE! | 0 | 6.4125 | 64.125 | Nr | 10 | 6.4125 | 64.125 | 0% | 0 | 0% | 0 | 0
| REPB42150 | WINDOWS | D | Window: Overhaul timber casement window, dismantle as necessary and subsequently reassemble including freeing, easing and adjusting casements to give correct operation, renew sealing gaskets, renew fixing screws, remove, refit or renew ironmongery as necessary, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.89 |  | 3150BA | NO | 2 | 29.05 | 58.1 | #VALUE! | #VALUE! | 0 | 25.7528 | 51.5056 | NO | 2 | 25.7528 | 51.5056 | 0% | 0 | 0% | 0 | 0
| REPB42150 | WINDOWS | D | Window: Overhaul timber sash window, renew staff and parting beads, take out sashes and later rehang on appropriate sized new undyed plaited nylon sash cords, renew pocket pieces, wedge and cramp loose sash frames, oil pulleys, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.9 |  | 3150CA | NO | 9 | 35.61 | 320.49 | #VALUE! | #VALUE! | 0 | 31.5683 | 284.1144 | NO | 9 | 31.5683 | 284.1144 | 0% | 0 | 0% | 0 | 0
| REPB42150 | SCAFFOLD | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42150 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 90 | 12.92 | 1162.8 | #VALUE! | #VALUE! | 0 | 16.4084 | 1476.756 | M2 | 90 | 16.4084 | 1476.756 | 80% | 1181.4048 | 0% | 0 | 1181.4048
| REPB42150 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 80% | 426.72 | 0% | 0 | 426.72
| REPB42150 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 1 | 50 | 50 | #VALUE! | #VALUE! | 0 | 63.5 | 63.5 | unit | 1 | 63.5 | 63.5 | 80% | 50.8 | 0% | 0 | 50.8
| REPB42150 | SCAFFOLD | D | Scaffold taken through property (protection to surfaces included) |  |  | 2.16 |  | SC016 | unit | 1 | 379.8 | 379.8 | #VALUE! | #VALUE! | 0 | 482.346 | 482.346 | unit | 1 | 482.346 | 482.346 | 80% | 385.8768 | 0% | 0 | 385.8768
| REPB42150 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB42150 | ESTATE WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42150 | ESTATE WORKS | D | Fencing:Renew or provide new 1.65m tanalised timber vertical board fencing including for taking down remnants of existing fence and posts set in concrete, remove from site to approved tip, and set 125x125mm x 2.65m long softwood posts in concrete at ne 1.80m centres with three 69x44mm softwood rails bolted to posts and 144x20mm vertical boards nailed to rails, softwood gravel board with centre prop (measured per metre run of fencing). |  |  | 7.79 |  | 0171AD | LM | 7 | 93.18 | 652.26 | #VALUE! | #VALUE! | 0 | 76.5008 | 535.5055 | LM | 7 | 76.5008 | 535.5055 | 0% | 0 | 0% | 0 | 0
| REPB42150 | ESTATE WORKS | D | Gate Post and Gate:Renew or repair any single fitting to post or timber or metal gate including any gate hinge, gudgeon, band, pivot plate or pivot socket, spring, any post or gate catch or bolt, remove waste and debris (measured per complete fitting). |  |  | 7.186 |  | 0250FA | NO | 1 | 12.05 | 12.05 | #VALUE! | #VALUE! | 0 | 9.8931 | 9.8931 | NO | 1 | 9.8931 | 9.8931 | 0% | 0 | 0% | 0 | 0
| REPB42150 | ESTATE WORKS | D | PROVISIONAL SUM: Paving: Rake out cracked sections of existing floor concrete , fill in cracks and make good structure . SM 20 |  |  | 7.316 |  | PROV SUM | SUM | 1 | 400 | 400 | #VALUE! | 400 |  |  | 400 | SUM | 1 |  | 400 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 7001.8317 |  |  | TOTAL | 7001.8317 |  | 2044.8016 |  | 0 | 2044.8016

## 8 Dale Street
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
8 Dale Street
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB42122 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB42122 | ENERGY EFFICIENY | H
| REPB42122 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! | 0 | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB42122 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0 | 0
| REPB42122 | ASBESTOS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42122 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB42122 | COMMUNAL WORKS | H | [23 empty] | 0
| REPB42122 | [25 empty] | 0
| REPB42122 | EXTREP | H | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris. | [22 empty] | 0
| REPB42122 | EXTREP | D | Wall: Cut out bricks from face of wall, clean and clear away, lay upto 15 No. new common bricks in cement lime mortar (1:1:6), bond, bed and point to match existing and remove waste and debris. |  |  | 6.83 |  | 1019AB | IT | 3 | 18.93 | 56.79 | #VALUE! | #VALUE! | 0 | 13.7242 | 41.1728 | IT | 3 | 13.7242 | 41.1728 | 0% | 0 | 0% | 0 | 0
| REPB42122 | EXTREP | D | Wall: Rake out existing joints of brickwork min 12mm and repoint brickwork in mortar to match existing and remove waste and debris. |  |  | 6.91 |  | 1021AA | SM | 2 | 20.13 | 40.26 | #VALUE! | #VALUE! | 0 | 14.5942 | 29.1885 | SM | 2 | 14.5942 | 29.1885 | 0% | 0 | 0% | 0 | 0
| REPB42122 | EXTREP | D | Walls: Wash down, fill in cracks and holes, sand down and apply one coat of stabilising solution and two coats of smooth or textured masonry paint to brickwork surfaces of walls. |  |  | 6.186 |  | 4356BD | SM | 8 | 11.63 | 93.04 | #VALUE! | #VALUE! | 0 | 9.8855 | 79.084 | SM | 8 | 9.8855 | 79.084 | 0% | 0 | 0% | 0 | 0
| REPB42122 | EXTREP | D | Window: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on surfaces of wooden windowsl (one side and edges). |  |  | 6.236 |  | 4380BA | SM | 20 | 25.87 | 517.4 | #VALUE! | #VALUE! | 0 | 21.9895 | 439.79 | SM | 20 | 21.9895 | 439.79 | 0% | 0 | 0% | 0 | 0
| REPB42122 | EXTREP | D | Frame: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on timber frame ne 300mm girth. |  |  | 6.237 |  | 4380CA | LM | 15 | 6.28 | 94.2 | #VALUE! | #VALUE! | 0 | 5.338 | 80.07 | LM | 15 | 5.338 | 80.07 | 0% | 0 | 0% | 0 | 0
| REPB42122 | EXTREP | D | Door: Rub down, prepare for and apply one coat of primer, one undercoat and two coats of gloss paint to all surfaces of any size or type of single glazed timber door. (one sides and edges). |  |  | 6.238 |  | 4380DA | IT | 2 | 20.71 | 41.42 | #VALUE! | #VALUE! | 0 | 17.6035 | 35.207 | IT | 2 | 17.6035 | 35.207 | 0% | 0 | 0% | 0 | 0
| REPB42122 | ROOF | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42122 | ROOF | D | Asphalt: Renew 20mm asphalt roof finish comprising isolating membrane, asphalt laid in two layers and bond to existing asphalt and finish smooth to match existing levels, and remove waste and debris. |  |  | 3.67 |  | 2190AA | SM | 6 | 85.24 | 511.44 | #VALUE! | #VALUE! | 0 | 68.192 | 409.152 | SM | 6 | 68.192 | 409.152 | 0% | 0 | 0% | 0 | 0
| REPB42122 | ROOF | D | Asphalt: Overhaul asphalt roofing to flat roof area, Including sweep and remove moss, algae and other debris, cut out blisters, cracks and make good in asphalt, prepare and apply two coats of solar reflective paint as necessary, rewedge and redress flashings, clear associated gutters and outlets, and remove waste and debris. |  |  | 3.74 |  | 2190GA | SM | 30 | 30.56 | 916.8 | #VALUE! | #VALUE! | 0 | 24.448 | 733.44 | SM | 30 | 24.448 | 733.44 | 0% | 0 | 0% | 0 | 0
| REPB42122 | ROOF | D | Moss: Carefully remove moss/lichen growth on roof covering of any kind and dispose of debris off site, reistate all disturbed surfaces, replace broken tiles, slates and the like, thoroughly clean out valleys, gutters, downpipes, hoppers etc, prepare and treat the complete roof area with a diluted fungicide solution AKZO or other equal and approved applied strictly in accordance with the manufacturer’s instructions, thoroughly clean out all gutters and the like to remove all chemical residue arising upon completion of the works, and remove waste and debris. |  |  | 3.18 |  | 2115AA | SM | 6 | 10.17 | 61.02 | #VALUE! | #VALUE! | 0 | 8.136 | 48.816 | SM | 6 | 8.136 | 48.816 | 0% | 0 | 0% | 0 | 0
| REPB42122 | ROOF | D | Secret Gutter: Clear debris and clean down large secret lead or copper gutter or valley, remove waste and debis |  |  | 3.189 |  | 2250CA | LM | 10 | 5.58 | 55.8 | #VALUE! | #VALUE! | 0 | 4.464 | 44.64 | LM | 10 | 4.464 | 44.64 | 0% | 0 | 0% | 0 | 0
| REPB42122 | WINDOWS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42122 | WINDOWS | D | Window: Overhaul timber casement window, dismantle as necessary and subsequently reassemble including freeing, easing and adjusting casements to give correct operation, renew sealing gaskets, renew fixing screws, remove, refit or renew ironmongery as necessary, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.89 |  | 3150BA | NO | 1 | 29.05 | 29.05 | #VALUE! | #VALUE! | 0 | 25.7528 | 25.7528 | NO | 1 | 25.7528 | 25.7528 | 0% | 0 | 0% | 0 | 0
| REPB42122 | WINDOWS | D | Window: Overhaul sash window, renew staff and parting beads, take out sashes and later rehang on spiral sash balances, renew pocket pieces, wedge and cramp loose sash frames, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.91 |  | 3150CB | NO | 8 | 98.99 | 791.92 | #VALUE! | #VALUE! | 0 | 87.7546 | 702.0371 | NO | 8 | 87.7546 | 702.0371 | 0% | 0 | 0% | 0 | 0
| REPB42122 | SCAFFOLD | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42122 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 140 | 12.92 | 1808.8 | #VALUE! | #VALUE! | 0 | 16.4084 | 2297.176 | M2 | 140 | 16.4084 | 2297.176 | 0% | 0 | 0% | 0 | 0
| REPB42122 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 1 | 50 | 50 | #VALUE! | #VALUE! | 0 | 63.5 | 63.5 | unit | 1 | 63.5 | 63.5 | 0% | 0 | 0% | 0 | 0
| REPB42122 | SCAFFOLD | D | Scaffold to chimney stack n.e. 3.00 girth, n.e. 2.00m high to gable, verge or edge |  |  | 2.7 |  | SC008 | unit | 1 | 383.72 | 383.72 | #VALUE! | #VALUE! | 0 | 487.3244 | 487.3244 | unit | 1 | 487.3244 | 487.3244 | 0% | 0 | 0% | 0 | 0
| REPB42122 | SCAFFOLD | D | Scaffold taken up&over the roof |  |  | 2.17 |  | SC017 | unit | 1 | 842 | 842 | #VALUE! | #VALUE! | 0 | 1069.34 | 1069.34 | unit | 1 | 1069.34 | 1069.34 | 0% | 0 | 0% | 0 | 0
| REPB42122 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB42122 | ESTATE WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42122 | ESTATE WORKS | D | Gates:Install tanalised softwood two leaved gate ne 2.5sm overall, each leaf comprising two 144x27mm ledges, six 144x20mm vertical boards at 175mm centres and one 144x27mm diagonal brace, including steel strap hinges and hangers fixed to and including precaste concrete posts, galvanised mild steel auto catch, prepare for and decorate, posts set in concrete including all excavation, concrete, backfill and remove waste and debris, reinstate paving, gardens and like as necessary. |  |  | 7.163 |  | 0210BC | NO | 1 | 259.88 | 259.88 | #VALUE! | #VALUE! | 0 | 213.3615 | 213.3615 | NO | 1 | 213.3615 | 213.3615 | 0% | 0 | 0% | 0 | 0
| REPB42122 | ESTATE WORKS | D | Wall: Supply and lay new common bricks in one and a half brick wall in cement lime mortar (1:1:6). |  |  | 7.199 |  | 1013AC | SM | 1 | 133.42 | 133.42 | #VALUE! | #VALUE! | 0 | 96.7295 | 96.7295 | SM | 1 | 96.7295 | 96.7295 | 0% | 0 | 0% | 0 | 0
| REPB42122 | FRA WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42122 | FRA WORKS | D | Door:Renew internal door with any size single half-hour fire check glazed door having 3.2mm luan, white Meranti or other approved plywood facing both sides and 9mm hardwood lipping on long edges, including remove existing door and hinges, remove and refit door stops as necessary, fit and hang new door on 1.50 pairs of 100mm steel butt hinges, make good or alter recesses on frame, door complete with all ironmongery, intumescent strips and smoke seals, glazed, redecorate to match existing and remove waste and debris. |  |  | 13 |  | 3300FC | Item | 2 | 222.2 | 444.4 | #VALUE! | #VALUE! | 0 | 196.9803 | 393.9606 | Item | 2 | 196.9803 | 393.9606 | 0% | 0 | 0% | 0 | 0
| REPB42122 | FRA WORKS | D | Fire Upgrading Coating:Remove all existing defective paint to plastered or rendered wall surfaces back to a solid edge, feather off and repair any defective areas with a high quality filler as necessary, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, wash down, rinse, clean off and apply one full coat of fire upgrading primer at a coverage rate of 10sm per litre, apply two full coats of fire upgrading finish at a coverage rate of 10sm per litre. |  |  | 27 |  | 4801AB | Item | 1 | 22.53 | 22.53 | #VALUE! | #VALUE! | 0 | 19.1505 | 19.1505 | Item | 1 | 19.1505 | 19.1505 | 0% | 0 | 0% | 0 | 0
| REPB42122 | FRA WORKS | D | Fire Upgrading Coating:Strip off existing multi layer paint coatings to existing plastered or rendered soffits with a proprietary paint stripper, scrape off or remove with a proprietary paint scraper, wash down,rinse, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, clean off and apply one full coat of primer at a coverage rate of 10sm per litre, apply one full coats of colourcoat complete with decorative flakes, and apply one full coat of gloss or satin lacquer finish at a coverage rate of 10sm per litre. |  |  | 41 |  | 4804AD | Item | 1 | 29.34 | 29.34 | #VALUE! | #VALUE! | 0 | 24.939 | 24.939 | Item | 1 | 24.939 | 24.939 | 0% | 0 | 0% | 0 | 0
| REPB42122 | FRA WORKS | D | Fire Alarm:Install L2 type fire alarm installation complete to BS5839:Part6 1995, control panel, circuits, call points, automatic detectors and sounders, builders work, make good, test, commission, and remove waste and debris. |  |  | 93 |  | 8711GA | Item | 1 | 550 | 550 | #VALUE! | #VALUE! | 0 | 440 | 440 | Item | 1 | 440 | 440 | 0% | 0 | 0% | 0 | 0
| REPB42122 | FRA WORKS | D | Intumescent Strip:Renew or supply and fix new 22x4mm intumescent strip, half hour application, with integral cold smoke seal and setting into groove in timber frame or door. |  |  | 104 |  | 3431AC | Item | 2 | 3.44 | 6.88 | #VALUE! | #VALUE! | 0 | 3.0496 | 6.0991 | Item | 2 | 3.0496 | 6.0991 | 0% | 0 | 0% | 0 | 0
| REPB42122 | FRA WORKS | D | Smoke Detector:Renew existing with mains operated optical smoke detector with rechargeable DC battery or condensor back up self contained type to BS 5446 kitemark certified with hush button, including back plate and all necessary connections to existing wiring, test and make good on completion, where interlinked detectors are replaced new detectors must be compatible with existing, and remove waste and debris. |  |  | 115 |  | 8720FA | Item | 2 | 70.11 | 140.22 | #VALUE! | #VALUE! | 0 | 56.088 | 112.176 | Item | 2 | 56.088 | 112.176 | 0% | 0 | 0% | 0 | 0
| REPB42122 | FRA WORKS | D | Partition:Supply and erect or renew stud partition comprising ne 50x100mm sole and head plate, noggins and studs fixed with nails or plugged and screwed to walls, and pack out and scribe, 12.5mm butt jointed plasterboard and 3mm plaster skim coat and all labours to both faces. |  |  | 180 |  | 3013AB | Item | 1 | 62.11 | 62.11 | #VALUE! | #VALUE! | 0 | 55.0605 | 55.0605 | Item | 1 | 55.0605 | 55.0605 | 0% | 0 | 0% | 0 | 0
| REPB42122 | FRA WORKS | D | Test:Carry out test of domestic installation to occupied property complete comprising continuity, insulation resistance, polarity, earth fault loop impedance and operation of residual current operated device, disconnect, repair and renew as necessary after removal of illegal wiring and components, and provide report and NICEIC/ECA test certificate to the Client’s Representative, and remove waste and debris. |  |  | 186 |  | 8950AA | Item | 1 | 86.88 | 86.88 | #VALUE! | #VALUE! | 0 | 69.504 | 69.504 | Item | 1 | 69.504 | 69.504 | 0% | 0 | 0% | 0 | 0
| REPB42122 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to the fire alarm system. |  |  | 190 |  | PROV SUM | Item | 1 | 1500 | 1500 | #VALUE! | 1500 |  |  | 1500 | Item | 1 |  | 1500 | 0% | 0 | 0% | 0 | 0
| REPB42122 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to clear waste and debris from fire escape routes. |  |  | 191 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB42122 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional fire stopping works |  |  | 192 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB42122 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional signage |  |  | 193 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  | 100 | 100 | Item | 1 | 100 | 100 | 0% | 0 | 0% | 0 | 0
| REPB42122 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional electrical works |  |  | 194 |  | PROV SUM | Item | 1 | 350 | 350 | #VALUE! | 350 |  | 350 | 350 | Item | 1 | 350 | 350 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 10788.9668 |  |  | TOTAL | 10788.9668 |  | 0 |  | 0 | 0

## 11 Gillies Street
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
11 Gillies Street
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB42154 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB42154 | ENERGY EFFICIENY | H
| REPB42154 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! | 0 | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB42154 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0 | 0
| REPB42154 | ASBESTOS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42154 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB42154 | ASBESTOS | D | PROVISIONAL SUM: Allow Provisional Sum for asbestos removal. |  |  | 1.47 |  | PROV SUM | SUM | 1 | 1000 | 1000 | #VALUE! | 1000 |  |  | 1000 | SUM | 1 |  | 1000 | 0% | 0 | 0% | 0 | 0
| REPB42154 | COMMUNAL WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42154 | COMMUNAL WORKS | D | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris. |  |  | 5.1 |  | 4540AC | IT | 1 | 480 | 480 | #VALUE! | #VALUE! | 0 | 408 | 408 | IT | 1 | 408 | 408 | 0% | 0 | 0% | 0 | 0
| REPB42154 | COMMUNAL WORKS | D | Skirting: Renew any size softwood plain, moulded or chamfered skirting plugged to brickwork, including all ends and angles and prepare for redecoration, and remove waste and debris. |  |  | 5.91 |  | 3810AA | LM | 2 | 14.7 | 29.4 | #VALUE! | #VALUE! | 0 | 13.0315 | 26.0631 | LM | 2 | 13.0315 | 26.0631 | 0% | 0 | 0% | 0 | 0
| REPB42154 | COMMUNAL WORKS | D | Carpet: Renew tight woven medium contract grade carpet to domestic areas, take up existing and dispose to tip, prepare sub-base, lay underlay secure all edges with gripper or proprietary adhesive tape, cut and fit around pipes, into alcoves, door openings and the like including all necessary door strips etc., and remove waste and debris. |  |  | 5.154 |  | 4328AC | SM | 6 | 16.28 | 97.68 | #VALUE! | #VALUE! | 0 | 13.7143 | 82.2856 | SM | 6 | 13.7143 | 82.2856 | 0% | 0 | 0% | 0 | 0
| REPB42154 | COMMUNAL WORKS | D | Wall: Hack off any thickness of render from walls, rake out and prepare brickwork or blockwork to receive rendering and remove waste and debris. |  |  | 5.173 |  | 4210AA | SM | 1 | 12.5 | 12.5 | #VALUE! | #VALUE! | 0 | 9.0625 | 9.0625 | SM | 1 | 9.0625 | 9.0625 | 0% | 0 | 0% | 0 | 0
| REPB42154 | EXTREP | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42154 | EXTREP | D | Wall: Rake out existing joints of brickwork min 12mm and repoint brickwork in mortar to match existing and remove waste and debris. |  |  | 6.91 |  | 1021AA | SM | 5 | 20.13 | 100.65 | #VALUE! | #VALUE! | 0 | 14.5942 | 72.9712 | SM | 5 | 14.5942 | 72.9712 | 0% | 0 | 0% | 0 | 0
| REPB42154 | EXTREP | D | Gates: Wire brush, prepare for and apply one undercoat and two coats of gloss paint to both sides of existing painted surface of any size/type single metal gate including all edges and all surfaces of posts. |  |  | 6.214 |  | 4363DA | IT | 1 | 16.98 | 16.98 | #VALUE! | #VALUE! | 0 | 14.433 | 14.433 | IT | 1 | 14.433 | 14.433 | 0% | 0 | 0% | 0 | 0
| REPB42154 | EXTREP | D | Window: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on surfaces of wooden windowsl (one side and edges). |  |  | 6.236 |  | 4380BA | SM | 28 | 25.87 | 724.36 | #VALUE! | #VALUE! | 0 | 21.9895 | 615.706 | SM | 28 | 21.9895 | 615.706 | 0% | 0 | 0% | 0 | 0
| REPB42154 | EXTREP | D | Frame: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on timber frame ne 300mm girth. |  |  | 6.237 |  | 4380CA | LM | 6 | 6.28 | 37.68 | #VALUE! | #VALUE! | 0 | 5.338 | 32.028 | LM | 6 | 5.338 | 32.028 | 0% | 0 | 0% | 0 | 0
| REPB42154 | EXTREP | D | Door: Rub down, prepare for and apply one coat of primer, one undercoat and two coats of gloss paint to all surfaces of any type or size of single timber door. (both sides and edges). |  |  | 6.241 |  | 4380DD | IT | 2 | 45.53 | 91.06 | #VALUE! | #VALUE! | 0 | 38.7005 | 77.401 | IT | 2 | 38.7005 | 77.401 | 0% | 0 | 0% | 0 | 0
| REPB42154 | ROOF | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42154 | ROOF | D | Fascia/Barge: Renew fascia or barge with preservative treated softwood, ne 300mm wide, fixed to roof timbers, apply preservative to cut ends, remove/refix rainwater goods and any cabling, adjust roof tiles and felt, renewal of any support battens and all mitred joints and prepare for redecoration. |  |  | 3.44 |  | 3030AA | LM | 10 | 21.94 | 219.4 | #VALUE! | #VALUE! | 0 | 19.4498 | 194.4981 | LM | 10 | 19.4498 | 194.4981 | 0% | 0 | 0% | 0 | 0
| REPB42154 | ROOF | D | Slate: Renew any size and type of fibre cement roof slates including double course at eaves cloaked verges, ridge, hips and valley tiles, supply and install proprietary ventilation units in roof, renew all code 6 lead flashings, aprons chimney gutters and the like wedged and pointed, renew valley gutter and valley board as necessary including all labours, cutting etc including renew roofing felt and battens, install ‘glidevale’ secret gutter to abutment to adjacent property, and remove waste and debris. |  |  | 3.218 |  | 2034AB | SM | 50 | 134.04 | 6702 | #VALUE! | #VALUE! | 0 | 107.232 | 5361.6 | SM | 50 | 107.232 | 5361.6 | 0% | 0 | 0% | 0 | 0
| REPB42154 | ROOF | D | Ridge: Renew half round ridge or hip tile fixed with galvanised steel clips and roofing screws with plastic washers including bedding in mastic as per manufacturers instructions, and remove waste and debris. |  |  | 3.221 |  | 2035AA | LM | 5 | 61.15 | 305.75 | #VALUE! | #VALUE! | 0 | 48.92 | 244.6 | LM | 5 | 48.92 | 244.6 | 0% | 0 | 0% | 0 | 0
| REPB42154 | ROOF | D | Gutter: Renew ne 112mm PVCu gutter outlet of any profile, including remaking joints and line and level, and remove waste and debris. |  |  | 3.326 |  | 6031CC | NO | 2 | 10.41 | 20.82 | #VALUE! | #VALUE! | 0 | 7.7149 | 15.4297 | NO | 2 | 7.7149 | 15.4297 | 0% | 0 | 0% | 0 | 0
| REPB42154 | WINDOWS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42154 | WINDOWS | D | Window: Renew window with purpose made softwood double hung cased box frame and sashes complete with 2 sashes, factory applied base stain or primer finish, compressible weatherstripping, glazing beads, ironmongery, remove existing and fix new into prepared opening, bed in mortar, point with sealant, double glazed and make good all finishes, decorate to match existing internally and prepare for redecoration externally, and remove waste and debris. |  |  | 4.28 |  | 3105AC | SM | 2 | 434.56 | 869.12 | #VALUE! | #VALUE! | 0 | 385.2374 | 770.4749 | SM | 2 | 385.2374 | 770.4749 | 0% | 0 | 0% | 0 | 0
| REPB42154 | WINDOWS | D | Window: Overhaul timber sash window, renew staff and parting beads, take out sashes and later rehang on appropriate sized new undyed plaited nylon sash cords, renew pocket pieces, wedge and cramp loose sash frames, oil pulleys, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.9 |  | 3150CA | NO | 9 | 35.61 | 320.49 | #VALUE! | #VALUE! | 0 | 31.5683 | 284.1144 | NO | 9 | 31.5683 | 284.1144 | 0% | 0 | 0% | 0 | 0
| REPB42154 | SCAFFOLD | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42154 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 151 | 12.92 | 1950.92 | #VALUE! | #VALUE! | 0 | 16.4084 | 2477.6684 | M2 | 151 | 16.4084 | 2477.6684 | 80% | 1982.1347 | 0% | 0 | 1982.1347
| REPB42154 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 80% | 426.72 | 0% | 0 | 426.72
| REPB42154 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 1 | 50 | 50 | #VALUE! | #VALUE! | 0 | 63.5 | 63.5 | unit | 1 | 63.5 | 63.5 | 80% | 50.8 | 0% | 0 | 50.8
| REPB42154 | SCAFFOLD | D | Scaffold taken through property (protection to surfaces included) |  |  | 2.16 |  | SC016 | unit | 1 | 379.8 | 379.8 | #VALUE! | #VALUE! | 0 | 482.346 | 482.346 | unit | 1 | 482.346 | 482.346 | 80% | 385.8768 | 0% | 0 | 385.8768
| REPB42154 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB42154 | ESTATE WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42154 | ESTATE WORKS | D | PROVISIONAL SUM: Allow for unforeseen estate works. |  |  | 7.316 |  | PROV SUM | SUM | 1 | 500 | 500 | #VALUE! | 500 |  |  | 500 | SUM | 1 |  | 500 | 0% | 0 | 0% | 0 | 0
| REPB42154 | FRA WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42154 | FRA WORKS | D | Door:Renew internal door with any size single half-hour fire check glazed door having 3.2mm luan, white Meranti or other approved plywood facing both sides and 9mm hardwood lipping on long edges, including remove existing door and hinges, remove and refit door stops as necessary, fit and hang new door on 1.50 pairs of 100mm steel butt hinges, make good or alter recesses on frame, door complete with all ironmongery, intumescent strips and smoke seals, glazed, redecorate to match existing and remove waste and debris. |  |  | 13 |  | 3300FC | Item | 2 | 222.2 | 444.4 | #VALUE! | #VALUE! | 0 | 196.9803 | 393.9606 | Item | 2 | 196.9803 | 393.9606 | 0% | 0 | 0% | 0 | 0
| REPB42154 | FRA WORKS | D | Fire Upgrading Coating:Remove all existing defective paint to plastered or rendered wall surfaces back to a solid edge, feather off and repair any defective areas with a high quality filler as necessary, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, wash down, rinse, clean off and apply one full coat of fire upgrading primer at a coverage rate of 10sm per litre, apply two full coats of fire upgrading finish at a coverage rate of 10sm per litre. |  |  | 27 |  | 4801AB | Item | 1 | 22.53 | 22.53 | #VALUE! | #VALUE! | 0 | 19.1505 | 19.1505 | Item | 1 | 19.1505 | 19.1505 | 0% | 0 | 0% | 0 | 0
| REPB42154 | FRA WORKS | D | Fire Upgrading Coating:Strip off existing multi layer paint coatings to existing plastered or rendered soffits with a proprietary paint stripper, scrape off or remove with a proprietary paint scraper, wash down,rinse, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, clean off and apply one full coat of primer at a coverage rate of 10sm per litre, apply one full coats of colourcoat complete with decorative flakes, and apply one full coat of gloss or satin lacquer finish at a coverage rate of 10sm per litre. |  |  | 41 |  | 4804AD | Item | 1 | 29.34 | 29.34 | #VALUE! | #VALUE! | 0 | 24.939 | 24.939 | Item | 1 | 24.939 | 24.939 | 0% | 0 | 0% | 0 | 0
| REPB42154 | FRA WORKS | D | Fire Alarm:Install L2 type fire alarm installation complete to BS5839:Part6 1995, control panel, circuits, call points, automatic detectors and sounders, builders work, make good, test, commission, and remove waste and debris. |  |  | 93 |  | 8711GA | Item | 1 | 550 | 550 | #VALUE! | #VALUE! | 0 | 440 | 440 | Item | 1 | 440 | 440 | 0% | 0 | 0% | 0 | 0
| REPB42154 | FRA WORKS | D | Intumescent Strip:Renew or supply and fix new 22x4mm intumescent strip, half hour application, with integral cold smoke seal and setting into groove in timber frame or door. |  |  | 104 |  | 3431AC | Item | 2 | 3.44 | 6.88 | #VALUE! | #VALUE! | 0 | 3.0496 | 6.0991 | Item | 2 | 3.0496 | 6.0991 | 0% | 0 | 0% | 0 | 0
| REPB42154 | FRA WORKS | D | Smoke Detector:Renew existing with mains operated optical smoke detector with rechargeable DC battery or condensor back up self contained type to BS 5446 kitemark certified with hush button, including back plate and all necessary connections to existing wiring, test and make good on completion, where interlinked detectors are replaced new detectors must be compatible with existing, and remove waste and debris. |  |  | 115 |  | 8720FA | Item | 2 | 70.11 | 140.22 | #VALUE! | #VALUE! | 0 | 56.088 | 112.176 | Item | 2 | 56.088 | 112.176 | 0% | 0 | 0% | 0 | 0
| REPB42154 | FRA WORKS | D | Closer:Renew or supply and fix Perko type concealed door closer screwed to door and frame, including remove and refix door or door stop as necessary. |  |  | 175 |  | 3905BA | Item | 2 | 9.81 | 19.62 | #VALUE! | #VALUE! | 0 | 8.6966 | 17.3931 | Item | 2 | 8.6966 | 17.3931 | 0% | 0 | 0% | 0 | 0
| REPB42154 | FRA WORKS | D | Partition:Supply and erect or renew stud partition comprising ne 50x100mm sole and head plate, noggins and studs fixed with nails or plugged and screwed to walls, and pack out and scribe, 12.5mm butt jointed plasterboard and 3mm plaster skim coat and all labours to both faces. |  |  | 180 |  | 3013AB | Item | 1 | 62.11 | 62.11 | #VALUE! | #VALUE! | 0 | 55.0605 | 55.0605 | Item | 1 | 55.0605 | 55.0605 | 0% | 0 | 0% | 0 | 0
| REPB42154 | FRA WORKS | D | Test:Carry out test of domestic installation to occupied property complete comprising continuity, insulation resistance, polarity, earth fault loop impedance and operation of residual current operated device, disconnect, repair and renew as necessary after removal of illegal wiring and components, and provide report and NICEIC/ECA test certificate to the Client’s Representative, and remove waste and debris. |  |  | 186 |  | 8950AA | Item | 1 | 86.88 | 86.88 | #VALUE! | #VALUE! | 0 | 69.504 | 69.504 | Item | 1 | 69.504 | 69.504 | 0% | 0 | 0% | 0 | 0
| REPB42154 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to the fire alarm system. |  |  | 190 |  | PROV SUM | Item | 1 | 1500 | 1500 | #VALUE! | 1500 |  | 1500 | 1500 | Item | 1 | 1500 | 1500 | 0% | 0 | 0% | 0 | 0
| REPB42154 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to clear waste and debris from fire escape routes. |  |  | 191 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  | 100 | 100 | Item | 1 | 100 | 100 | 0% | 0 | 0% | 0 | 0
| REPB42154 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional fire stopping works |  |  | 192 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  | 100 | 100 | Item | 1 | 100 | 100 | 0% | 0 | 0% | 0 | 0
| REPB42154 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional signage |  |  | 193 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  | 100 | 100 | Item | 1 | 100 | 100 | 0% | 0 | 0% | 0 | 0
| REPB42154 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional electrical works |  |  | 194 |  | PROV SUM | Item | 1 | 350 | 350 | #VALUE! | 350 |  | 350 | 350 | Item | 1 | 350 | 350 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 17176.1603 |  |  | TOTAL | 17176.1603 |  | 2845.5315 |  | 0 | 2845.5315

## 30 Grove Terrace
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
30 Grove Terrace
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB47495 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB47495 | ENERGY EFFICIENY | H
| REPB47495 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! | 0 | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB47495 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0 | 0
| REPB47495 | ASBESTOS | H | [23 empty] | 0
| REPB47495 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB47495 | COMMUNAL WORKS | H | [23 empty] | 0
| REPB47495 | COMMUNAL WORKS | D | Hall: Thoroughly clean down all wall and ceiling surfaces to common areas to remove dirt, grease and surface containments, scrape and remove all loose and defective coatings, prime bare areas with one coat of fire retardant primer and apply two coats of Class ‘O’ fire retardant matt paint, prepare and apply two coats of polyurethane lacquer or one undercoat and one gloss coat to all previously decorated timber surfaces to lobby, hall or corridor over 3.00sm ceiling area complete (classified as a single area). |  |  | 5.1 |  | 4540AC | IT | 1 | 480 | 480 | #VALUE! | #VALUE! | 0 | 408 | 408 | IT | 1 | 408 | 408 | 0% | 0 | 0% | 0 | 0
| REPB47495 | COMMUNAL WORKS | D | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris. |  |  | 5.386 |  | PROV SUM | SUM | 1 | 150 | 150 | #VALUE! | 150 |  |  | 150 | SUM | 1 |  | 150 | 0% | 0 | 0% | 0 | 0
| REPB47495 | COMMUNAL WORKS | D | PROVISIONAL SUM: Take up and renew linoleum floor covering. |  |  | 5.387 |  | PROV SUM | SUM | 1 | 700 | 700 | #VALUE! | 700 |  |  | 700 | SUM | 1 |  | 700 | 0% | 0 | 0% | 0 | 0
| REPB47495 | EXTREP | H | [23 empty] | 0
| REPB47495 | EXTREP | D | Moulding Repairs 0-5no. per property Fosroc repair mortar or equivalent Insitu repairs using straight edge to form moulding repair. (Girth NE300mm Length NE300mm) |  |  | 6.11 |  | FAB071 | no | 5 | 79.14 | 395.7 | #VALUE! | #VALUE! | 0 | 63.312 | 316.56 | no | 5 | 63.312 | 316.56 | 0% | 0 | 0% | 0 | 0
| REPB47495 | EXTREP | D | Fracture: Remove any applied finish and cut out bricks as necessary to either side of fracture, one face only, stitch in new bricks, bed and point to match existing in cement lime mortar (1:1:6), and make good any applied finishes, and remove waste and debris (measured over mean general line of fracture). |  |  | 6.82 |  | 1019AA | LM | 41 | 44.12 | 1808.92 | #VALUE! | #VALUE! | 0 | 31.987 | 1311.467 | LM | 41 | 31.987 | 1311.467 | 0% | 0 | 0% | 0 | 0
| REPB47495 | EXTREP | D | Cills: Prepare, clean off all dust and debris, fill in or resurface cracks or spalled surfaces of concrete with epoxy mortar in surfaces of cills, not exceeding 300mm girth, repair over 5 and ne 10mm deep, and remove waste and debris. |  |  | 6.161 |  | 1460AF | LM | 12 | 38.25 | 459 | #VALUE! | #VALUE! | 0 | 27.7312 | 332.775 | LM | 12 | 27.7312 | 332.775 | 0% | 0 | 0% | 0 | 0
| REPB47495 | EXTREP | D | Walls: Wash down, fill in cracks and holes, sand smooth and apply two coats of smooth finish masonry paint to rendered or concrete surfaces of walls. |  |  | 6.194 |  | 4360BA | SM | 33 | 7.02 | 231.66 | #VALUE! | #VALUE! | 0 | 5.967 | 196.911 | SM | 33 | 5.967 | 196.911 | 0% | 0 | 0% | 0 | 0
| REPB47495 | EXTREP | D | Balustrading: Wire brush, prepare for and apply one coat of primer, one undercoat, two coats of gloss paint on ornamental metal balustrading, railings or gates (measured both sides). |  |  | 6.204 |  | 4362EA | SM | 12 | 20.51 | 246.12 | #VALUE! | #VALUE! | 0 | 17.4335 | 209.202 | SM | 12 | 17.4335 | 209.202 | 0% | 0 | 0% | 0 | 0
| REPB47495 | EXTREP | D | Window: Rub down, prepare and apply one undercoat and one coat of gloss paint on existing painted surfaces of wooden windows (one side and edges). |  |  | 6.262 |  | 4381JB | SM | 34 | 16.86 | 573.24 | #VALUE! | #VALUE! | 0 | 14.331 | 487.254 | SM | 34 | 14.331 | 487.254 | 0% | 0 | 0% | 0 | 0
| REPB47495 | EXTREP | D | Door: Rub down, prepare for and apply one undercoat and one coat of gloss paint to all existing painted surfaces of any size or type of single glazed timber door (both sides and edges). |  |  | 6.265 |  | 4381LB | IT | 1 | 19.34 | 19.34 | #VALUE! | #VALUE! | 0 | 16.439 | 16.439 | IT | 1 | 16.439 | 16.439 | 0% | 0 | 0% | 0 | 0
| REPB47495 | EXTREP | D | PROVISIONAL SUM: Rear wall: Complete pebbledash rendering to lower section of wall SM 8. |  |  | 6.399 |  | PROV SUM | SUM | 1 | 400 | 400 | #VALUE! | 400 |  |  | 400 | SUM | 1 |  | 400 | 0% | 0 | 0% | 0 | 0
| REPB47495 | ROOF | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47495 | ROOF | D | Moss: Carefully remove moss/lichen growth on roof covering of any kind and dispose of debris off site, reistate all disturbed surfaces, replace broken tiles, slates and the like, thoroughly clean out valleys, gutters, downpipes, hoppers etc, prepare and treat the complete roof area with a diluted fungicide solution AKZO or other equal and approved applied strictly in accordance with the manufacturer’s instructions, thoroughly clean out all gutters and the like to remove all chemical residue arising upon completion of the works, and remove waste and debris. |  |  | 3.18 |  | 2115AA | SM | 55 | 10.17 | 559.35 | #VALUE! | #VALUE! | 0 | 8.136 | 447.48 | SM | 55 | 8.136 | 447.48 | 0% | 0 | 0% | 0 | 0
| REPB47495 | ROOF | D | Roofing: Apply sealing compound to cracks to roof or leadwork. |  |  | 3.182 |  | 2150AB | LM | 8 | 5.4 | 43.2 | #VALUE! | #VALUE! | 0 | 4.32 | 34.56 | LM | 8 | 4.32 | 34.56 | 0% | 0 | 0% | 0 | 0
| REPB47495 | ROOF | D | Slate: Overhaul fibre cement slate roof, refix loose slates, renew broken or missing slates to match existing, redress, rewedge and repoint all flashings, aprons, chimney gutters etc, cut out and make good cement weather fillets, repoint in cement mortar (1:3) to all hips, ridges and verges, make good, and remove waste and debris. |  |  | 3.207 |  | 2031CA | SM | 3 | 30.56 | 91.68 | #VALUE! | #VALUE! | 0 | 24.448 | 73.344 | SM | 3 | 24.448 | 73.344 | 0% | 0 | 0% | 0 | 0
| REPB47495 | ROOF | D | Downpipe: Take down any PVCu downpipe, remove and refix pipe brackets, plugged and screwed to brickwork and refix downpipes including all hopperheads offsets, shoes and remake all joints, make good to structure and finishes, and remove waste and debris. |  |  | 3.293 |  | 6011CA | LM | 24 | 13.68 | 328.32 | #VALUE! | #VALUE! | 0 | 10.1382 | 243.318 | LM | 24 | 10.1382 | 243.318 | 0% | 0 | 0% | 0 | 0
| REPB47495 | ROOF | D | Gutter: Take down any PVCu gutter, remove and refix brackets to fascia and refix gutter to brackets to line and level including all angles, outlets and stop ends and remake all joints. |  |  | 3.324 |  | 6031CA | LM | 12 | 7.33 | 87.96 | #VALUE! | #VALUE! | 0 | 5.4323 | 65.1872 | LM | 12 | 5.4323 | 65.1872 | 0% | 0 | 0% | 0 | 0
| REPB47495 | ROOF | D | PROVISIONAL SUM: Decorate soil pipe at rear elevation. |  |  | 3.434 |  | PROV SUM | SUM | 1 | 150 | 150 | #VALUE! | 150 |  |  | 150 | SUM | 1 |  | 150 | 0% | 0 | 0% | 0 | 0
| REPB47495 | WINDOWS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47495 | WINDOWS | D | 7. Timber repair system; using window care dry fix/dry flex RP; Conservation Joint; up to 100mm |  |  | 4.14 |  | WIND023 | Nr | 30 | 6.75 | 202.5 | #VALUE! | #VALUE! | 0 | 6.4125 | 192.375 | Nr | 30 | 6.4125 | 192.375 | 0% | 0 | 0% | 0 | 0
| REPB47495 | WINDOWS | D | Window: Overhaul timber casement window, dismantle as necessary and subsequently reassemble including freeing, easing and adjusting casements to give correct operation, renew sealing gaskets, renew fixing screws, remove, refit or renew ironmongery as necessary, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.89 |  | 3150BA | NO | 4 | 29.05 | 116.2 | #VALUE! | #VALUE! | 0 | 25.7528 | 103.0113 | NO | 4 | 25.7528 | 103.0113 | 0% | 0 | 0% | 0 | 0
| REPB47495 | WINDOWS | D | Window: Overhaul timber sash window, renew staff and parting beads, take out sashes and later rehang on appropriate sized new undyed plaited nylon sash cords, renew pocket pieces, wedge and cramp loose sash frames, oil pulleys, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.9 |  | 3150CA | NO | 26 | 35.61 | 925.86 | #VALUE! | #VALUE! | 0 | 31.5683 | 820.7749 | NO | 26 | 31.5683 | 820.7749 | 0% | 0 | 0% | 0 | 0
| REPB47495 | SCAFFOLD | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47495 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 256 | 12.92 | 3307.52 | #VALUE! | #VALUE! | 0 | 16.4084 | 4200.5504 | M2 | 256 | 16.4084 | 4200.5504 | 0% | 0 | 0% | 0 | 0
| REPB47495 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 0% | 0 | 0% | 0 | 0
| REPB47495 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 2 | 50 | 100 | #VALUE! | #VALUE! | 0 | 63.5 | 127 | unit | 2 | 63.5 | 127 | 0% | 0 | 0% | 0 | 0
| REPB47495 | SCAFFOLD | D | Scaffold taken through property (protection to surfaces included) |  |  | 2.16 |  | SC016 | unit | 1 | 379.8 | 379.8 | #VALUE! | #VALUE! | 0 | 482.346 | 482.346 | unit | 1 | 482.346 | 482.346 | 0% | 0 | 0% | 0 | 0
| REPB47495 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB47495 | ESTATE WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47495 | ESTATE WORKS | D | Fencing: Renew or provide new 1.65m tanalised timber vertical board fencing including for taking down remnants of existing fence and posts set in concrete, remove from site to approved tip, and set 125x125mm x 2.65m long softwood posts in concrete at ne 1.80m centres with three 69x44mm softwood rails bolted to posts and 144x20mm vertical boards nailed to rails, softwood gravel board with centre prop (measured per metre run of fencing). |  |  | 7.79 |  | 0171AD | LM | 7 | 93.18 | 652.26 | #VALUE! | #VALUE! | 0 | 76.5008 | 535.5055 | LM | 7 | 76.5008 | 535.5055 | 0% | 0 | 0% | 0 | 0
| REPB47495 | ESTATE WORKS | D | Fracture: Remove any applied finish and cut out bricks as necessary to either side of fracture, one face only, stitch in new bricks, bed and point to match existing in cement lime mortar (1:1:6), and make good any applied finishes, and remove waste and debris (measured over mean general line of fracture). |  |  | 7.244 |  | 1019AA | LM | 17 | 44.12 | 750.04 | #VALUE! | #VALUE! | 0 | 31.987 | 543.779 | LM | 17 | 31.987 | 543.779 | 0% | 0 | 0% | 0 | 0
| REPB47495 | ESTATE WORKS | D | PROVISIONAL SUM: Paving slab: Repair minor cracks and re-allign to attain even surfcace. SM 3. |  |  | 7.316 |  | PROV SUM | SUM | 1 | 300 | 300 | #VALUE! | 300 |  |  | 300 | SUM | 1 |  | 300 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 14003.5347 |  |  | TOTAL | 14003.5347 |  | 0 |  | 0 | 0

## 25 Elaine Grove
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
25 Elaine Grove
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB42129 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB42129 | ENERGY EFFICIENY | H
| REPB42129 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! | 0 | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB42129 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0 | 0
| REPB42129 | ASBESTOS | H | [23 empty] | 0
| REPB42129 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB42129 | COMMUNAL WORKS | H | [23 empty] | 0
| REPB42129 | [25 empty] | 0
| REPB42129 | EXTREP | H | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris. | [22 empty] | 0
| REPB42129 | EXTREP | D | Wall: Rake out existing joints of brickwork min 12mm and repoint brickwork in mortar to match existing and remove waste and debris. |  |  | 6.91 |  | 1021AA | SM | 6 | 20.13 | 120.78 | #VALUE! | #VALUE! | 0 | 14.5942 | 87.5655 | SM | 6 | 14.5942 | 87.5655 | 0% | 0 | 0% | 0 | 0
| REPB42129 | EXTREP | D | Coping: Take off precast coping ne 300mm wide, clean mortar from top of wall and coping, bed and point in cement lime mortar (1:1:6) with bonding agent and remove waste and debris. |  |  | 6.127 |  | 1033CA | LM | 12 | 6.04 | 72.48 | #VALUE! | #VALUE! | 0 | 4.379 | 52.548 | LM | 12 | 4.379 | 52.548 | 0% | 0 | 0% | 0 | 0
| REPB42129 | EXTREP | D | Walls: Wash down, fill in cracks and holes, sand smooth and apply two coats of smooth finish masonry paint to rendered or concrete surfaces of walls. |  |  | 6.194 |  | 4360BA | SM | 50 | 7.02 | 351 | #VALUE! | #VALUE! | 0 | 5.967 | 298.35 | SM | 50 | 5.967 | 298.35 | 0% | 0 | 0% | 0 | 0
| REPB42129 | EXTREP | D | Fascias, soffits, Bargeboards and the like: Rub down, prepare for, and apply one coat primer, one undercoat, two coats of gloss paint on surfaces of facias, soffits, bargeboards and the like ne 300mm girth. |  |  | 6.235 |  | 4380AB | LM | 28 | 5.28 | 147.84 | #VALUE! | #VALUE! | 0 | 4.488 | 125.664 | LM | 28 | 4.488 | 125.664 | 0% | 0 | 0% | 0 | 0
| REPB42129 | EXTREP | D | Window: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on surfaces of wooden windowsl (one side and edges). |  |  | 6.236 |  | 4380BA | SM | 19 | 25.87 | 491.53 | #VALUE! | #VALUE! | 0 | 21.9895 | 417.8005 | SM | 19 | 21.9895 | 417.8005 | 0% | 0 | 0% | 0 | 0
| REPB42129 | EXTREP | D | Frame: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on timber frame ne 300mm girth. |  |  | 6.237 |  | 4380CA | LM | 30 | 6.28 | 188.4 | #VALUE! | #VALUE! | 0 | 5.338 | 160.14 | LM | 30 | 5.338 | 160.14 | 0% | 0 | 0% | 0 | 0
| REPB42129 | EXTREP | D | Door: Rub down, prepare for and apply one coat of primer, one undercoat and two coats of gloss paint to all surfaces of any size or type of single glazed timber door. (one sides and edges). |  |  | 6.238 |  | 4380DA | IT | 5 | 20.71 | 103.55 | #VALUE! | #VALUE! | 0 | 17.6035 | 88.0175 | IT | 5 | 17.6035 | 88.0175 | 0% | 0 | 0% | 0 | 0
| REPB42129 | EXTREP | D | Wall: Apply 12mm cement and sand render (1:3) with waterproofing agent to external walls including ‘Rough Sandtex’ finish, dub out as necessary with cement and sand and all labours and remove waste and debris. |  |  | 6.305 |  | 4210AF | SM | 1 | 33.5 | 33.5 | #VALUE! | #VALUE! | 0 | 24.2875 | 24.2875 | SM | 1 | 24.2875 | 24.2875 | 0% | 0 | 0% | 0 | 0
| REPB42129 | ROOF | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42129 | ROOF | D | Slate: Renew any size and type of natural roof slates including double course at eaves cloaked verges, ridge, hips and valley tiles, supply and install proprietary ventilation units in roof, renew all code 6 lead flashings, aprons chimney gutters and the like wedged and pointed, renew valley gutter and valley board as necessary including all labours, cutting etc including renew roofing felt and battens and install restraint straps to gables and elevational gables, and remove waste and debris. |  |  | 3.219 |  | 2034AC | SM | 40 | 133.3 | 5332 | #VALUE! | #VALUE! | 0 | 106.64 | 4265.6 | SM | 40 | 106.64 | 4265.6 | 0% | 0 | 0% | 0 | 0
| REPB42129 | ROOF | D | Downpipe: Clear blockage from downpipe any 2 to 4 storey including gain access, rod, flush out and test including clean out gulley and remove debris from site on completion (not to be claimed with 6039BA). |  |  | 3.363 |  | 6039AD | IT | 2 | 20.13 | 40.26 | #VALUE! | #VALUE! | 0 | 14.9183 | 29.8367 | IT | 2 | 14.9183 | 29.8367 | 0% | 0 | 0% | 0 | 0
| REPB42129 | ROOF | D | Gutter: Clean out debris from gutters to any type of property including flush out and test, rod downpipe including clean out gulley and remove debris from site on completion (per elevation). |  |  | 3.364 |  | 6039BA | IT | 20 | 20.13 | 402.6 | #VALUE! | #VALUE! | 0 | 14.9183 | 298.3669 | IT | 20 | 14.9183 | 298.3669 | 0% | 0 | 0% | 0 | 0
| REPB42129 | WINDOWS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42129 | WINDOWS | D | Soft wood timber splice with resin; face splice repair method no. 5. Remove old and loose paint as necessary. Cut out decayed timber from windows and frames, piecing in or frame in new wrought softwood with resin to match existing. Leave ready to decorate. Splice not exc 500 to 1000mm |  |  | 4.11 |  | WIND017 | Nr | 5 | 36.75 | 183.75 | #VALUE! | #VALUE! | 0 | 34.9125 | 174.5625 | Nr | 5 | 34.9125 | 174.5625 | 0% | 0 | 0% | 0 | 0
| REPB42129 | WINDOWS | D | 7. Timber repair system; using window care dry fix/dry flex RP; Conservation Joint; Up to 50mm |  |  | 4.13 |  | WIND022 | Nr | 70 | 4.25 | 297.5 | #VALUE! | #VALUE! | 0 | 4.0375 | 282.625 | Nr | 70 | 4.0375 | 282.625 | 0% | 0 | 0% | 0 | 0
| REPB42129 | WINDOWS | D | 7. Timber repair system; using window care dry fix/dry flex RP; Conservation Joint; up to 100mm |  |  | 4.14 |  | WIND023 | Nr | 10 | 6.75 | 67.5 | #VALUE! | #VALUE! | 0 | 6.4125 | 64.125 | Nr | 10 | 6.4125 | 64.125 | 0% | 0 | 0% | 0 | 0
| REPB42129 | WINDOWS | D | Window: Overhaul timber sash window, renew staff and parting beads, take out sashes and later rehang on appropriate sized new undyed plaited nylon sash cords, renew pocket pieces, wedge and cramp loose sash frames, oil pulleys, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.9 |  | 3150CA | NO | 6 | 35.61 | 213.66 | #VALUE! | #VALUE! | 0 | 31.5683 | 189.4096 | NO | 6 | 31.5683 | 189.4096 | 0% | 0 | 0% | 0 | 0
| REPB42129 | WINDOWS | D | Pane: Reglaze single pane in 4mm clear or obscure glass, over 1.00sm, hack out and glaze with putty, sprigs, clips or beads at any level, touch up paintwork to match existing, and remove waste and debris. |  |  | 4.231 |  | 5150AD | SM | 1 | 67.93 | 67.93 | #VALUE! | #VALUE! | 0 | 55.7977 | 55.7977 | SM | 1 | 55.7977 | 55.7977 | 0% | 0 | 0% | 0 | 0
| REPB42129 | SCAFFOLD | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42129 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 170 | 12.92 | 2196.4 | #VALUE! | #VALUE! | 0 | 16.4084 | 2789.428 | M2 | 170 | 16.4084 | 2789.428 | 80% | 2231.5424 | 0% | 0 | 2231.5424
| REPB42129 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 80% | 426.72 | 0% | 0 | 426.72
| REPB42129 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 1 | 50 | 50 | #VALUE! | #VALUE! | 0 | 63.5 | 63.5 | unit | 1 | 63.5 | 63.5 | 80% | 50.8 | 0% | 0 | 50.8
| REPB42129 | SCAFFOLD | D | Scaffold taken up&over the roof |  |  | 2.17 |  | SC017 | unit | 1 | 842 | 842 | #VALUE! | #VALUE! | 0 | 1069.34 | 1069.34 | unit | 1 | 1069.34 | 1069.34 | 80% | 855.472 | 0% | 0 | 855.472
| REPB42129 | SCAFFOLD | D | Modular Beams (Measured as lm include inside/outside face of scaffold- 1 beam included) |  |  | 2.19 |  | SC019 | lm | 10 | 31.75 | 317.5 | #VALUE! | #VALUE! | 0 | 40.3225 | 403.225 | lm | 10 | 40.3225 | 403.225 | 80% | 322.58 | 0% | 0 | 322.58
| REPB42129 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB42129 | ESTATE WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42129 | ESTATE WORKS | D | Flag: Lift any size existing precast concrete paving flag, fill and compact hardcore to soft spots and rebed existing flag on 25mm bed of cement mortar (1:4) and point up joints. |  |  | 7.55 |  | 0070BF | NO | 15 | 6.68 | 100.2 | #VALUE! | #VALUE! | 0 | 5.493 | 82.3945 | NO | 15 | 5.493 | 82.3945 | 0% | 0 | 0% | 0 | 0
| REPB42129 | FRA WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42129 | FRA WORKS | D | Door:Renew internal door with any size single half-hour fire check glazed door having 3.2mm luan, white Meranti or other approved plywood facing both sides and 9mm hardwood lipping on long edges, including remove existing door and hinges, remove and refit door stops as necessary, fit and hang new door on 1.50 pairs of 100mm steel butt hinges, make good or alter recesses on frame, door complete with all ironmongery, intumescent strips and smoke seals, glazed, redecorate to match existing and remove waste and debris. |  |  | 13 |  | 3300FC | Item | 2 | 222.2 | 444.4 | #VALUE! | #VALUE! | 0 | 196.9803 | 393.9606 | Item | 2 | 196.9803 | 393.9606 | 0% | 0 | 0% | 0 | 0
| REPB42129 | FRA WORKS | D | Fire Upgrading Coating:Remove all existing defective paint to plastered or rendered wall surfaces back to a solid edge, feather off and repair any defective areas with a high quality filler as necessary, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, wash down, rinse, clean off and apply one full coat of fire upgrading primer at a coverage rate of 10sm per litre, apply two full coats of fire upgrading finish at a coverage rate of 10sm per litre. |  |  | 27 |  | 4801AB | Item | 1 | 22.53 | 22.53 | #VALUE! | #VALUE! | 0 | 19.1505 | 19.1505 | Item | 1 | 19.1505 | 19.1505 | 0% | 0 | 0% | 0 | 0
| REPB42129 | FRA WORKS | D | Fire Upgrading Coating:Strip off existing multi layer paint coatings to existing plastered or rendered soffits with a proprietary paint stripper, scrape off or remove with a proprietary paint scraper, wash down,rinse, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, clean off and apply one full coat of primer at a coverage rate of 10sm per litre, apply one full coats of colourcoat complete with decorative flakes, and apply one full coat of gloss or satin lacquer finish at a coverage rate of 10sm per litre. |  |  | 41 |  | 4804AD | Item | 1 | 29.34 | 29.34 | #VALUE! | #VALUE! | 0 | 24.939 | 24.939 | Item | 1 | 24.939 | 24.939 | 0% | 0 | 0% | 0 | 0
| REPB42129 | FRA WORKS | D | Fire Alarm:Install L2 type fire alarm installation complete to BS5839:Part6 1995, control panel, circuits, call points, automatic detectors and sounders, builders work, make good, test, commission, and remove waste and debris. |  |  | 93 |  | 8711GA | Item | 1 | 550 | 550 | #VALUE! | #VALUE! | 0 | 440 | 440 | Item | 1 | 440 | 440 | 0% | 0 | 0% | 0 | 0
| REPB42129 | FRA WORKS | D | Intumescent Strip:Renew or supply and fix new 22x4mm intumescent strip, half hour application, with integral cold smoke seal and setting into groove in timber frame or door. |  |  | 104 |  | 3431AC | Item | 2 | 3.44 | 6.88 | #VALUE! | #VALUE! | 0 | 3.0496 | 6.0991 | Item | 2 | 3.0496 | 6.0991 | 0% | 0 | 0% | 0 | 0
| REPB42129 | FRA WORKS | D | Smoke Detector:Renew existing with mains operated optical smoke detector with rechargeable DC battery or condensor back up self contained type to BS 5446 kitemark certified with hush button, including back plate and all necessary connections to existing wiring, test and make good on completion, where interlinked detectors are replaced new detectors must be compatible with existing, and remove waste and debris. |  |  | 115 |  | 8720FA | Item | 2 | 70.11 | 140.22 | #VALUE! | #VALUE! | 0 | 56.088 | 112.176 | Item | 2 | 56.088 | 112.176 | 0% | 0 | 0% | 0 | 0
| REPB42129 | FRA WORKS | D | Closer:Renew or supply and fix Perko type concealed door closer screwed to door and frame, including remove and refix door or door stop as necessary. |  |  | 175 |  | 3905BA | Item | 2 | 9.81 | 19.62 | #VALUE! | #VALUE! | 0 | 8.6966 | 17.3931 | Item | 2 | 8.6966 | 17.3931 | 0% | 0 | 0% | 0 | 0
| REPB42129 | FRA WORKS | D | Partition:Supply and erect or renew stud partition comprising ne 50x100mm sole and head plate, noggins and studs fixed with nails or plugged and screwed to walls, and pack out and scribe, 12.5mm butt jointed plasterboard and 3mm plaster skim coat and all labours to both faces. |  |  | 180 |  | 3013AB | Item | 1 | 62.11 | 62.11 | #VALUE! | #VALUE! | 0 | 55.0605 | 55.0605 | Item | 1 | 55.0605 | 55.0605 | 0% | 0 | 0% | 0 | 0
| REPB42129 | FRA WORKS | D | Test:Carry out test of domestic installation to occupied property complete comprising continuity, insulation resistance, polarity, earth fault loop impedance and operation of residual current operated device, disconnect, repair and renew as necessary after removal of illegal wiring and components, and provide report and NICEIC/ECA test certificate to the Client’s Representative, and remove waste and debris. |  |  | 186 |  | 8950AA | Item | 1 | 86.88 | 86.88 | #VALUE! | #VALUE! | 0 | 69.504 | 69.504 | Item | 1 | 69.504 | 69.504 | 0% | 0 | 0% | 0 | 0
| REPB42129 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to the fire alarm system. |  |  | 190 |  | PROV SUM | Item | 1 | 1500 | 1500 | #VALUE! | 1500 |  | 1500 | 1500 | Item | 1 | 1500 | 1500 | 0% | 0 | 0% | 0 | 0
| REPB42129 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to clear waste and debris from fire escape routes. |  |  | 191 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  | 100 | 100 | Item | 1 | 100 | 100 | 0% | 0 | 0% | 0 | 0
| REPB42129 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional fire stopping works |  |  | 192 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  | 100 | 100 | Item | 1 | 100 | 100 | 0% | 0 | 0% | 0 | 0
| REPB42129 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional signage |  |  | 193 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  | 100 | 100 | Item | 1 | 100 | 100 | 0% | 0 | 0% | 0 | 0
| REPB42129 | FRA WORKS | D |  |  |  | 194 |  | PROV SUM | Item | 1 | 350 | 350 | #VALUE! | 350 |  | 350 | 350 | Item | 1 | 350 | 350 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 15466.5622 |  |  | TOTAL | 15466.5622 |  | 3887.1144 |  | 0 | 3887.1144

## 130 POW Road
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
130 Prince Of Wales Road
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB42458 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB42458 | ENERGY EFFICIENY | H
| REPB42458 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! | 0 | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB42458 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0 | 0
| REPB42458 | ASBESTOS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42458 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB42458 | COMMUNAL WORKS | H | [23 empty] | 0
| REPB42458 | [25 empty] | 0
| REPB42458 | EXTREP | H | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris. | [22 empty] | 0
| REPB42458 | EXTREP | D | Wall: Rake out existing joints of brickwork min 12mm and repoint brickwork in mortar to match existing and remove waste and debris. |  |  | 6.91 |  | 1021AA | SM | 10 | 20.13 | 201.3 | #VALUE! | #VALUE! | 0 | 14.5942 | 145.9425 | SM | 10 | 14.5942 | 145.9425 | 0% | 0 | 0% | 0 | 0
| REPB42458 | EXTREP | D | Coping: Take off precast coping ne 300mm wide, clean mortar from top of wall and coping, bed and point in cement lime mortar (1:1:6) with bonding agent and remove waste and debris. |  |  | 6.127 |  | 1033CA | LM | 12 | 6.04 | 72.48 | #VALUE! | #VALUE! | 0 | 4.379 | 52.548 | LM | 12 | 4.379 | 52.548 | 0% | 0 | 0% | 0 | 0
| REPB42458 | EXTREP | D | Walls: Wash down, fill in cracks and holes, sand smooth and apply two coats of smooth finish masonry paint to rendered or concrete surfaces of walls. |  |  | 6.194 |  | 4360BA | SM | 110 | 7.02 | 772.2 | #VALUE! | #VALUE! | 0 | 5.967 | 656.37 | SM | 110 | 5.967 | 656.37 | 0% | 0 | 0% | 0 | 0
| REPB42458 | EXTREP | D | Balustrading: Wire brush, prepare for and apply one undercoat and two coats of gloss paint on existing painted surfaces ornamental metal balustrading, railings or gates (measured both sides). |  |  | 6.215 |  | 4363EA | SM | 18 | 16.08 | 289.44 | #VALUE! | #VALUE! | 0 | 13.668 | 246.024 | SM | 18 | 13.668 | 246.024 | 0% | 0 | 0% | 0 | 0
| REPB42458 | EXTREP | D | Window: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on surfaces of wooden windowsl (one side and edges). |  |  | 6.236 |  | 4380BA | SM | 18 | 25.87 | 465.66 | #VALUE! | #VALUE! | 0 | 21.9895 | 395.811 | SM | 18 | 21.9895 | 395.811 | 0% | 0 | 0% | 0 | 0
| REPB42458 | EXTREP | D | Frame: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on timber frame ne 300mm girth. |  |  | 6.237 |  | 4380CA | LM | 30 | 6.28 | 188.4 | #VALUE! | #VALUE! | 0 | 5.338 | 160.14 | LM | 30 | 5.338 | 160.14 | 0% | 0 | 0% | 0 | 0
| REPB42458 | EXTREP | D | Door: Rub down, prepare for and apply one coat of primer, one undercoat and two coats of gloss paint to all surfaces of any size or type of single glazed timber door. (one sides and edges). |  |  | 6.238 |  | 4380DA | IT | 5 | 20.71 | 103.55 | #VALUE! | #VALUE! | 0 | 17.6035 | 88.0175 | IT | 5 | 17.6035 | 88.0175 | 0% | 0 | 0% | 0 | 0
| REPB42458 | EXTREP | D | Wall: Apply 12mm cement and sand render (1:3) with waterproofing agent to external walls including ‘Rough Sandtex’ finish, dub out as necessary with cement and sand and all labours and remove waste and debris. |  |  | 6.305 |  | 4210AF | SM | 2 | 33.5 | 67 | #VALUE! | #VALUE! | 0 | 24.2875 | 48.575 | SM | 2 | 24.2875 | 48.575 | 0% | 0 | 0% | 0 | 0
| REPB42458 | EXTREP | D | Render Repairs: Repair crack in any external render including carefully hack out and make good with cement and sand including applying finish to match existing, and remove waste and debris. |  |  | 6.306 |  | 4230ZA | LM | 2 | 6.87 | 13.74 | #VALUE! | #VALUE! | 0 | 4.9807 | 9.9615 | LM | 2 | 4.9807 | 9.9615 | 0% | 0 | 0% | 0 | 0
| REPB42458 | ROOF | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42458 | ROOF | D | PROVISIONAL SUM: Slate: Remove any size natural slates and carefully stack, renew roofing felt and battens and refix slates with clips or copper nails, and remove waste and debris. |  |  | 3.434 |  | PROV SUM | SUM | 1 | 2200 | 2200 | #VALUE! | 2200 |  |  | 2200 | SUM | 1 |  | 2200 | 0% | 0 | 0% | 0 | 0
| REPB42458 | ROOF | D | PROVISIONAL SUM: Slate: Overhaul natural slate roof, refix loose slates, renew broken or missing slates to match existing, redress, rewedge and repoint all flashings, aprons, chimney gutters etc, cut out and make good cement weather fillets, repoint in cement mortar (1:3) to all hips, ridges and verges, make good, and remove waste and debris. |  |  | 3.435 |  | PROV SUM | SUM | 1 | 1300 | 1300 | #VALUE! | 1300 |  |  | 1300 | SUM | 1 |  | 1300 | 0% | 0 | 0% | 0 | 0
| REPB42458 | ROOF | D | PROVISIONAL SUM: Roof Covering: Extra over any renewal or refixing of natural slates for renew roofing felt and battens. |  |  | 3.436 |  | PROV SUM | SUM | 1 | 900 | 900 | #VALUE! | 900 |  |  | 900 | SUM | 1 |  | 900 | 0% | 0 | 0% | 0 | 0
| REPB42458 | WINDOWS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42458 | WINDOWS | D | Soft wood timber splice with resin; face splice repair method no. 5. Remove old and loose paint as necessary. Cut out decayed timber from windows and frames, piecing in or frame in new wrought softwood with resin to match existing. Leave ready to decorate. Splice not exc 500 to 1000mm |  |  | 4.11 |  | WIND017 | Nr | 5 | 36.75 | 183.75 | #VALUE! | #VALUE! | 0 | 34.9125 | 174.5625 | Nr | 5 | 34.9125 | 174.5625 | 0% | 0 | 0% | 0 | 0
| REPB42458 | WINDOWS | D | 7. Timber repair system; using window care dry fix/dry flex RP; Conservation Joint; Up to 50mm |  |  | 4.13 |  | WIND022 | Nr | 60 | 4.25 | 255 | #VALUE! | #VALUE! | 0 | 4.0375 | 242.25 | Nr | 60 | 4.0375 | 242.25 | 0% | 0 | 0% | 0 | 0
| REPB42458 | WINDOWS | D | 7. Timber repair system; using window care dry fix/dry flex RP; Conservation Joint; up to 100mm |  |  | 4.14 |  | WIND023 | Nr | 10 | 6.75 | 67.5 | #VALUE! | #VALUE! | 0 | 6.4125 | 64.125 | Nr | 10 | 6.4125 | 64.125 | 0% | 0 | 0% | 0 | 0
| REPB42458 | WINDOWS | D | Window: Overhaul timber sash window, renew staff and parting beads, take out sashes and later rehang on appropriate sized new undyed plaited nylon sash cords, renew pocket pieces, wedge and cramp loose sash frames, oil pulleys, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.9 |  | 3150CA | NO | 6 | 35.61 | 213.66 | #VALUE! | #VALUE! | 0 | 31.5683 | 189.4096 | NO | 6 | 31.5683 | 189.4096 | 0% | 0 | 0% | 0 | 0
| REPB42458 | WINDOWS | D | Pane: Reglaze single pane in 4mm clear or obscure glass, over 1.00sm, hack out and glaze with putty, sprigs, clips or beads at any level, touch up paintwork to match existing, and remove waste and debris. |  |  | 4.231 |  | 5150AD | SM | 1 | 67.93 | 67.93 | #VALUE! | #VALUE! | 0 | 55.7977 | 55.7977 | SM | 1 | 55.7977 | 55.7977 | 0% | 0 | 0% | 0 | 0
| REPB42458 | SCAFFOLD | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42458 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 120 | 12.92 | 1550.4 | #VALUE! | #VALUE! | 0 | 16.4084 | 1969.008 | M2 | 120 | 16.4084 | 1969.008 | 0% | 0 | 0% | 0 | 0
| REPB42458 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 0% | 0 | 0% | 0 | 0
| REPB42458 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 1 | 50 | 50 | #VALUE! | #VALUE! | 0 | 63.5 | 63.5 | unit | 1 | 63.5 | 63.5 | 0% | 0 | 0% | 0 | 0
| REPB42458 | SCAFFOLD | D | Scaffold taken up&over the roof |  |  | 2.17 |  | SC017 | unit | 1 | 842 | 842 | #VALUE! | #VALUE! | 0 | 1069.34 | 1069.34 | unit | 1 | 1069.34 | 1069.34 | 0% | 0 | 0% | 0 | 0
| REPB42458 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB42458 | ESTATE WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42458 | ESTATE WORKS | D | PROVISIONAL SUM: Paving: Supply and lay new brick paving including excavate to level, lay 100mm hardcore bed and lay new paving on 25mm bed of cement mortar (1:4) or 50mm sand bed including all pointing and cutting and bonding. |  |  | 7.316 |  | PROV SUM | SUM | 1 | 240 | 240 | #VALUE! | 240 |  |  | 240 | SUM | 1 |  | 240 | 0% | 0 | 0% | 0 | 0
| REPB42458 | ESTATE WORKS | D | PROVISIONAL SUM: Fencing: Renew or provide new 1.65m tanalised timber vertical board fencing including for taking down remnants of existing fence and posts set in concrete, remove from site to approved tip, and set 125x125mm x 2.65m long softwood posts in concrete at ne 1.80m centres with three 69x44mm softwood rails bolted to posts and 144x20mm vertical boards nailed to rails, softwood gravel board with centre prop (measured per metre run of fencing). |  |  | 7.317 |  | PROV SUM | SUM | 1 | 450 | 450 | #VALUE! | 450 |  |  | 450 | SUM | 1 |  | 450 | 0% | 0 | 0% | 0 | 0
| REPB42458 | ESTATE WORKS | D | PROVISIONAL SUM: Fence Post: Renew tanalised softwood fence post set in hardcore or concrete size 100x100mm and ne 2.40m long including any struts, excavate hole, place hardcore and or concrete, backfill, remove and refix fencing, and remove waste and debris, reinstate paving, gardens and the like as necessary. |  |  | 7.318 |  | PROV SUM | SUM | 1 | 150 | 150 | #VALUE! | 150 |  |  | 150 | SUM | 1 |  | 150 | 0% | 0 | 0% | 0 | 0
| REPB42458 | ESTATE WORKS | D | PROVISIONAL SUM: Wall: Demolish as necessary, clean off and clear away, rebuild one brick wall in common bricks, bed and point in cement lime mortar (1:1:6) to match existing and remove waste and debris. |  |  | 7.319 |  | PROV SUM | SUM | 1 | 1000 | 1000 | #VALUE! | 1000 |  |  | 1000 | SUM | 1 |  | 1000 | 0% | 0 | 0% | 0 | 0
| REPB42458 | FRA WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42458 | FRA WORKS | D | Door:Renew internal door with any size single half-hour fire check glazed door having 3.2mm luan, white Meranti or other approved plywood facing both sides and 9mm hardwood lipping on long edges, including remove existing door and hinges, remove and refit door stops as necessary, fit and hang new door on 1.50 pairs of 100mm steel butt hinges, make good or alter recesses on frame, door complete with all ironmongery, intumescent strips and smoke seals, glazed, redecorate to match existing and remove waste and debris. |  |  | 13 |  | 3300FC | Item | 2 | 222.2 | 444.4 | #VALUE! | #VALUE! | 0 | 196.9803 | 393.9606 | Item | 2 | 196.9803 | 393.9606 | 0% | 0 | 0% | 0 | 0
| REPB42458 | FRA WORKS | D | Fire Upgrading Coating:Remove all existing defective paint to plastered or rendered wall surfaces back to a solid edge, feather off and repair any defective areas with a high quality filler as necessary, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, wash down, rinse, clean off and apply one full coat of fire upgrading primer at a coverage rate of 10sm per litre, apply two full coats of fire upgrading finish at a coverage rate of 10sm per litre. |  |  | 27 |  | 4801AB | Item | 1 | 22.53 | 22.53 | #VALUE! | #VALUE! | 0 | 19.1505 | 19.1505 | Item | 1 | 19.1505 | 19.1505 | 0% | 0 | 0% | 0 | 0
| REPB42458 | FRA WORKS | D | Fire Upgrading Coating:Strip off existing multi layer paint coatings to existing plastered or rendered soffits with a proprietary paint stripper, scrape off or remove with a proprietary paint scraper, wash down,rinse, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, clean off and apply one full coat of primer at a coverage rate of 10sm per litre, apply one full coats of colourcoat complete with decorative flakes, and apply one full coat of gloss or satin lacquer finish at a coverage rate of 10sm per litre. |  |  | 41 |  | 4804AD | Item | 1 | 29.34 | 29.34 | #VALUE! | #VALUE! | 0 | 24.939 | 24.939 | Item | 1 | 24.939 | 24.939 | 0% | 0 | 0% | 0 | 0
| REPB42458 | FRA WORKS | D | Fire Alarm:Install L2 type fire alarm installation complete to BS5839:Part6 1995, control panel, circuits, call points, automatic detectors and sounders, builders work, make good, test, commission, and remove waste and debris. |  |  | 93 |  | 8711GA | Item | 1 | 550 | 550 | #VALUE! | #VALUE! | 0 | 440 | 440 | Item | 1 | 440 | 440 | 0% | 0 | 0% | 0 | 0
| REPB42458 | FRA WORKS | D | Intumescent Strip:Renew or supply and fix new 22x4mm intumescent strip, half hour application, with integral cold smoke seal and setting into groove in timber frame or door. |  |  | 104 |  | 3431AC | Item | 2 | 3.44 | 6.88 | #VALUE! | #VALUE! | 0 | 3.0496 | 6.0991 | Item | 2 | 3.0496 | 6.0991 | 0% | 0 | 0% | 0 | 0
| REPB42458 | FRA WORKS | D | Smoke Detector:Renew existing with mains operated optical smoke detector with rechargeable DC battery or condensor back up self contained type to BS 5446 kitemark certified with hush button, including back plate and all necessary connections to existing wiring, test and make good on completion, where interlinked detectors are replaced new detectors must be compatible with existing, and remove waste and debris. |  |  | 115 |  | 8720FA | Item | 2 | 70.11 | 140.22 | #VALUE! | #VALUE! | 0 | 56.088 | 112.176 | Item | 2 | 56.088 | 112.176 | 0% | 0 | 0% | 0 | 0
| REPB42458 | FRA WORKS | D | Partition:Supply and erect or renew stud partition comprising ne 50x100mm sole and head plate, noggins and studs fixed with nails or plugged and screwed to walls, and pack out and scribe, 12.5mm butt jointed plasterboard and 3mm plaster skim coat and all labours to both faces. |  |  | 180 |  | 3013AB | Item | 1 | 62.11 | 62.11 | #VALUE! | #VALUE! | 0 | 55.0605 | 55.0605 | Item | 1 | 55.0605 | 55.0605 | 0% | 0 | 0% | 0 | 0
| REPB42458 | FRA WORKS | D | Test:Carry out test of domestic installation to occupied property complete comprising continuity, insulation resistance, polarity, earth fault loop impedance and operation of residual current operated device, disconnect, repair and renew as necessary after removal of illegal wiring and components, and provide report and NICEIC/ECA test certificate to the Client’s Representative, and remove waste and debris. |  |  | 186 |  | 8950AA | Item | 1 | 86.88 | 86.88 | #VALUE! | #VALUE! | 0 | 69.504 | 69.504 | Item | 1 | 69.504 | 69.504 | 0% | 0 | 0% | 0 | 0
| REPB42458 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to the fire alarm system. |  |  | 190 |  | PROV SUM | Item | 1 | 1500 | 1500 | #VALUE! | 1500 |  |  | 1500 | Item | 1 |  | 1500 | 0% | 0 | 0% | 0 | 0
| REPB42458 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to clear waste and debris from fire escape routes. |  |  | 191 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB42458 | FRA WORKS | D |  |  |  | 192 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB42458 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional signage |  |  | 193 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB42458 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional electrical works |  |  | 194 |  | PROV SUM | Item | 1 | 350 | 350 | #VALUE! | 350 |  |  | 350 | Item | 1 |  | 350 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 16297.9675 |  |  | TOTAL | 16297.9675 |  | 0 |  | 0 | 0

## 25 Herbert Street
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
25 Herbert Street
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB42313 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB42313 | ENERGY EFFICIENY | H
| REPB42313 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! | 0 | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB42313 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0 | 0
| REPB42313 | ASBESTOS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42313 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB42313 | COMMUNAL WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42313 | COMMUNAL WORKS | D | Hall: Thoroughly clean down all wall and ceiling surfaces to common areas to remove dirt, grease and surface containments, scrape and remove all loose and defective coatings, prime bare areas with one coat of fire retardant primer and apply two coats of Class ‘O’ fire retardant matt paint, prepare and apply two coats of polyurethane lacquer or one undercoat and one gloss coat to all previously decorated timber surfaces to lobby, hall or corridor over 3.00sm ceiling area complete (classified as a single area). |  |  | 5.1 |  | 4540AC | IT | 1 | 480 | 480 | #VALUE! | #VALUE! | 0 | 408 | 408 | IT | 1 | 408 | 408 | 0% | 0 | 0% | 0 | 0
| REPB42313 | COMMUNAL WORKS | D | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris. |  |  | 5.165 |  | 4328BC | SM | 4 | 38.13 | 152.52 | #VALUE! | #VALUE! | 0 | 32.1207 | 128.4828 | SM | 4 | 32.1207 | 128.4828 | 0% | 0 | 0% | 0 | 0
| REPB42313 | COMMUNAL WORKS | D | Wall: Hack off any thickness of render from walls, rake out and prepare brickwork or blockwork to receive rendering and remove waste and debris. |  |  | 5.173 |  | 4210AA | SM | 2 | 12.5 | 25 | #VALUE! | #VALUE! | 0 | 9.0625 | 18.125 | SM | 2 | 9.0625 | 18.125 | 0% | 0 | 0% | 0 | 0
| REPB42313 | COMMUNAL WORKS | D | Wall: Apply 12mm cement and sand render (1:3) with waterproofing agent to external walls trowelled smooth, dub out as necessary with cement and sand, including all labours and remove waste and debris. |  |  | 5.174 |  | 4210AB | SM | 2 | 20.44 | 40.88 | #VALUE! | #VALUE! | 0 | 14.819 | 29.638 | SM | 2 | 14.819 | 29.638 | 0% | 0 | 0% | 0 | 0
| REPB42313 | EXTREP | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42313 | EXTREP | D | Wall: Rake out existing joints of brickwork min 12mm and repoint brickwork in mortar to match existing and remove waste and debris. |  |  | 6.91 |  | 1021AA | SM | 3 | 20.13 | 60.39 | #VALUE! | #VALUE! | 0 | 14.5942 | 43.7827 | SM | 3 | 14.5942 | 43.7827 | 0% | 0 | 0% | 0 | 0
| REPB42313 | EXTREP | D | Walls: Prepare and apply two coats smooth or textured masonry paint to external rendered surfaces of walls. |  |  | 6.179 |  | 4356AA | SM | 1 | 10.36 | 10.36 | #VALUE! | #VALUE! | 0 | 8.806 | 8.806 | SM | 1 | 8.806 | 8.806 | 0% | 0 | 0% | 0 | 0
| REPB42313 | EXTREP | D | Gates: Wire brush, prepare for, and apply one coat primer, one undercoat, two coats of gloss paint to both sides of any size type single metal gate including all edges and all surfaces of posts. |  |  | 6.203 |  | 4362DA | IT | 1 | 21.61 | 21.61 | #VALUE! | #VALUE! | 0 | 18.3685 | 18.3685 | IT | 1 | 18.3685 | 18.3685 | 0% | 0 | 0% | 0 | 0
| REPB42313 | EXTREP | D | Window: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on surfaces of wooden windowsl (one side and edges). |  |  | 6.236 |  | 4380BA | SM | 22 | 25.87 | 569.14 | #VALUE! | #VALUE! | 0 | 21.9895 | 483.769 | SM | 22 | 21.9895 | 483.769 | 0% | 0 | 0% | 0 | 0
| REPB42313 | EXTREP | D | Frame: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on timber frame ne 300mm girth. |  |  | 6.237 |  | 4380CA | LM | 6 | 6.28 | 37.68 | #VALUE! | #VALUE! | 0 | 5.338 | 32.028 | LM | 6 | 5.338 | 32.028 | 0% | 0 | 0% | 0 | 0
| REPB42313 | ROOF | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42313 | ROOF | D | Felt: Renew two layer felt to any girth gutter including remove defective felt and lay new felt bedded in hot bitumen, and remove waste and debris. |  |  | 3.14 |  | 2170EA | LM | 4 | 22.84 | 91.36 | #VALUE! | #VALUE! | 0 | 18.272 | 73.088 | LM | 4 | 18.272 | 73.088 | 0% | 0 | 0% | 0 | 0
| REPB42313 | ROOF | D | Valley: Renew lead valley gutter not exceeding 800mm girth, remove and refix roof tiles or slates and battens as required, including all necessary labours and remove waste and debris. |  |  | 3.171 |  | 2310CC | LM | 2 | 91.63 | 183.26 | #VALUE! | #VALUE! | 0 | 73.304 | 146.608 | LM | 2 | 73.304 | 146.608 | 0% | 0 | 0% | 0 | 0
| REPB42313 | ROOF | D | Slate: Overhaul natural slate roof, refix loose slates, renew broken or missing slates to match existing, redress, rewedge and repoint all flashings, aprons, chimney gutters etc, cut out and make good cement weather fillets, repoint in cement mortar (1:3) to all hips, ridges and verges, make good, and remove waste and debris. |  |  | 3.215 |  | 2033CA | SM | 5 | 30.56 | 152.8 | #VALUE! | #VALUE! | 0 | 24.448 | 122.24 | SM | 5 | 24.448 | 122.24 | 0% | 0 | 0% | 0 | 0
| REPB42313 | WINDOWS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42313 | WINDOWS | D | Window: Overhaul timber sash window, renew staff and parting beads, take out sashes and later rehang on appropriate sized new undyed plaited nylon sash cords, renew pocket pieces, wedge and cramp loose sash frames, oil pulleys, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.9 |  | 3150CA | NO | 6 | 35.61 | 213.66 | #VALUE! | #VALUE! | 0 | 31.5683 | 189.4096 | NO | 6 | 31.5683 | 189.4096 | 0% | 0 | 0% | 0 | 0
| REPB42313 | WINDOWS | D | Window: Overhaul sash window, renew staff and parting beads, take out sashes and later rehang on spiral sash balances, renew pocket pieces, wedge and cramp loose sash frames, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.91 |  | 3150CB | NO | 3 | 98.99 | 296.97 | #VALUE! | #VALUE! | 0 | 87.7546 | 263.2639 | NO | 3 | 87.7546 | 263.2639 | 0% | 0 | 0% | 0 | 0
| REPB42313 | SCAFFOLD | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42313 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 99 | 12.92 | 1279.08 | #VALUE! | #VALUE! | 0 | 16.4084 | 1624.4316 | M2 | 99 | 16.4084 | 1624.4316 | 0% | 0 | 0% | 0 | 0
| REPB42313 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 0% | 0 | 0% | 0 | 0
| REPB42313 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 1 | 50 | 50 | #VALUE! | #VALUE! | 0 | 63.5 | 63.5 | unit | 1 | 63.5 | 63.5 | 0% | 0 | 0% | 0 | 0
| REPB42313 | SCAFFOLD | D | Scaffold taken through property (protection to surfaces included) |  |  | 2.16 |  | SC016 | unit | 1 | 379.8 | 379.8 | #VALUE! | #VALUE! | 0 | 482.346 | 482.346 | unit | 1 | 482.346 | 482.346 | 0% | 0 | 0% | 0 | 0
| REPB42313 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB42313 | ESTATE WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42313 | ESTATE WORKS | D | PROVISIONAL SUM: Allow provisional sum for unforeseen works, as no access to rear made. |  |  | 7.316 |  | PROV SUM | SUM | 1 | 400 | 400 | #VALUE! | 400 |  |  | 400 | SUM | 1 |  | 400 | 0% | 0 | 0% | 0 | 0
| REPB42313 | FRA WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42313 | FRA WORKS | D | Intumescent Strip:Renew or supply and fix new 22x4mm intumescent strip, half hour application, with integral cold smoke seal and setting into groove in timber frame or door. |  |  | 104 |  | 3431AC | Item | 2 | 3.44 | 6.88 | #VALUE! | #VALUE! | 0 | 3.0496 | 6.0991 | Item | 2 | 3.0496 | 6.0991 | 0% | 0 | 0% | 0 | 0
| REPB42313 | FRA WORKS | D | Smoke Detector:Renew existing with mains operated optical smoke detector with rechargeable DC battery or condensor back up self contained type to BS 5446 kitemark certified with hush button, including back plate and all necessary connections to existing wiring, test and make good on completion, where interlinked detectors are replaced new detectors must be compatible with existing, and remove waste and debris. |  |  | 115 |  | 8720FA | Item | 2 | 70.11 | 140.22 | #VALUE! | #VALUE! | 0 | 56.088 | 112.176 | Item | 2 | 56.088 | 112.176 | 0% | 0 | 0% | 0 | 0
| REPB42313 | FRA WORKS | D | Test:Carry out test of domestic installation to occupied property complete comprising continuity, insulation resistance, polarity, earth fault loop impedance and operation of residual current operated device, disconnect, repair and renew as necessary after removal of illegal wiring and components, and provide report and NICEIC/ECA test certificate to the Client’s Representative, and remove waste and debris. |  |  | 186 |  | 8950AA | Item | 1 | 86.88 | 86.88 | #VALUE! | #VALUE! | 0 | 69.504 | 69.504 | Item | 1 | 69.504 | 69.504 | 0% | 0 | 0% | 0 | 0
| REPB42313 | FRA WORKS | D | Door and Frame:Renew internal door and frincluding remove existing door, hinges and frame, install 32mm door frame with 25x32mm stops, fit and hang new any size FD30S plywood faced fire check flush door on 1.5 pairs of 100mm steel hinges, make good or alter recesses on frame, door complete with all ironmongery, intumescent strips and smoke seals, make good and prepare door and frame for decoration and remove waste and debris. |  |  | 189 |  | 3300DA | Item | 1 | 152.85 | 152.85 | #VALUE! | #VALUE! | 0 | 135.5015 | 135.5015 | Item | 1 | 135.5015 | 135.5015 | 0% | 0 | 0% | 0 | 0
| REPB42313 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to the fire alarm system. |  |  | 190 |  | PROV SUM | Item | 1 | 1500 | 1500 | #VALUE! | 1500 |  |  | 1500 | Item | 1 |  | 1500 | 0% | 0 | 0% | 0 | 0
| REPB42313 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to clear waste and debris from fire escape routes. |  |  | 191 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB42313 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional fire stopping works |  |  | 192 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB42313 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional signage |  |  | 193 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB42313 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional electrical works |  |  | 194 |  | PROV SUM | Item | 1 | 350 | 350 | #VALUE! | 350 |  |  | 350 | Item | 1 |  | 350 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 8164.8634 |  |  | TOTAL | 8164.8634 |  | 0 |  | 0 | 0

## 128 POW Road
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
128 Prince Of Wales Road
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB42457 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB42457 | ENERGY EFFICIENY | H
| REPB42457 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! | 0 | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB42457 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0 | 0
| REPB42457 | ASBESTOS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42457 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB42457 | COMMUNAL WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42457 | COMMUNAL WORKS | D | Hall: Thoroughly clean down all wall and ceiling surfaces to common areas to remove dirt, grease and surface containments, scrape and remove all loose and defective coatings, prime bare areas with one coat of fire retardant primer and apply two coats of Class ‘O’ fire retardant matt paint, prepare and apply two coats of polyurethane lacquer or one undercoat and one gloss coat to all previously decorated timber surfaces to lobby, hall or corridor over 3.00sm ceiling area complete (classified as a single area). |  |  | 5.1 |  | 4540AC | IT | 1 | 480 | 480 | #VALUE! | #VALUE! | 0 | 408 | 408 | IT | 1 | 408 | 408 | 0% | 0 | 0% | 0 | 0
| REPB42457 | COMMUNAL WORKS | D | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris. |  |  | 5.148 |  | 4326BB | SM | 2 | 40.94 | 81.88 | #VALUE! | #VALUE! | 0 | 34.4879 | 68.9757 | SM | 2 | 34.4879 | 68.9757 | 0% | 0 | 0% | 0 | 0
| REPB42457 | EXTREP | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42457 | EXTREP | D | Wall: Rake out existing joints of brickwork min 12mm and repoint brickwork in mortar to match existing and remove waste and debris. |  |  | 6.91 |  | 1021AA | SM | 2 | 20.13 | 40.26 | #VALUE! | #VALUE! | 0 | 14.5942 | 29.1885 | SM | 2 | 14.5942 | 29.1885 | 0% | 0 | 0% | 0 | 0
| REPB42457 | EXTREP | D | Walls:Wash down, fill in cracks and holes, sand down and apply one undercoat and one coat of gloss paint to rendered or concrete walls. |  |  | 6.197 |  | 4361AB | SM | 8 | 15.71 | 125.68 | #VALUE! | #VALUE! | 0 | 13.3535 | 106.828 | SM | 8 | 13.3535 | 106.828 | 0% | 0 | 0% | 0 | 0
| REPB42457 | EXTREP | D | Gates: Wire brush, prepare for, and apply one coat primer, one undercoat, two coats of gloss paint to both sides of any size type single metal gate including all edges and all surfaces of posts. |  |  | 6.203 |  | 4362DA | IT | 1 | 21.61 | 21.61 | #VALUE! | #VALUE! | 0 | 18.3685 | 18.3685 | IT | 1 | 18.3685 | 18.3685 | 0% | 0 | 0% | 0 | 0
| REPB42457 | EXTREP | D | Balustrading: Wire brush, prepare for and apply one coat of primer, one undercoat, two coats of gloss paint on ornamental metal balustrading, railings or gates (measured both sides). |  |  | 6.204 |  | 4362EA | SM | 8 | 20.51 | 164.08 | #VALUE! | #VALUE! | 0 | 17.4335 | 139.468 | SM | 8 | 17.4335 | 139.468 | 0% | 0 | 0% | 0 | 0
| REPB42457 | EXTREP | D | Window: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on surfaces of wooden windowsl (one side and edges). |  |  | 6.236 |  | 4380BA | SM | 10 | 25.87 | 258.7 | #VALUE! | #VALUE! | 0 | 21.9895 | 219.895 | SM | 10 | 21.9895 | 219.895 | 0% | 0 | 0% | 0 | 0
| REPB42457 | EXTREP | D | Frame: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on timber frame ne 300mm girth. |  |  | 6.237 |  | 4380CA | LM | 14 | 6.28 | 87.92 | #VALUE! | #VALUE! | 0 | 5.338 | 74.732 | LM | 14 | 5.338 | 74.732 | 0% | 0 | 0% | 0 | 0
| REPB42457 | EXTREP | D | Door: Rub down, prepare for and apply one coat of primer, one undercoat and two coats of gloss paint to all surfaces of any size or type of single glazed timber door. (one sides and edges). |  |  | 6.238 |  | 4380DA | IT | 3 | 20.71 | 62.13 | #VALUE! | #VALUE! | 0 | 17.6035 | 52.8105 | IT | 3 | 17.6035 | 52.8105 | 0% | 0 | 0% | 0 | 0
| REPB42457 | ROOF | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42457 | [20 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42457 | WINDOWS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42457 | WINDOWS | D | Window: Overhaul timber casement window, dismantle as necessary and subsequently reassemble including freeing, easing and adjusting casements to give correct operation, renew sealing gaskets, renew fixing screws, remove, refit or renew ironmongery as necessary, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.89 |  | 3150BA | NO | 1 | 29.05 | 29.05 | #VALUE! | #VALUE! | 0 | 25.7528 | 25.7528 | NO | 1 | 25.7528 | 25.7528 | 0% | 0 | 0% | 0 | 0
| REPB42457 | WINDOWS | D | Window: Overhaul timber sash window, renew staff and parting beads, take out sashes and later rehang on appropriate sized new undyed plaited nylon sash cords, renew pocket pieces, wedge and cramp loose sash frames, oil pulleys, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.9 |  | 3150CA | NO | 5 | 35.61 | 178.05 | #VALUE! | #VALUE! | 0 | 31.5683 | 157.8413 | NO | 5 | 31.5683 | 157.8413 | 0% | 0 | 0% | 0 | 0
| REPB42457 | SCAFFOLD | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42457 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 140 | 12.92 | 1808.8 | #VALUE! | #VALUE! | 0 | 16.4084 | 2297.176 | M2 | 140 | 16.4084 | 2297.176 | 0% | 0 | 0% | 0 | 0
| REPB42457 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 0% | 0 | 0% | 0 | 0
| REPB42457 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 1 | 50 | 50 | #VALUE! | #VALUE! | 0 | 63.5 | 63.5 | unit | 1 | 63.5 | 63.5 | 0% | 0 | 0% | 0 | 0
| REPB42457 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB42457 | ESTATE WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42457 | FRA WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42457 | FRA WORKS | D | Door:Renew internal door with any size single half-hour fire check glazed door having 3.2mm luan, white Meranti or other approved plywood facing both sides and 9mm hardwood lipping on long edges, including remove existing door and hinges, remove and refit door stops as necessary, fit and hang new door on 1.50 pairs of 100mm steel butt hinges, make good or alter recesses on frame, door complete with all ironmongery, intumescent strips and smoke seals, glazed, redecorate to match existing and remove waste and debris. |  |  | 13 |  | 3300FC | Item | 2 | 222.2 | 444.4 | #VALUE! | #VALUE! | 0 | 196.9803 | 393.9606 | Item | 2 | 196.9803 | 393.9606 | 0% | 0 | 0% | 0 | 0
| REPB42457 | FRA WORKS | D | Fire Upgrading Coating:Remove all existing defective paint to plastered or rendered wall surfaces back to a solid edge, feather off and repair any defective areas with a high quality filler as necessary, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, wash down, rinse, clean off and apply one full coat of fire upgrading primer at a coverage rate of 10sm per litre, apply two full coats of fire upgrading finish at a coverage rate of 10sm per litre. |  |  | 27 |  | 4801AB | Item | 1 | 22.53 | 22.53 | #VALUE! | #VALUE! | 0 | 19.1505 | 19.1505 | Item | 1 | 19.1505 | 19.1505 | 0% | 0 | 0% | 0 | 0
| REPB42457 | FRA WORKS | D | Fire Upgrading Coating:Strip off existing multi layer paint coatings to existing plastered or rendered soffits with a proprietary paint stripper, scrape off or remove with a proprietary paint scraper, wash down,rinse, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, clean off and apply one full coat of primer at a coverage rate of 10sm per litre, apply one full coats of colourcoat complete with decorative flakes, and apply one full coat of gloss or satin lacquer finish at a coverage rate of 10sm per litre. |  |  | 41 |  | 4804AD | Item | 1 | 29.34 | 29.34 | #VALUE! | #VALUE! | 0 | 24.939 | 24.939 | Item | 1 | 24.939 | 24.939 | 0% | 0 | 0% | 0 | 0
| REPB42457 | FRA WORKS | D | Fire Alarm:Install L2 type fire alarm installation complete to BS5839:Part6 1995, control panel, circuits, call points, automatic detectors and sounders, builders work, make good, test, commission, and remove waste and debris. |  |  | 93 |  | 8711GA | Item | 1 | 550 | 550 | #VALUE! | #VALUE! | 0 | 440 | 440 | Item | 1 | 440 | 440 | 0% | 0 | 0% | 0 | 0
| REPB42457 | FRA WORKS | D | Intumescent Strip:Renew or supply and fix new 22x4mm intumescent strip, half hour application, with integral cold smoke seal and setting into groove in timber frame or door. |  |  | 104 |  | 3431AC | Item | 2 | 3.44 | 6.88 | #VALUE! | #VALUE! | 0 | 3.0496 | 6.0991 | Item | 2 | 3.0496 | 6.0991 | 0% | 0 | 0% | 0 | 0
| REPB42457 | FRA WORKS | D | Smoke Detector:Renew existing with mains operated optical smoke detector with rechargeable DC battery or condensor back up self contained type to BS 5446 kitemark certified with hush button, including back plate and all necessary connections to existing wiring, test and make good on completion, where interlinked detectors are replaced new detectors must be compatible with existing, and remove waste and debris. |  |  | 115 |  | 8720FA | Item | 2 | 70.11 | 140.22 | #VALUE! | #VALUE! | 0 | 56.088 | 112.176 | Item | 2 | 56.088 | 112.176 | 0% | 0 | 0% | 0 | 0
| REPB42457 | FRA WORKS | D | Closer:Renew or supply and fix Perko type concealed door closer screwed to door and frame, including remove and refix door or door stop as necessary. |  |  | 175 |  | 3905BA | Item | 2 | 9.81 | 19.62 | #VALUE! | #VALUE! | 0 | 8.6966 | 17.3931 | Item | 2 | 8.6966 | 17.3931 | 0% | 0 | 0% | 0 | 0
| REPB42457 | FRA WORKS | D | Partition:Supply and erect or renew stud partition comprising ne 50x100mm sole and head plate, noggins and studs fixed with nails or plugged and screwed to walls, and pack out and scribe, 12.5mm butt jointed plasterboard and 3mm plaster skim coat and all labours to both faces. |  |  | 180 |  | 3013AB | Item | 1 | 62.11 | 62.11 | #VALUE! | #VALUE! | 0 | 55.0605 | 55.0605 | Item | 1 | 55.0605 | 55.0605 | 0% | 0 | 0% | 0 | 0
| REPB42457 | FRA WORKS | D | Test:Carry out test of domestic installation to occupied property complete comprising continuity, insulation resistance, polarity, earth fault loop impedance and operation of residual current operated device, disconnect, repair and renew as necessary after removal of illegal wiring and components, and provide report and NICEIC/ECA test certificate to the Client’s Representative, and remove waste and debris. |  |  | 186 |  | 8950AA | Item | 1 | 86.88 | 86.88 | #VALUE! | #VALUE! | 0 | 69.504 | 69.504 | Item | 1 | 69.504 | 69.504 | 0% | 0 | 0% | 0 | 0
| REPB42457 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to the fire alarm system. |  |  | 190 |  | PROV SUM | Item | 1 | 1500 | 1500 | #VALUE! | 1500 |  |  | 1500 | Item | 1 |  | 1500 | 0% | 0 | 0% | 0 | 0
| REPB42457 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to clear waste and debris from fire escape routes. |  |  | 191 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB42457 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional fire stopping works |  |  | 192 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB42457 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional signage |  |  | 193 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB42457 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional electrical works |  |  | 194 |  | PROV SUM | Item | 1 | 350 | 350 | #VALUE! | 350 |  |  | 350 | Item | 1 |  | 350 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 8106.5147 |  |  | TOTAL | 8106.5147 |  | 0 |  | 0 | 0

## 10 Gillies Street
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
10 Gillies Street
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB42153 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB42153 | ENERGY EFFICIENY | H
| REPB42153 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! | 0 | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB42153 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0 | 0
| REPB42153 | ASBESTOS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42153 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB42153 | COMMUNAL WORKS | H | [23 empty] | 0
| REPB42153 | EXTREP | H | [23 empty] | 0
| REPB42153 | EXTREP | D | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris. |  |  | 6.91 |  | 1021AA | SM | 12 | 20.13 | 241.56 | #VALUE! | #VALUE! | 0 | 14.5942 | 175.131 | SM | 12 | 14.5942 | 175.131 | 0% | 0 | 0% | 0 | 0
| REPB42153 | EXTREP | D | Gates:Wire brush, prepare for, and apply one coat primer, one undercoat, two coats of gloss paint to both sides of any size type single metal gate including all edges and all surfaces of posts. |  |  | 6.203 |  | 4362DA | IT | 1 | 21.61 | 21.61 | #VALUE! | #VALUE! | 0 | 18.3685 | 18.3685 | IT | 1 | 18.3685 | 18.3685 | 0% | 0 | 0% | 0 | 0
| REPB42153 | EXTREP | D | Window:Rub down, prepare and apply one undercoat and one coat of gloss paint on existing painted surfaces of wooden windows (one side and edges). |  |  | 6.262 |  | 4381JB | SM | 22 | 16.86 | 370.92 | #VALUE! | #VALUE! | 0 | 14.331 | 315.282 | SM | 22 | 14.331 | 315.282 | 0% | 0 | 0% | 0 | 0
| REPB42153 | EXTREP | D | Frame:Rub down, prepare and apply one undercoat and one coat of gloss paint on existing painted timber frame ne 300mm girth. |  |  | 6.263 |  | 4381KA | LM | 44 | 3.81 | 167.64 | #VALUE! | #VALUE! | 0 | 3.2385 | 142.494 | LM | 44 | 3.2385 | 142.494 | 0% | 0 | 0% | 0 | 0
| REPB42153 | EXTREP | D | Door:Rub down, prepare for and apply one undercoat and one coat of gloss paint to all existing painted surfaces of any size or type of single glazed timber door (one sides and edges). |  |  | 6.264 |  | 4381LA | IT | 2 | 9.67 | 19.34 | #VALUE! | #VALUE! | 0 | 8.2195 | 16.439 | IT | 2 | 8.2195 | 16.439 | 0% | 0 | 0% | 0 | 0
| REPB42153 | ROOF | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42153 | ROOF | D | Moss:Carefully remove moss/lichen growth on roof covering of any kind and dispose of debris off site, reistate all disturbed surfaces, replace broken tiles, slates and the like, thoroughly clean out valleys, gutters, downpipes, hoppers etc, prepare and treat the complete roof area with a diluted fungicide solution AKZO or other equal and approved applied strictly in accordance with the manufacturer’s instructions, thoroughly clean out all gutters and the like to remove all chemical residue arising upon completion of the works, and remove waste and debris. |  |  | 3.18 |  | 2115AA | SM | 2 | 10.17 | 20.34 | #VALUE! | #VALUE! | 0 | 8.136 | 16.272 | SM | 2 | 8.136 | 16.272 | 0% | 0 | 0% | 0 | 0
| REPB42153 | ROOF | D | Gutter:Clean out debris from gutters to any type of property including flush out and test, rod downpipe including clean out gulley and remove debris from site on completion (per elevation). |  |  | 3.364 |  | 6039BA | IT | 2 | 20.13 | 40.26 | #VALUE! | #VALUE! | 0 | 14.9183 | 29.8367 | IT | 2 | 14.9183 | 29.8367 | 0% | 0 | 0% | 0 | 0
| REPB42153 | WINDOWS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42153 | WINDOWS | D | Window: Overhaul timber casement window, dismantle as necessary and subsequently reassemble including freeing, easing and adjusting casements to give correct operation, renew sealing gaskets, renew fixing screws, remove, refit or renew ironmongery as necessary, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.89 |  | 3150BA | NO | 6 | 29.05 | 174.3 | #VALUE! | #VALUE! | 0 | 25.7528 | 154.5169 | NO | 6 | 25.7528 | 154.5169 | 0% | 0 | 0% | 0 | 0
| REPB42153 | WINDOWS | D | Window: Overhaul sash window, renew staff and parting beads, take out sashes and later rehang on spiral sash balances, renew pocket pieces, wedge and cramp loose sash frames, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.91 |  | 3150CB | NO | 5 | 98.99 | 494.95 | #VALUE! | #VALUE! | 0 | 87.7546 | 438.7732 | NO | 5 | 87.7546 | 438.7732 | 0% | 0 | 0% | 0 | 0
| REPB42153 | SCAFFOLD | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42153 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 100 | 12.92 | 1292 | #VALUE! | #VALUE! | 0 | 16.4084 | 1640.84 | M2 | 100 | 16.4084 | 1640.84 | 80% | 1312.672 | 0% | 0 | 1312.672
| REPB42153 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 80% | 426.72 | 0% | 0 | 426.72
| REPB42153 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 1 | 50 | 50 | #VALUE! | #VALUE! | 0 | 63.5 | 63.5 | unit | 1 | 63.5 | 63.5 | 80% | 50.8 | 0% | 0 | 50.8
| REPB42153 | SCAFFOLD | D | Scaffold taken up&over the roof |  |  | 2.17 |  | SC017 | unit | 1 | 842 | 842 | #VALUE! | #VALUE! | 0 | 1069.34 | 1069.34 | unit | 1 | 1069.34 | 1069.34 | 80% | 855.472 | 0% | 0 | 855.472
| REPB42153 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB42153 | ESTATE WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB42153 | ESTATE WORKS | D | Path:Excavate 250mm below required finished level, remove waste and debris, level and compact bottoms of excavations and fill, 150mm hardcore bed, blinded and ne 100mm concrete trowelled smooth including dishing to gullies and the like and all formwork. |  |  | 7.4 |  | 0030AA | SM | 18 | 58.8 | 1058.4 | #VALUE! | #VALUE! | 0 | 48.3512 | 870.3223 | SM | 18 | 48.3512 | 870.3223 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 6106.8112 |  |  | TOTAL | 6106.8112 |  | 2645.664 |  | 0 | 2645.664

## 17 Ascham Street
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
17 Ascham Street
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB47024 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB47024 | ENERGY EFFICIENY | H
| REPB47024 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! | 0 | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB47024 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0 | 0
| REPB47024 | ASBESTOS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47024 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB47024 | COMMUNAL WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47024 | COMMUNAL WORKS | D | Hall: Thoroughly clean down all wall and ceiling surfaces to common areas to remove dirt, grease and surface containments, scrape and remove all loose and defective coatings, prime bare areas with one coat of fire retardant primer and apply two coats of Class ‘O’ fire retardant matt paint, prepare and apply two coats of polyurethane lacquer or one undercoat and one gloss coat to all previously decorated timber surfaces to lobby, hall or corridor over 3.00sm ceiling area complete (classified as a single area). |  |  | 5.1 |  | 4540AC | IT | 1 | 480 | 480 | #VALUE! | #VALUE! | 0 | 408 | 408 | IT | 1 | 408 | 408 | 0% | 0 | 0% | 0 | 0
| REPB47024 | COMMUNAL WORKS | D | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris. |  |  | 5.154 |  | 4328AC | SM | 6 | 16.28 | 97.68 | #VALUE! | #VALUE! | 0 | 13.7143 | 82.2856 | SM | 6 | 13.7143 | 82.2856 | 0% | 0 | 0% | 0 | 0
| REPB47024 | EXTREP | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47024 | EXTREP | D | Fracture: Remove any applied finish and cut out bricks as necessary to either side of fracture, one face only, stitch in new bricks, bed and point to match existing in cement lime mortar (1:1:6), and make good any applied finishes, and remove waste and debris (measured over mean general line of fracture). |  |  | 6.82 |  | 1019AA | LM | 4 | 44.12 | 176.48 | #VALUE! | #VALUE! | 0 | 31.987 | 127.948 | LM | 4 | 31.987 | 127.948 | 0% | 0 | 0% | 0 | 0
| REPB47024 | EXTREP | D | Wall: Rake out existing joints of brickwork min 12mm and repoint brickwork in mortar to match existing and remove waste and debris. |  |  | 6.91 |  | 1021AA | SM | 8 | 20.13 | 161.04 | #VALUE! | #VALUE! | 0 | 14.5942 | 116.754 | SM | 8 | 14.5942 | 116.754 | 0% | 0 | 0% | 0 | 0
| REPB47024 | EXTREP | D | Walls: Wash down, fill in cracks and holes, sand down and apply two coats of smooth or textured masonry paint to brickwork surfaces of walls. |  |  | 6.182 |  | 4356AD | SM | 6 | 10.17 | 61.02 | #VALUE! | #VALUE! | 0 | 8.6445 | 51.867 | SM | 6 | 8.6445 | 51.867 | 0% | 0 | 0% | 0 | 0
| REPB47024 | EXTREP | D | Gates: Wire brush, prepare for and apply one undercoat and two coats of gloss paint to both sides of existing painted surface of any size/type single metal gate including all edges and all surfaces of posts. |  |  | 6.214 |  | 4363DA | IT | 1 | 16.98 | 16.98 | #VALUE! | #VALUE! | 0 | 14.433 | 14.433 | IT | 1 | 14.433 | 14.433 | 0% | 0 | 0% | 0 | 0
| REPB47024 | EXTREP | D | Frame: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on timber frame ne 300mm girth. |  |  | 6.237 |  | 4380CA | LM | 6 | 6.28 | 37.68 | #VALUE! | #VALUE! | 0 | 5.338 | 32.028 | LM | 6 | 5.338 | 32.028 | 0% | 0 | 0% | 0 | 0
| REPB47024 | EXTREP | D | Door: Rub down, prepare for and apply one coat of primer, one undercoat and two coats of gloss paint to all surfaces of any size or type of single glazed timber door (both sides and edges). |  |  | 6.239 |  | 4380DB | IT | 2 | 39.28 | 78.56 | #VALUE! | #VALUE! | 0 | 33.388 | 66.776 | IT | 2 | 33.388 | 66.776 | 0% | 0 | 0% | 0 | 0
| REPB47024 | EXTREP | D | Window: Rub down, prepare and apply one undercoat and one coat of gloss paint on existing painted surfaces of wooden windows (one side and edges). |  |  | 6.262 |  | 4381JB | SM | 16 | 16.86 | 269.76 | #VALUE! | #VALUE! | 0 | 14.331 | 229.296 | SM | 16 | 14.331 | 229.296 | 0% | 0 | 0% | 0 | 0
| REPB47024 | ROOF | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47024 | ROOF | D | Slate: Overhaul natural slate roof, refix loose slates, renew broken or missing slates to match existing, redress, rewedge and repoint all flashings, aprons, chimney gutters etc, cut out and make good cement weather fillets, repoint in cement mortar (1:3) to all hips, ridges and verges, make good, and remove waste and debris. |  |  | 3.215 |  | 2033CA | SM | 50 | 30.56 | 1528 | #VALUE! | #VALUE! | 0 | 24.448 | 1222.4 | SM | 50 | 24.448 | 1222.4 | 0% | 0 | 0% | 0 | 0
| REPB47024 | WINDOWS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47024 | WINDOWS | D | Window: Overhaul timber sash window, renew staff and parting beads, take out sashes and later rehang on appropriate sized new undyed plaited nylon sash cords, renew pocket pieces, wedge and cramp loose sash frames, oil pulleys, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.9 |  | 3150CA | NO | 40 | 35.61 | 1424.4 | #VALUE! | #VALUE! | 0 | 31.5683 | 1262.7306 | NO | 40 | 31.5683 | 1262.7306 | 0% | 0 | 0% | 0 | 0
| REPB47024 | SCAFFOLD | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47024 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 106 | 12.92 | 1369.52 | #VALUE! | #VALUE! | 0 | 16.4084 | 1739.2904 | M2 | 106 | 16.4084 | 1739.2904 | 0% | 0 | 0% | 0 | 0
| REPB47024 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 0% | 0 | 0% | 0 | 0
| REPB47024 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 1 | 50 | 50 | #VALUE! | #VALUE! | 0 | 63.5 | 63.5 | unit | 1 | 63.5 | 63.5 | 0% | 0 | 0% | 0 | 0
| REPB47024 | SCAFFOLD | D | Up&over boarded walkway bridge (over the roof) boarded and handrails included |  |  | 2.15 |  | SC015 | unit | 1 | 1310 | 1310 | #VALUE! | #VALUE! | 0 | 1663.7 | 1663.7 | unit | 1 | 1663.7 | 1663.7 | 0% | 0 | 0% | 0 | 0
| REPB47024 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB47024 | ESTATE WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47024 | ESTATE WORKS | D | Wall: Take down one and a half brick wall and remove waste and debris. |  |  | 7.19 |  | 1011AC | SM | 4 | 39.57 | 158.28 | #VALUE! | #VALUE! | 0 | 28.6883 | 114.753 | SM | 4 | 28.6883 | 114.753 | 0% | 0 | 0% | 0 | 0
| REPB47024 | ESTATE WORKS | D | Wall: Supply and lay new facing bricks in one brick wall bedded and pointed in cement lime mortar (1:1:6) as the work proceeds. |  |  | 7.202 |  | 1013BB | SM | 6 | 133.12 | 798.72 | #VALUE! | #VALUE! | 0 | 96.512 | 579.072 | SM | 6 | 96.512 | 579.072 | 0% | 0 | 0% | 0 | 0
| REPB47024 | ESTATE WORKS | D | Pier: Demolish as necessary, clean off and clear away, rebuild attached pier in common bricks, one brick wide x half brick projection, bedded and pointed in cement lime mortar (1:1:6) to match existing and remove waste and debris. |  |  | 7.236 |  | 1017AA | LM | 1 | 21.51 | 21.51 | #VALUE! | #VALUE! | 0 | 15.5948 | 15.5948 | LM | 1 | 15.5948 | 15.5948 | 0% | 0 | 0% | 0 | 0
| REPB47024 | ESTATE WORKS | D | PROVISIONAL SUM: Allow provisional sum for any unforeseen works to rear elevation. |  |  | 7.316 |  | PROV SUM | SUM | 1 | 400 | 400 | #VALUE! | 400 |  |  | 400 | SUM | 1 |  | 400 | 0% | 0 | 0% | 0 | 0
| REPB47024 | FRA WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47024 | FRA WORKS | D | Door:Renew internal door with any size single half-hour fire check glazed door having 3.2mm luan, white Meranti or other approved plywood facing both sides and 9mm hardwood lipping on long edges, including remove existing door and hinges, remove and refit door stops as necessary, fit and hang new door on 1.50 pairs of 100mm steel butt hinges, make good or alter recesses on frame, door complete with all ironmongery, intumescent strips and smoke seals, glazed, redecorate to match existing and remove waste and debris. |  |  | 13 |  | 3300FC | Item | 2 | 222.2 | 444.4 | #VALUE! | #VALUE! | 0 | 196.9803 | 393.9606 | Item | 2 | 196.9803 | 393.9606 | 0% | 0 | 0% | 0 | 0
| REPB47024 | FRA WORKS | D | Fire Upgrading Coating:Remove all existing defective paint to plastered or rendered wall surfaces back to a solid edge, feather off and repair any defective areas with a high quality filler as necessary, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, wash down, rinse, clean off and apply one full coat of fire upgrading primer at a coverage rate of 10sm per litre, apply two full coats of fire upgrading finish at a coverage rate of 10sm per litre. |  |  | 27 |  | 4801AB | Item | 1 | 22.53 | 22.53 | #VALUE! | #VALUE! | 0 | 19.1505 | 19.1505 | Item | 1 | 19.1505 | 19.1505 | 0% | 0 | 0% | 0 | 0
| REPB47024 | FRA WORKS | D | Fire Upgrading Coating:Strip off existing multi layer paint coatings to existing plastered or rendered soffits with a proprietary paint stripper, scrape off or remove with a proprietary paint scraper, wash down,rinse, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, clean off and apply one full coat of primer at a coverage rate of 10sm per litre, apply one full coats of colourcoat complete with decorative flakes, and apply one full coat of gloss or satin lacquer finish at a coverage rate of 10sm per litre. |  |  | 41 |  | 4804AD | Item | 1 | 29.34 | 29.34 | #VALUE! | #VALUE! | 0 | 24.939 | 24.939 | Item | 1 | 24.939 | 24.939 | 0% | 0 | 0% | 0 | 0
| REPB47024 | FRA WORKS | D | Smoke Detector:Renew existing with mains operated optical smoke detector with rechargeable DC battery or condensor back up self contained type to BS 5446 kitemark certified with hush button, including back plate and all necessary connections to existing wiring, test and make good on completion, where interlinked detectors are replaced new detectors must be compatible with existing, and remove waste and debris. |  |  | 115 |  | 8720FA | Item | 2 | 70.11 | 140.22 | #VALUE! | #VALUE! | 0 | 56.088 | 112.176 | Item | 2 | 56.088 | 112.176 | 0% | 0 | 0% | 0 | 0
| REPB47024 | FRA WORKS | D | Partition:Supply and erect or renew stud partition comprising ne 50x100mm sole and head plate, noggins and studs fixed with nails or plugged and screwed to walls, and pack out and scribe, 12.5mm butt jointed plasterboard and 3mm plaster skim coat and all labours to both faces. |  |  | 180 |  | 3013AB | Item | 1 | 62.11 | 62.11 | #VALUE! | #VALUE! | 0 | 55.0605 | 55.0605 | Item | 1 | 55.0605 | 55.0605 | 0% | 0 | 0% | 0 | 0
| REPB47024 | FRA WORKS | D | Test:Carry out test of domestic installation to occupied property complete comprising continuity, insulation resistance, polarity, earth fault loop impedance and operation of residual current operated device, disconnect, repair and renew as necessary after removal of illegal wiring and components, and provide report and NICEIC/ECA test certificate to the Client’s Representative, and remove waste and debris. |  |  | 186 |  | 8950AA | Item | 1 | 86.88 | 86.88 | #VALUE! | #VALUE! | 0 | 69.504 | 69.504 | Item | 1 | 69.504 | 69.504 | 0% | 0 | 0% | 0 | 0
| REPB47024 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to the fire alarm system. |  |  | 190 |  | PROV SUM | Item | 1 | 1500 | 1500 | #VALUE! | 1500 |  |  | 1500 | Item | 1 |  | 1500 | 0% | 0 | 0% | 0 | 0
| REPB47024 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to clear waste and debris from fire escape routes. |  |  | 191 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47024 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional fire stopping works |  |  | 192 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47024 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional signage |  |  | 193 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47024 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional electrical works |  |  | 194 |  | PROV SUM | Item | 1 | 350 | 350 | #VALUE! | 350 |  |  | 350 | Item | 1 |  | 350 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 12170.9145 |  |  | TOTAL | 12170.9145 |  | 0 |  | 0 | 0

## 13 Doynton Street
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
13 Doynton Street
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB47344 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB47344 | ENERGY EFFICIENY | H
| REPB47344 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! | 0 | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB47344 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0 | 0
| REPB47344 | ASBESTOS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47344 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB47344 | COMMUNAL WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47344 | [20 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47344 | EXTREP | H | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris. | [17 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47344 | EXTREP | D | Wall: Rake out existing joints of brickwork min 12mm and repoint brickwork in mortar to match existing and remove waste and debris. |  |  | 6.91 |  | 1021AA | SM | 2 | 20.13 | 40.26 | #VALUE! | #VALUE! | 0 | 14.5942 | 29.1885 | SM | 2 | 14.5942 | 29.1885 | 0% | 0 | 0% | 0 | 0
| REPB47344 | EXTREP | D | Cill: Cut out and remove existing cill from brick wall, prepare and lay precast concrete splay rebated twice grooved, finished fair cill with stooled ends reinforced with 2 No. 6mm diameter bars bedded in cement lime mortar (1:1:6) renew dpc and make good brickwork, plasterwork, sealant and or cement fillets and remove waste and debris. |  |  | 6.117 |  | 1031CA | LM | 4 | 38.38 | 153.52 | #VALUE! | #VALUE! | 0 | 27.8255 | 111.302 | LM | 4 | 27.8255 | 111.302 | 0% | 0 | 0% | 0 | 0
| REPB47344 | EXTREP | D | Walls: Wash down, fill in cracks and holes, sand down and apply one undercoat and one coat of gloss paint to rendered or concrete walls. |  |  | 6.197 |  | 4361AB | SM | 20 | 15.71 | 314.2 | #VALUE! | #VALUE! | 0 | 13.3535 | 267.07 | SM | 20 | 13.3535 | 267.07 | 0% | 0 | 0% | 0 | 0
| REPB47344 | EXTREP | D | Balustrading: Wire brush, prepare for and apply one coat of primer, one undercoat, two coats of gloss paint on ornamental metal balustrading, railings or gates (measured both sides). |  |  | 6.204 |  | 4362EA | SM | 8 | 20.51 | 164.08 | #VALUE! | #VALUE! | 0 | 17.4335 | 139.468 | SM | 8 | 17.4335 | 139.468 | 0% | 0 | 0% | 0 | 0
| REPB47344 | EXTREP | D | Window: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on surfaces of wooden windowsl (one side and edges). |  |  | 6.236 |  | 4380BA | SM | 24 | 25.87 | 620.88 | #VALUE! | #VALUE! | 0 | 21.9895 | 527.748 | SM | 24 | 21.9895 | 527.748 | 0% | 0 | 0% | 0 | 0
| REPB47344 | EXTREP | D | Frame: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on timber frame ne 300mm girth. |  |  | 6.237 |  | 4380CA | LM | 28 | 6.28 | 175.84 | #VALUE! | #VALUE! | 0 | 5.338 | 149.464 | LM | 28 | 5.338 | 149.464 | 0% | 0 | 0% | 0 | 0
| REPB47344 | EXTREP | D | Door: Rub down, prepare for and apply one coat of primer, one undercoat and two coats of gloss paint to all surfaces of any size or type of single glazed timber door. (one sides and edges). |  |  | 6.238 |  | 4380DA | IT | 4 | 20.71 | 82.84 | #VALUE! | #VALUE! | 0 | 17.6035 | 70.414 | IT | 4 | 17.6035 | 70.414 | 0% | 0 | 0% | 0 | 0
| REPB47344 | ROOF | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47344 | ROOF | D | PROV SUM: Slate: Overhaul natural slate roof, refix loose slates, renew broken or missing slates to match existing, redress, rewedge and repoint all flashings, aprons, chimney gutters etc, cut out and make good cement weather fillets, repoint in cement mortar (1:3) to all hips, ridges and verges, make good, and remove waste and debris. Code 2033CA |  |  | 3.434 |  | PROV SUM | SM | 30 | 30.56 | 916.8 | #VALUE! | 916.8 |  |  | 916.8 | SM | 30 |  | 916.8 | 0% | 0 | 0% | 0 | 0
| REPB47344 | WINDOWS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47344 | WINDOWS | D | Window: Overhaul timber casement window, dismantle as necessary and subsequently reassemble including freeing, easing and adjusting casements to give correct operation, renew sealing gaskets, renew fixing screws, remove, refit or renew ironmongery as necessary, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.89 |  | 3150BA | NO | 2 | 29.05 | 58.1 | #VALUE! | #VALUE! | 0 | 25.7528 | 51.5056 | NO | 2 | 25.7528 | 51.5056 | 0% | 0 | 0% | 0 | 0
| REPB47344 | WINDOWS | D | Window: Overhaul timber sash window, renew staff and parting beads, take out sashes and later rehang on appropriate sized new undyed plaited nylon sash cords, renew pocket pieces, wedge and cramp loose sash frames, oil pulleys, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.9 |  | 3150CA | NO | 10 | 35.61 | 356.1 | #VALUE! | #VALUE! | 0 | 31.5683 | 315.6826 | NO | 10 | 31.5683 | 315.6826 | 0% | 0 | 0% | 0 | 0
| REPB47344 | SCAFFOLD | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47344 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 70 | 12.92 | 904.4 | #VALUE! | #VALUE! | 0 | 16.4084 | 1148.588 | M2 | 70 | 16.4084 | 1148.588 | 80% | 918.8704 | 0% | 0 | 918.8704
| REPB47344 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 80% | 426.72 | 0% | 0 | 426.72
| REPB47344 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB47344 | ESTATE WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47344 | FRA WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47344 | FRA WORKS | D | Fire Alarm:Install L2 type fire alarm installation complete to BS5839:Part6 1995, control panel, circuits, call points, automatic detectors and sounders, builders work, make good, test, commission, and remove waste and debris. |  |  | 93 |  | 8711GA | Item | 1 | 550 | 550 | #VALUE! | #VALUE! | 0 | 440 | 440 | Item | 1 | 440 | 440 | 0% | 0 | 0% | 0 | 0
| REPB47344 | FRA WORKS | D | Intumescent Strip:Renew or supply and fix new 22x4mm intumescent strip, half hour application, with integral cold smoke seal and setting into groove in timber frame or door. |  |  | 104 |  | 3431AC | Item | 2 | 3.44 | 6.88 | #VALUE! | #VALUE! | 0 | 3.0496 | 6.0991 | Item | 2 | 3.0496 | 6.0991 | 0% | 0 | 0% | 0 | 0
| REPB47344 | FRA WORKS | D | Smoke Detector:Renew existing with mains operated optical smoke detector with rechargeable DC battery or condensor back up self contained type to BS 5446 kitemark certified with hush button, including back plate and all necessary connections to existing wiring, test and make good on completion, where interlinked detectors are replaced new detectors must be compatible with existing, and remove waste and debris. |  |  | 115 |  | 8720FA | Item | 2 | 70.11 | 140.22 | #VALUE! | #VALUE! | 0 | 56.088 | 112.176 | Item | 2 | 56.088 | 112.176 | 0% | 0 | 0% | 0 | 0
| REPB47344 | FRA WORKS | D | Closer:Renew or supply and fix Perko type concealed door closer screwed to door and frame, including remove and refix door or door stop as necessary. |  |  | 175 |  | 3905BA | Item | 1 | 9.81 | 9.81 | #VALUE! | #VALUE! | 0 | 8.6966 | 8.6966 | Item | 1 | 8.6966 | 8.6966 | 0% | 0 | 0% | 0 | 0
| REPB47344 | FRA WORKS | D | Test:Carry out test of domestic installation to occupied property complete comprising continuity, insulation resistance, polarity, earth fault loop impedance and operation of residual current operated device, disconnect, repair and renew as necessary after removal of illegal wiring and components, and provide report and NICEIC/ECA test certificate to the Client’s Representative, and remove waste and debris. |  |  | 186 |  | 8950AA | Item | 1 | 86.88 | 86.88 | #VALUE! | #VALUE! | 0 | 69.504 | 69.504 | Item | 1 | 69.504 | 69.504 | 0% | 0 | 0% | 0 | 0
| REPB47344 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to the fire alarm system. |  |  | 190 |  | PROV SUM | Item | 1 | 1500 | 1500 | #VALUE! | 1500 |  |  | 1500 | Item | 1 |  | 1500 | 0% | 0 | 0% | 0 | 0
| REPB47344 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to clear waste and debris from fire escape routes. |  |  | 191 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47344 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional fire stopping works |  |  | 192 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47344 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional signage |  |  | 193 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47344 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional electrical works |  |  | 194 |  | PROV SUM | Item | 1 | 350 | 350 | #VALUE! | 350 |  |  | 350 | Item | 1 |  | 350 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 7669.402 |  |  | TOTAL | 7669.402 |  | 1345.5904 |  | 0 | 1345.5904

## 111 Chetwynd Road
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
111 Chetwynd Road
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB47293 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB47293 | ENERGY EFFICIENY | H
| REPB47293 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! | 0 | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB47293 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0 | 0
| REPB47293 | ASBESTOS | H | [18 empty] | 0 |  |  |  |  | 0
| REPB47293 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB47293 | COMMUNAL WORKS | H | [18 empty] | 0 |  |  |  |  | 0
| REPB47293 | COMMUNAL WORKS | D | Door: Renew front door with any size 44mm hardwood panelled, glazed or part glazed door prepared for glazing, hang on 1.5 pair butts, fix new mortice lock, furniture, keep, pair of bolts, cylinder latch and pull, security restraint device, letter plate including cutting mortice in door to suit, numerals, hardwood weathermould, adjust stops, ease rebates, cut out and make good to frame to suit new position of butts, weathermould, lock and latch, rebate door bottom as necessary and fit new waterbar if required, double glazed and decorate to match existing internally and prepare for redecoration externally, and remove waste and debris. |  |  | 5.326 |  | 3211BA | NO | 1 | 461.13 | 461.13 | #VALUE! | #VALUE! | 0 | 408.7917 | 408.7917 | NO | 1 | 408.7917 | 408.7917 | 0% | 0 | 0% | 0 | 0
| REPB47293 | COMMUNAL WORKS | D | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris. |  |  | 5.386 |  | PROV SUM | SUM | 1 | 150 | 150 | #VALUE! | 150 |  |  | 150 | SUM | 1 |  | 150 | 0% | 0 | 0% | 0 | 0
| REPB47293 | COMMUNAL WORKS | D | PROVISIONAL SUM: Take up and renew existing floor covering (SM 20). |  |  | 5.387 |  | PROV SUM | SUM | 1 | 200 | 200 | #VALUE! | 200 |  |  | 200 | SUM | 1 |  | 200 | 0% | 0 | 0% | 0 | 0
| REPB47293 | COMMUNAL WORKS | D | PROV SUM: Hall: Thoroughly clean down all wall and ceiling surfaces to common areas to remove dirt, grease and surface containments, scrape and remove all loose and defective coatings, prime bare areas with one coat of fire retardant primer and apply two coats of Class ‘O’ fire retardant matt paint, prepare and apply two coats of polyurethane lacquer or one undercoat and one gloss coat to all previously decorated timber surfaces to lobby, hall or corridor over 3.00sm ceiling area complete (classified as a single area). Code 4540AC |  |  | 5.388 |  | PROV SUM | IT | 1 | 480 | 480 | #VALUE! | 480 |  |  | 480 | IT | 1 |  | 480 | 0% | 0 | 0% | 0 | 0
| REPB47293 | EXTREP | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47293 | EXTREP | D | Moulding Repairs 0-5no. per property Fosroc repair mortar or equivalent Insitu repairs using straight edge to form moulding repair. (Girth NE300mm Length NE300mm) |  |  | 6.11 |  | FAB071 | no | 1 | 79.14 | 79.14 | #VALUE! | #VALUE! | 0 | 63.312 | 63.312 | no | 1 | 63.312 | 63.312 | 0% | 0 | 0% | 0 | 0
| REPB47293 | EXTREP | D | Fracture: Remove any applied finish and cut out bricks as necessary to either side of fracture, one face only, stitch in new bricks, bed and point to match existing in cement lime mortar (1:1:6), and make good any applied finishes, and remove waste and debris (measured over mean general line of fracture). |  |  | 6.82 |  | 1019AA | LM | 40 | 44.12 | 1764.8 | #VALUE! | #VALUE! | 0 | 31.987 | 1279.48 | LM | 40 | 31.987 | 1279.48 | 0% | 0 | 0% | 0 | 0
| REPB47293 | EXTREP | D | Cills: Prepare, clean off all dust and debris, fill in or resurface cracks or spalled surfaces of concrete with epoxy mortar in surfaces of cills, not exceeding 300mm girth, repair over 5 and ne 10mm deep, and remove waste and debris. |  |  | 6.161 |  | 1460AF | LM | 22 | 38.25 | 841.5 | #VALUE! | #VALUE! | 0 | 27.7312 | 610.0875 | LM | 22 | 27.7312 | 610.0875 | 0% | 0 | 0% | 0 | 0
| REPB47293 | EXTREP | D | Walls: Wash down, fill in cracks and holes, sand smooth and apply two coats of smooth finish masonry paint to rendered or concrete surfaces of walls. |  |  | 6.194 |  | 4360BA | SM | 25 | 7.02 | 175.5 | #VALUE! | #VALUE! | 0 | 5.967 | 149.175 | SM | 25 | 5.967 | 149.175 | 0% | 0 | 0% | 0 | 0
| REPB47293 | EXTREP | D | Gates: Wire brush, prepare for and apply one undercoat, one coat of gloss paint to both sides of existing painted any size/type single metal gate including all edges and all surfaces of posts. |  |  | 6.224 |  | 4364CA | IT | 1 | 12.36 | 12.36 | #VALUE! | #VALUE! | 0 | 10.506 | 10.506 | IT | 1 | 10.506 | 10.506 | 0% | 0 | 0% | 0 | 0
| REPB47293 | EXTREP | D | Fascias, soffits, Bargeboards and the like:Rub down, prepare for, and apply one undercoat, two coats of gloss paint on existing painted surfaces of facias, soffits, bargeboards and the like ne 300mm girth. |  |  | 6.26 |  | 4381HB | LM | 29 | 3.74 | 108.46 | #VALUE! | #VALUE! | 0 | 3.179 | 92.191 | LM | 29 | 3.179 | 92.191 | 0% | 0 | 0% | 0 | 0
| REPB47293 | EXTREP | D | Window: Rub down, prepare and apply one undercoat and one coat of gloss paint on existing painted surfaces of wooden windows (one side and edges). |  |  | 6.262 |  | 4381JB | SM | 31 | 16.86 | 522.66 | #VALUE! | #VALUE! | 0 | 14.331 | 444.261 | SM | 31 | 14.331 | 444.261 | 0% | 0 | 0% | 0 | 0
| REPB47293 | ROOF | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47293 | ROOF | D | Gutter: Clean out debris from gutters to any type of property including flush out and test, rod downpipe including clean out gulley and remove debris from site on completion (per elevation). |  |  | 3.364 |  | 6039BA | IT | 3 | 20.13 | 60.39 | #VALUE! | #VALUE! | 0 | 14.9183 | 44.755 | IT | 3 | 14.9183 | 44.755 | 0% | 0 | 0% | 0 | 0
| REPB47293 | ROOF | D | Chimney: Renew facing bricks in chimney stack in area ne 0.50sm, cut out defective bricks, lay new facing bricks bedded and pointed in mortar to match existing and remove waste and debris. |  |  | 3.422 |  | 1200AN | NO | 1 | 66.79 | 66.79 | #VALUE! | #VALUE! | 0 | 48.4228 | 48.4228 | NO | 1 | 48.4228 | 48.4228 | 0% | 0 | 0% | 0 | 0
| REPB47293 | WINDOWS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47293 | WINDOWS | D | Window: Renew window with purpose made hardwood double hung cased box frame and sashes complete with 2 sashes, factory applied base stain, compressible weatherstripping, glazing beads, ironmongery, remove existing and fix new into prepared opening, bed in mortar, point with sealant, double glazed and make good all finishes, decorate to match existing internally and prepare for redecoration externally, and remove waste and debris. |  |  | 4.42 |  | 3115AA | SM | 21 | 698.79 | 14674.59 | #VALUE! | #VALUE! | 0 | 619.4773 | 13009.024 | SM | 21 | 619.4773 | 13009.024 | 0% | 0 | 0% | 0 | 0
| REPB47293 | SCAFFOLD | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47293 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 245 | 12.92 | 3165.4 | #VALUE! | #VALUE! | 0 | 16.4084 | 4020.058 | M2 | 245 | 16.4084 | 4020.058 | 0% | 0 | 0% | 0 | 0
| REPB47293 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 0% | 0 | 0% | 0 | 0
| REPB47293 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 2 | 50 | 100 | #VALUE! | #VALUE! | 0 | 63.5 | 127 | unit | 2 | 63.5 | 127 | 0% | 0 | 0% | 0 | 0
| REPB47293 | SCAFFOLD | D | Scaffold taken through property (protection to surfaces included) |  |  | 2.16 |  | SC016 | unit | 1 | 379.8 | 379.8 | #VALUE! | #VALUE! | 0 | 482.346 | 482.346 | unit | 1 | 482.346 | 482.346 | 0% | 0 | 0% | 0 | 0
| REPB47293 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB47293 | ESTATE WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47293 | ESTATE WORKS | D | Path: Excavate 250mm below required finished level, remove waste and debris, level and compact bottoms of excavations and fill, 150mm hardcore bed, blinded and ne 100mm concrete trowelled smooth including dishing to gullies and the like and all formwork. |  |  | 7.4 |  | 0030AA | SM | 20 | 58.8 | 1176 | #VALUE! | #VALUE! | 0 | 48.3512 | 967.0248 | SM | 20 | 48.3512 | 967.0248 | 0% | 0 | 0% | 0 | 0
| REPB47293 | ESTATE WORKS | D | Chainlink: Renew chainlink fencing 0.9m high on existing posts, including removal of old and remove from site to approved tip, supply and fix new galvanised or plastic coated steel chainlink wire fencing including three 2.50mm diameter galvanised mild steel line wires and all fittings, ties etc. (measured per metre run of fencing). |  |  | 7.121 |  | 0174AA | LM | 10 | 8.39 | 83.9 | #VALUE! | #VALUE! | 0 | 6.8882 | 68.8819 | LM | 10 | 6.8882 | 68.8819 | 0% | 0 | 0% | 0 | 0
| REPB47293 | ESTATE WORKS | D | Fracture: Remove any applied finish and cut out bricks as necessary to either side of fracture, one face only, stitch in new bricks, bed and point to match existing in cement lime mortar (1:1:6), and make good any applied finishes, and remove waste and debris (measured over mean general line of fracture). |  |  | 7.244 |  | 1019AA | LM | 1 | 44.12 | 44.12 | #VALUE! | #VALUE! | 0 | 31.987 | 31.987 | LM | 1 | 31.987 | 31.987 | 0% | 0 | 0% | 0 | 0
| REPB47293 | ESTATE WORKS | D | Wall: Cut out bricks from face of wall, clean and clear away, lay upto 15 No. new common bricks in cement lime mortar (1:1:6), bond, bed and point to match existing and remove waste and debris. |  |  | 7.245 |  | 1019AB | IT | 13 | 18.93 | 246.09 | #VALUE! | #VALUE! | 0 | 13.7242 | 178.4152 | IT | 13 | 13.7242 | 178.4152 | 0% | 0 | 0% | 0 | 0
| REPB47293 | ESTATE WORKS | D | Wall: Cut out bricks from face of wall, clean and clear away, lay over 15 No. new facing bricks up to 2sm in area in cement lime mortar (1:1:6), bond, bed and point to match existing and remove waste and debris. |  |  | 7.248 |  | 1019BB | IT | 1 | 114.45 | 114.45 | #VALUE! | #VALUE! | 0 | 82.9762 | 82.9762 | IT | 1 | 82.9762 | 82.9762 | 0% | 0 | 0% | 0 | 0
| REPB47293 | ESTATE WORKS | D | Wall: Rake out existing joints of brickwork min 12mm and repoint brickwork in mortar to match existing and remove waste and debris. |  |  | 7.253 |  | 1021AA | SM | 20 | 20.13 | 402.6 | #VALUE! | #VALUE! | 0 | 14.5942 | 291.885 | SM | 20 | 14.5942 | 291.885 | 0% | 0 | 0% | 0 | 0
| REPB47293 | ESTATE WORKS | D | PROVISIONAL SUM: Paving slab: Renew cracked slabs and re-align to attain even surface (SM 4). |  |  | 7.316 |  | PROV SUM | SUM | 1 | 400 | 400 | #VALUE! | 400 |  |  | 400 | SUM | 1 |  | 400 | 0% | 0 | 0% | 0 | 0
| REPB47293 | ESTATE WORKS | D | PROVISIONAL SUM: Timber gate: Renew timber gate leading to the flank (IT 1). |  |  | 7.317 |  | PROV SUM | SUM | 1 | 150 | 150 | #VALUE! | 150 |  |  | 150 | SUM | 1 |  | 150 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | D | Door:Renew front door with any size panelled, glazed or partially glazed or similar proprietary high performance GRP door, prefinished, preglazed, and prehung to and including proprietary door frame and cill, including new mortice lock, door furniture, keeps, pair of bolts, cylinder nightlatch and pull, security restraint device, proprietary letter plate, numerals, proprietary weathermould, fix frame and cill to struycture, seal around frame and cill, make good and remove waste and debris. |  |  | 11 |  | 3221CB | Item | 1 | 1212.5 | 1212.5 | #VALUE! | #VALUE! | 0 | 1074.8812 | 1074.8812 | Item | 1 | 1074.8812 | 1074.8812 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | D | Door:Renew internal door with any size single half-hour fire check glazed door having 3.2mm luan, white Meranti or other approved plywood facing both sides and 9mm hardwood lipping on long edges, including remove existing door and hinges, remove and refit door stops as necessary, fit and hang new door on 1.50 pairs of 100mm steel butt hinges, make good or alter recesses on frame, door complete with all ironmongery, intumescent strips and smoke seals, glazed, redecorate to match existing and remove waste and debris. |  |  | 13 |  | 3300FC | Item | 2 | 222.2 | 444.4 | #VALUE! | #VALUE! | 0 | 196.9803 | 393.9606 | Item | 2 | 196.9803 | 393.9606 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | D | Fire Upgrading Coating:Remove all existing defective paint to plastered or rendered wall surfaces back to a solid edge, feather off and repair any defective areas with a high quality filler as necessary, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, wash down, rinse, clean off and apply one full coat of fire upgrading primer at a coverage rate of 10sm per litre, apply two full coats of fire upgrading finish at a coverage rate of 10sm per litre. |  |  | 27 |  | 4801AB | Item | 1 | 22.53 | 22.53 | #VALUE! | #VALUE! | 0 | 19.1505 | 19.1505 | Item | 1 | 19.1505 | 19.1505 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | D | Fire Upgrading Coating:Strip off existing multi layer paint coatings to existing plastered or rendered soffits with a proprietary paint stripper, scrape off or remove with a proprietary paint scraper, wash down,rinse, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, clean off and apply one full coat of primer at a coverage rate of 10sm per litre, apply one full coats of colourcoat complete with decorative flakes, and apply one full coat of gloss or satin lacquer finish at a coverage rate of 10sm per litre. |  |  | 41 |  | 4804AD | Item | 1 | 29.34 | 29.34 | #VALUE! | #VALUE! | 0 | 24.939 | 24.939 | Item | 1 | 24.939 | 24.939 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | D | Fire Upgrading Coating:Remove all existing defective paint to general surfaces of woodwork not exceeding 300mm girth, back to a solid edge, feather off and repair any defective areas with a high quality filler as necessary, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, wash down, rinse, clean off and apply one full coat of fire upgrading primer at a coverage rate of 10sm per litre, apply two full coats of fire upgrading finish at a coverage rate of 10sm per litre. |  |  | 43 |  | 4805AB | Item | 1 | 20.4 | 20.4 | #VALUE! | #VALUE! | 0 | 17.34 | 17.34 | Item | 1 | 17.34 | 17.34 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | D | Fire Upgrading Coating:Remove all existing defective paint to general surfaces of timber doors back to a solid edge, feather off and repair any defective areas with a high quality filler as necessary, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, wash down, rinse, clean off and apply one full coat of fire upgrading primer at a coverage rate of 10sm per litre, apply two full coats of fire upgrading finish at a coverage rate of 10sm per litre. |  |  | 44 |  | 4805AC | Item | 1 | 35.86 | 35.86 | #VALUE! | #VALUE! | 0 | 30.481 | 30.481 | Item | 1 | 30.481 | 30.481 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | D | Fire Alarm:Install L2 type fire alarm installation complete to BS5839:Part6 1995, control panel, circuits, call points, automatic detectors and sounders, builders work, make good, test, commission, and remove waste and debris. |  |  | 93 |  | 8711GA | Item | 1 | 550 | 550 | #VALUE! | #VALUE! | 0 | 440 | 440 | Item | 1 | 440 | 440 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | D | Intumescent Strip:Renew or supply and fix new 22x4mm intumescent strip, half hour application, with integral cold smoke seal and setting into groove in timber frame or door. |  |  | 104 |  | 3431AC | Item | 2 | 3.44 | 6.88 | #VALUE! | #VALUE! | 0 | 3.0496 | 6.0991 | Item | 2 | 3.0496 | 6.0991 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | D | Smoke Detector:Renew existing with mains operated optical smoke detector with rechargeable DC battery or condensor back up self contained type to BS 5446 kitemark certified with hush button, including back plate and all necessary connections to existing wiring, test and make good on completion, where interlinked detectors are replaced new detectors must be compatible with existing, and remove waste and debris. |  |  | 115 |  | 8720FA | Item | 3 | 70.11 | 210.33 | #VALUE! | #VALUE! | 0 | 56.088 | 168.264 | Item | 3 | 56.088 | 168.264 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | D | Emergency Lighting:Install emergency lighting installation to block of dwellings or scheme, strip out any existing installation and equipment, supply and install self contained non-maintained emergency uminaries and emergency exit signs, connect by specified cable to local lighting circuit, all builders work and make good all works disturbed, test and commission, and remove waste and debris (Per Dwelling in Scheme) |  |  | 126 |  | 8810XA | Item | 1 | 300 | 300 | #VALUE! | #VALUE! | 0 | 240 | 240 | Item | 1 | 240 | 240 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | D |  |  |  | 175 |  | 3905BA | Item | 2 | 9.81 | 19.62 | #VALUE! | #VALUE! | 0 | 8.6966 | 17.3931 | Item | 2 | 8.6966 | 17.3931 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | D | Partition:Supply and erect or renew stud partition comprising ne 50x100mm sole and head plate, noggins and studs fixed with nails or plugged and screwed to walls, and pack out and scribe, 12.5mm butt jointed plasterboard and 3mm plaster skim coat and all labours to both faces. |  |  | 180 |  | 3013AB | Item | 1 | 62.11 | 62.11 | #VALUE! | #VALUE! | 0 | 55.0605 | 55.0605 | Item | 1 | 55.0605 | 55.0605 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | D | Test:Carry out test of domestic installation to occupied property complete comprising continuity, insulation resistance, polarity, earth fault loop impedance and operation of residual current operated device, disconnect, repair and renew as necessary after removal of illegal wiring and components, and provide report and NICEIC/ECA test certificate to the Client’s Representative, and remove waste and debris. |  |  | 186 |  | 8950AA | Item | 1 | 86.88 | 86.88 | #VALUE! | #VALUE! | 0 | 69.504 | 69.504 | Item | 1 | 69.504 | 69.504 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | D | Door and Frame:Renew internal door and frincluding remove existing door, hinges and frame, install 32mm door frame with 25x32mm stops, fit and hang new any size FD30S plywood faced fire check flush door on 1.5 pairs of 100mm steel hinges, make good or alter recesses on frame, door complete with all ironmongery, intumescent strips and smoke seals, make good and prepare door and frame for decoration and remove waste and debris. |  |  | 189 |  | 3300DA | Item | 1 | 152.85 | 152.85 | #VALUE! | #VALUE! | 0 | 135.5015 | 135.5015 | Item | 1 | 135.5015 | 135.5015 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to the fire alarm system. |  |  | 190 |  | PROV SUM | Item | 1 | 1500 | 1500 | #VALUE! | 1500 |  |  | 1500 | Item | 1 |  | 1500 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to clear waste and debris from fire escape routes. |  |  | 191 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional fire stopping works |  |  | 192 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional signage |  |  | 193 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47293 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional electrical works |  |  | 194 |  | PROV SUM | Item | 1 | 350 | 350 | #VALUE! | 350 |  |  | 350 | Item | 1 |  | 350 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 29788.8504 |  |  | TOTAL | 29788.8504 |  | 0 |  | 0 | 0

## 19 Ascham Street
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
19 Ascham Street
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB47025 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB47025 | ENERGY EFFICIENY | H
| REPB47025 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! | 0 | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB47025 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0 | 0
| REPB47025 | ASBESTOS | H | [23 empty] | 0
| REPB47025 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB47025 | COMMUNAL WORKS | H | [23 empty] | 0
| REPB47025 | COMMUNAL WORKS | D | Hall: Thoroughly clean down all wall and ceiling surfaces to common areas to remove dirt, grease and surface containments, scrape and remove all loose and defective coatings, prime bare areas with one coat of fire retardant primer and apply two coats of Class ‘O’ fire retardant matt paint, prepare and apply two coats of polyurethane lacquer or one undercoat and one gloss coat to all previously decorated timber surfaces to lobby, hall or corridor over 3.00sm ceiling area complete (classified as a single area). |  |  | 5.1 |  | 4540AC | IT | 1 | 480 | 480 | #VALUE! | #VALUE! | 0 | 408 | 408 | IT | 1 | 408 | 408 | 0% | 0 | 0% | 0 | 0
| REPB47025 | COMMUNAL WORKS | D | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris. |  |  | 5.24 |  | 4506AB | IT | 1 | 140.12 | 140.12 | #VALUE! | #VALUE! | 0 | 119.102 | 119.102 | IT | 1 | 119.102 | 119.102 | 0% | 0 | 0% | 0 | 0
| REPB47025 | COMMUNAL WORKS | D | Flooring: Take up any covering, clear away, supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to cement and sand screed, or hardboard including all necessary cutting, all labours and clean off, and remove waste and debris. |  |  | 5.14 |  | 4325AA | SM | 4 | 27.96 | 111.84 | #VALUE! | #VALUE! | 0 | 23.5535 | 94.214 | SM | 4 | 23.5535 | 94.214 | 0% | 0 | 0% | 0 | 0
| REPB47025 | COMMUNAL WORKS | D | PROVISIONAL SUM: Surface of papered wall will require a quote of paint. |  |  | 5.386 |  | PROV SUM | SUM | 1 | 300 | 300 | #VALUE! | 300 |  |  | 300 | SUM | 1 |  | 300 | 0% | 0 | 0% | 0 | 0
| REPB47025 | EXTREP | H | [23 empty] | 0
| REPB47025 | EXTREP | D | Moulding Repairs 0-5no. per property Fosroc repair mortar or equivalent Insitu repairs using straight edge to form moulding repair. (Girth NE300mm Length NE300mm) |  |  | 6.11 |  | FAB071 | no | 1 | 79.14 | 79.14 | #VALUE! | #VALUE! | 0 | 63.312 | 63.312 | no | 1 | 63.312 | 63.312 | 0% | 0 | 0% | 0 | 0
| REPB47025 | EXTREP | D | Fracture: Remove any applied finish and cut out bricks as necessary to either side of fracture, one face only, stitch in new bricks, bed and point to match existing in cement lime mortar (1:1:6), and make good any applied finishes, and remove waste and debris (measured over mean general line of fracture). |  |  | 6.82 |  | 1019AA | LM | 12 | 44.12 | 529.44 | #VALUE! | #VALUE! | 0 | 31.987 | 383.844 | LM | 12 | 31.987 | 383.844 | 0% | 0 | 0% | 0 | 0
| REPB47025 | EXTREP | D | Cills: Prepare, clean off all dust and debris, fill in or resurface cracks or spalled surfaces of concrete with epoxy mortar in surfaces of cills, not exceeding 300mm girth, repair over 5 and ne 10mm deep, and remove waste and debris. |  |  | 6.161 |  | 1460AF | LM | 10 | 38.25 | 382.5 | #VALUE! | #VALUE! | 0 | 27.7312 | 277.3125 | LM | 10 | 27.7312 | 277.3125 | 0% | 0 | 0% | 0 | 0
| REPB47025 | EXTREP | D | Walls: Wash down, fill in cracks and holes, sand down and apply one coat of stabilising solution and two coats of smooth or textured masonry paint to rendered or concrete walls. |  |  | 6.185 |  | 4356BC | SM | 25 | 11.01 | 275.25 | #VALUE! | #VALUE! | 0 | 9.3585 | 233.9625 | SM | 25 | 9.3585 | 233.9625 | 0% | 0 | 0% | 0 | 0
| REPB47025 | EXTREP | D | Pipework: Wire brush, prepare for and apply one undercoat and two coats of gloss paint to existing painted surfaces of external pipework ne 300mm girth including brackets. |  |  | 6.218 |  | 4363HA | LM | 15 | 1.73 | 25.95 | #VALUE! | #VALUE! | 0 | 1.4705 | 22.0575 | LM | 15 | 1.4705 | 22.0575 | 0% | 0 | 0% | 0 | 0
| REPB47025 | EXTREP | D | Fascias, soffits, Bargeboards and the like:Rub down, prepare for, and apply one undercoat, two coats of gloss paint on existing painted surfaces of facias, soffits, bargeboards and the like ne 300mm girth. |  |  | 6.26 |  | 4381HB | LM | 4 | 3.74 | 14.96 | #VALUE! | #VALUE! | 0 | 3.179 | 12.716 | LM | 4 | 3.179 | 12.716 | 0% | 0 | 0% | 0 | 0
| REPB47025 | EXTREP | D | Window: Rub down, prepare and apply one undercoat and one coat of gloss paint on existing painted surfaces of wooden windows (one side and edges). |  |  | 6.262 |  | 4381JB | SM | 15 | 16.86 | 252.9 | #VALUE! | #VALUE! | 0 | 14.331 | 214.965 | SM | 15 | 14.331 | 214.965 | 0% | 0 | 0% | 0 | 0
| REPB47025 | EXTREP | D | Door: Rub down, prepare for and apply one undercoat and one coat of gloss paint to all existing painted surfaces of any size or type of single glazed timber door (both sides and edges). |  |  | 6.265 |  | 4381LB | IT | 2 | 19.34 | 38.68 | #VALUE! | #VALUE! | 0 | 16.439 | 32.878 | IT | 2 | 16.439 | 32.878 | 0% | 0 | 0% | 0 | 0
| REPB47025 | EXTREP | D | Door: Rub down, prepare for, and apply three coats decorative wood stain on external surfaces of any size/type of single door(both sides and edges) |  |  | 6.276 |  | 4382DB | IT | 1 | 33.52 | 33.52 | #VALUE! | #VALUE! | 0 | 28.492 | 28.492 | IT | 1 | 28.492 | 28.492 | 0% | 0 | 0% | 0 | 0
| REPB47025 | EXTREP | D | Render Repairs: Repair crack in any external render including carefully hack out and make good with cement and sand including applying finish to match existing, and remove waste and debris. |  |  | 6.306 |  | 4230ZA | LM | 25 | 6.87 | 171.75 | #VALUE! | #VALUE! | 0 | 4.9807 | 124.5187 | LM | 25 | 4.9807 | 124.5187 | 0% | 0 | 0% | 0 | 0
| REPB47025 | EXTREP | D | PROVISIONAL SUM: Rub down, prepare, spot prime and apply one undercoat and one coat of gloss paint on existing painted general surfaces of woodwork. 4 no |  |  | 6.399 |  | PROV SUM | SUM | 1 | 200 | 200 | #VALUE! | 200 |  |  | 200 | SUM | 1 |  | 200 | 0% | 0 | 0% | 0 | 0
| REPB47025 | ROOF | H | [23 empty] | 0
| REPB47025 | ROOF | D | Fascia/Soffit/Barge: Refix any size fascia, soffit or bargeboard to existing roof timbers including remove/refix rainwater goods and cabling as necessary, renewal of support battens, all cutting and packing and prepare for redecoration. |  |  | 3.63 |  | 3030HA | LM | 4 | 11.87 | 47.48 | #VALUE! | #VALUE! | 0 | 10.5228 | 42.091 | LM | 4 | 10.5228 | 42.091 | 0% | 0 | 0% | 0 | 0
| REPB47025 | ROOF | D | Moss: Carefully remove moss/lichen growth on roof covering of any kind and dispose of debris off site, reistate all disturbed surfaces, replace broken tiles, slates and the like, thoroughly clean out valleys, gutters, downpipes, hoppers etc, prepare and treat the complete roof area with a diluted fungicide solution AKZO or other equal and approved applied strictly in accordance with the manufacturer’s instructions, thoroughly clean out all gutters and the like to remove all chemical residue arising upon completion of the works, and remove waste and debris. |  |  | 3.18 |  | 2115AA | SM | 70 | 10.17 | 711.9 | #VALUE! | #VALUE! | 0 | 8.136 | 569.52 | SM | 70 | 8.136 | 569.52 | 0% | 0 | 0% | 0 | 0
| REPB47025 | ROOF | D | Secret Gutter: Clear debris and clean down large secret lead or copper gutter or valley, remove waste and debis |  |  | 3.189 |  | 2250CA | LM | 10 | 5.58 | 55.8 | #VALUE! | #VALUE! | 0 | 4.464 | 44.64 | LM | 10 | 4.464 | 44.64 | 0% | 0 | 0% | 0 | 0
| REPB47025 | ROOF | D | Downpipe: Renew ne 76.5mm cast aluminium downpipe complete to ne 2 storey dwelling with new brackets plugged and screwed to brickwork and all necessary branches, offset projections, hopperheads, shoe, terminal and slate if necessary, cut and make all joints, make good to structure and finishes and prepare for redecoration, and remove waste and debris. |  |  | 3.298 |  | 6013AA | IT | 1 | 148.48 | 148.48 | #VALUE! | #VALUE! | 0 | 110.0385 | 110.0385 | IT | 1 | 110.0385 | 110.0385 | 0% | 0 | 0% | 0 | 0
| REPB47025 | ROOF | D | Gutter: Take down any PVCu gutter, remove and refix brackets to fascia and refix gutter to brackets to line and level including all angles, outlets and stop ends and remake all joints. |  |  | 3.324 |  | 6031CA | LM | 5 | 7.33 | 36.65 | #VALUE! | #VALUE! | 0 | 5.4323 | 27.1613 | LM | 5 | 5.4323 | 27.1613 | 0% | 0 | 0% | 0 | 0
| REPB47025 | ROOF | D | PROVISIONAL SUM: Clear rainwater downpipes. |  |  | 3.434 |  | PROV SUM | SUM | 1 | 150 | 150 | #VALUE! | 150 |  |  | 150 | SUM | 1 |  | 150 | 0% | 0 | 0% | 0 | 0
| REPB47025 | ROOF | D | PROVISIONAL SUM: Allow for unforseen roof repairs. |  |  | 3.435 |  | PROV SUM | SUM | 1 | 500 | 500 | #VALUE! | 500 |  |  | 500 | SUM | 1 |  | 500 | 0% | 0 | 0% | 0 | 0
| REPB47025 | WINDOWS | H | [23 empty] | 0
| REPB47025 | WINDOWS | D | 7. Timber repair system; using window care dry fix/dry flex RP; Conservation Joint; up to 100mm |  |  | 4.14 |  | WIND023 | Nr | 15 | 6.75 | 101.25 | #VALUE! | #VALUE! | 0 | 6.4125 | 96.1875 | Nr | 15 | 6.4125 | 96.1875 | 0% | 0 | 0% | 0 | 0
| REPB47025 | WINDOWS | D | Window: Overhaul timber casement window, dismantle as necessary and subsequently reassemble including freeing, easing and adjusting casements to give correct operation, renew sealing gaskets, renew fixing screws, remove, refit or renew ironmongery as necessary, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.89 |  | 3150BA | NO | 5 | 29.05 | 145.25 | #VALUE! | #VALUE! | 0 | 25.7528 | 128.7641 | NO | 5 | 25.7528 | 128.7641 | 0% | 0 | 0% | 0 | 0
| REPB47025 | WINDOWS | D | Window: Overhaul timber sash window, renew staff and parting beads, take out sashes and later rehang on appropriate sized new undyed plaited nylon sash cords, renew pocket pieces, wedge and cramp loose sash frames, oil pulleys, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.9 |  | 3150CA | NO | 10 | 35.61 | 356.1 | #VALUE! | #VALUE! | 0 | 31.5683 | 315.6826 | NO | 10 | 31.5683 | 315.6826 | 0% | 0 | 0% | 0 | 0
| REPB47025 | SCAFFOLD | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47025 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 100 | 12.92 | 1292 | #VALUE! | #VALUE! | 0 | 16.4084 | 1640.84 | M2 | 100 | 16.4084 | 1640.84 | 0% | 0 | 0% | 0 | 0
| REPB47025 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 0% | 0 | 0% | 0 | 0
| REPB47025 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 1 | 50 | 50 | #VALUE! | #VALUE! | 0 | 63.5 | 63.5 | unit | 1 | 63.5 | 63.5 | 0% | 0 | 0% | 0 | 0
| REPB47025 | SCAFFOLD | D | Scaffold taken through property (protection to surfaces included) |  |  | 2.16 |  | SC016 | unit | 1 | 379.8 | 379.8 | #VALUE! | #VALUE! | 0 | 482.346 | 482.346 | unit | 1 | 482.346 | 482.346 | 0% | 0 | 0% | 0 | 0
| REPB47025 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB47025 | ESTATE WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47025 | ESTATE WORKS | D | Fracture: Remove any applied finish and cut out bricks as necessary to either side of fracture, one face only, stitch in new bricks, bed and point to match existing in cement lime mortar (1:1:6), and make good any applied finishes, and remove waste and debris (measured over mean general line of fracture). |  |  | 7.244 |  | 1019AA | LM | 17 | 44.12 | 750.04 | #VALUE! | #VALUE! | 0 | 31.987 | 543.779 | LM | 17 | 31.987 | 543.779 | 0% | 0 | 0% | 0 | 0
| REPB47025 | ESTATE WORKS | D | PROVISIONAL SUM: Repair and treat concrete stair cracks. IT 1no. |  |  | 7.316 |  | PROV SUM | SUM | 1 | 200 | 200 | #VALUE! | 200 |  |  | 200 | SUM | 1 |  | 200 | 0% | 0 | 0% | 0 | 0
| REPB47025 | ESTATE WORKS | D | PROVISIONAL SUM: Repair or renew concrete ground paving with cracks at front elevation. SM 30 |  |  | 7.317 |  | PROV SUM | SUM | 1 | 800 | 800 | #VALUE! | 800 |  |  | 800 | SUM | 1 |  | 800 | 0% | 0 | 0% | 0 | 0
| REPB47025 | ESTATE WORKS | D | PROVISIONAL SUM: Renew cast concrete floor at rear of property. SM 30 |  |  | 7.318 |  | PROV SUM | SUM | 1 | 800 | 800 | #VALUE! | 800 |  |  | 800 | SUM | 1 |  | 800 | 0% | 0 | 0% | 0 | 0
| REPB47025 | FRA WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47025 | FRA WORKS | D | Door:Renew internal door with any size single half-hour fire check glazed door having 3.2mm luan, white Meranti or other approved plywood facing both sides and 9mm hardwood lipping on long edges, including remove existing door and hinges, remove and refit door stops as necessary, fit and hang new door on 1.50 pairs of 100mm steel butt hinges, make good or alter recesses on frame, door complete with all ironmongery, intumescent strips and smoke seals, glazed, redecorate to match existing and remove waste and debris. |  |  | 13 |  | 3300FC | Item | 2 | 222.2 | 444.4 | #VALUE! | #VALUE! | 0 | 196.9803 | 393.9606 | Item | 2 | 196.9803 | 393.9606 | 0% | 0 | 0% | 0 | 0
| REPB47025 | FRA WORKS | D | Fire Upgrading Coating:Remove all existing defective paint to plastered or rendered wall surfaces back to a solid edge, feather off and repair any defective areas with a high quality filler as necessary, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, wash down, rinse, clean off and apply one full coat of fire upgrading primer at a coverage rate of 10sm per litre, apply two full coats of fire upgrading finish at a coverage rate of 10sm per litre. |  |  | 27 |  | 4801AB | Item | 1 | 22.53 | 22.53 | #VALUE! | #VALUE! | 0 | 19.1505 | 19.1505 | Item | 1 | 19.1505 | 19.1505 | 0% | 0 | 0% | 0 | 0
| REPB47025 | FRA WORKS | D | Fire Upgrading Coating:Strip off existing multi layer paint coatings to existing plastered or rendered soffits with a proprietary paint stripper, scrape off or remove with a proprietary paint scraper, wash down,rinse, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, clean off and apply one full coat of primer at a coverage rate of 10sm per litre, apply one full coats of colourcoat complete with decorative flakes, and apply one full coat of gloss or satin lacquer finish at a coverage rate of 10sm per litre. |  |  | 41 |  | 4804AD | Item | 1 | 29.34 | 29.34 | #VALUE! | #VALUE! | 0 | 24.939 | 24.939 | Item | 1 | 24.939 | 24.939 | 0% | 0 | 0% | 0 | 0
| REPB47025 | FRA WORKS | D |  |  |  | 104 |  | 3431AC | Item | 2 | 3.44 | 6.88 | #VALUE! | #VALUE! | 0 | 3.0496 | 6.0991 | Item | 2 | 3.0496 | 6.0991 | 0% | 0 | 0% | 0 | 0
| REPB47025 | FRA WORKS | D | Smoke Detector:Renew existing with mains operated optical smoke detector with rechargeable DC battery or condensor back up self contained type to BS 5446 kitemark certified with hush button, including back plate and all necessary connections to existing wiring, test and make good on completion, where interlinked detectors are replaced new detectors must be compatible with existing, and remove waste and debris. |  |  | 115 |  | 8720FA | Item | 2 | 70.11 | 140.22 | #VALUE! | #VALUE! | 0 | 56.088 | 112.176 | Item | 2 | 56.088 | 112.176 | 0% | 0 | 0% | 0 | 0
| REPB47025 | FRA WORKS | D | Partition:Supply and erect or renew stud partition comprising ne 50x100mm sole and head plate, noggins and studs fixed with nails or plugged and screwed to walls, and pack out and scribe, 12.5mm butt jointed plasterboard and 3mm plaster skim coat and all labours to both faces. |  |  | 180 |  | 3013AB | Item | 1 | 62.11 | 62.11 | #VALUE! | #VALUE! | 0 | 55.0605 | 55.0605 | Item | 1 | 55.0605 | 55.0605 | 0% | 0 | 0% | 0 | 0
| REPB47025 | FRA WORKS | D | Test:Carry out test of domestic installation to occupied property complete comprising continuity, insulation resistance, polarity, earth fault loop impedance and operation of residual current operated device, disconnect, repair and renew as necessary after removal of illegal wiring and components, and provide report and NICEIC/ECA test certificate to the Client’s Representative, and remove waste and debris. |  |  | 186 |  | 8950AA | Item | 1 | 86.88 | 86.88 | #VALUE! | #VALUE! | 0 | 69.504 | 69.504 | Item | 1 | 69.504 | 69.504 | 0% | 0 | 0% | 0 | 0
| REPB47025 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to the fire alarm system. |  |  | 190 |  | PROV SUM | Item | 1 | 1500 | 1500 | #VALUE! | 1500 |  |  | 1500 | Item | 1 |  | 1500 | 0% | 0 | 0% | 0 | 0
| REPB47025 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to clear waste and debris from fire escape routes. |  |  | 191 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47025 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional fire stopping works |  |  | 192 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47025 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional signage |  |  | 193 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47025 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional electrical works |  |  | 194 |  | PROV SUM | Item | 1 | 350 | 350 | #VALUE! | 350 |  |  | 350 | Item | 1 |  | 350 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 13016.5097 |  |  | TOTAL | 13016.5097 |  | 0 |  | 0 | 0

## 66 Leverton Street
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
66 Leverton Street
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB47684 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB47684 | ENERGY EFFICIENY | H
| REPB47684 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! | 0 | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB47684 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0 | 0
| REPB47684 | ASBESTOS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47684 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB47684 | COMMUNAL WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47684 | COMMUNAL WORKS | D | Hall: Thoroughly clean down all wall and ceiling surfaces to common areas to remove dirt, grease and surface containments, scrape and remove all loose and defective coatings, prime bare areas with one coat of fire retardant primer and apply two coats of Class ‘O’ fire retardant matt paint, prepare and apply two coats of polyurethane lacquer or one undercoat and one gloss coat to all previously decorated timber surfaces to lobby, hall or corridor over 3.00sm ceiling area complete (classified as a single area). |  |  | 5.1 |  | 4540AC | IT | 1 | 480 | 480 | #VALUE! | #VALUE! | 0 | 408 | 408 | IT | 1 | 408 | 408 | 0% | 0 | 0% | 0 | 0
| REPB47684 | COMMUNAL WORKS | D | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris. |  |  | 5.135 |  | 4323BA | SM | 4 | 21.11 | 84.44 | #VALUE! | #VALUE! | 0 | 17.7831 | 71.1323 | SM | 4 | 17.7831 | 71.1323 | 0% | 0 | 0% | 0 | 0
| REPB47684 | EXTREP | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47684 | EXTREP | D | Wall: Rake out existing joints of brickwork min 12mm and repoint brickwork in mortar to match existing and remove waste and debris. |  |  | 6.91 |  | 1021AA | SM | 4 | 20.13 | 80.52 | #VALUE! | #VALUE! | 0 | 14.5942 | 58.377 | SM | 4 | 14.5942 | 58.377 | 0% | 0 | 0% | 0 | 0
| REPB47684 | EXTREP | D | Walls:Wash down, fill in cracks and holes, sand down and apply one coat of stabilising solution and two coats of smooth or textured masonry paint to brickwork surfaces of walls. |  |  | 6.186 |  | 4356BD | SM | 6 | 11.63 | 69.78 | #VALUE! | #VALUE! | 0 | 9.8855 | 59.313 | SM | 6 | 9.8855 | 59.313 | 0% | 0 | 0% | 0 | 0
| REPB47684 | EXTREP | D | Gates:Rub down, prepare for, and apply one undercoat, two coats of gloss paint on existing painted surfaces of gates and posts (measured both sides). |  |  | 6.258 |  | 4381FA | SM | 1 | 12.41 | 12.41 | #VALUE! | #VALUE! | 0 | 10.5485 | 10.5485 | SM | 1 | 10.5485 | 10.5485 | 0% | 0 | 0% | 0 | 0
| REPB47684 | EXTREP | D | Window:Rub down, prepare and apply one undercoat and one coat of gloss paint on existing painted surfaces of wooden windows (one side and edges). |  |  | 6.262 |  | 4381JB | SM | 20 | 16.86 | 337.2 | #VALUE! | #VALUE! | 0 | 14.331 | 286.62 | SM | 20 | 14.331 | 286.62 | 0% | 0 | 0% | 0 | 0
| REPB47684 | EXTREP | D | Frame:Rub down, prepare and apply one undercoat and one coat of gloss paint on existing painted timber frame ne 300mm girth. |  |  | 6.263 |  | 4381KA | LM | 42 | 3.81 | 160.02 | #VALUE! | #VALUE! | 0 | 3.2385 | 136.017 | LM | 42 | 3.2385 | 136.017 | 0% | 0 | 0% | 0 | 0
| REPB47684 | EXTREP | D | Door:Rub down, prepare for and apply one undercoat and one coat of gloss paint to all existing painted surfaces of any size or type of single glazed timber door (one sides and edges). |  |  | 6.264 |  | 4381LA | IT | 2 | 9.67 | 19.34 | #VALUE! | #VALUE! | 0 | 8.2195 | 16.439 | IT | 2 | 8.2195 | 16.439 | 0% | 0 | 0% | 0 | 0
| REPB47684 | EXTREP | D | Provisional Sum Lintel: Cut out and remove existing lintol from brick wall, prepare to receive new including all necessary propping and temporary supports, and supply and fix new stone lintol. |  |  | 6.399 |  | PROV SUM | SUM | 1 | 500 | 500 | #VALUE! | 500 |  |  | 500 | SUM | 1 |  | 500 | 0% | 0 | 0% | 0 | 0
| REPB47684 | ROOF | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47684 | ROOF | D | Slate:Renew any size and type of natural roof slates including double course at eaves cloaked verges, ridge, hips and valley tiles, supply and install proprietary ventilation units in roof, renew all code 6 lead flashings, aprons chimney gutters and the like wedged and pointed, renew valley gutter and valley board as necessary including all labours, cutting etc including renew roofing felt and battens and install restraint straps togables and elevational gables, install ‘glidevale’ secret gutter to abutment to adjacent property, and remove waste and debris. |  |  | 3.22 |  | 2034AD | SM | 40 | 138.28 | 5531.2 | #VALUE! | #VALUE! | 0 | 110.624 | 4424.96 | SM | 40 | 110.624 | 4424.96 | 0% | 0 | 0% | 0 | 0
| REPB47684 | WINDOWS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47684 | WINDOWS | D | Window: Renew window with purpose made hardwood double hung cased box frame and sashes complete with 2 sashes, factory applied base stain, compressible weatherstripping, glazing beads, ironmongery, remove existing and fix new into prepared opening, bed in mortar, point with sealant, double glazed and make good all finishes, decorate to match existing internally and prepare for redecoration externally, and remove waste and debris. |  |  | 4.42 |  | 3115AA | SM | 3 | 698.79 | 2096.37 | #VALUE! | #VALUE! | 0 | 619.4773 | 1858.432 | SM | 3 | 619.4773 | 1858.432 | 0% | 0 | 0% | 0 | 0
| REPB47684 | WINDOWS | D | Window: Overhaul sash window, renew staff and parting beads, take out sashes and later rehang on spiral sash balances, renew pocket pieces, wedge and cramp loose sash frames, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.91 |  | 3150CB | NO | 7 | 98.99 | 692.93 | #VALUE! | #VALUE! | 0 | 87.7546 | 614.2824 | NO | 7 | 87.7546 | 614.2824 | 0% | 0 | 0% | 0 | 0
| REPB47684 | WINDOWS | D | Window: Check operation of all fittings and operating mechanisms to PVCu window complete including lubricate and adjust as necessary. |  |  | 4.115 |  | 3181AH | IT | 2 | 4.81 | 9.62 | #VALUE! | #VALUE! | 0 | 4.2641 | 8.5281 | IT | 2 | 4.2641 | 8.5281 | 0% | 0 | 0% | 0 | 0
| REPB47684 | WINDOWS | D | Window: Overhaul any type of PVCu window, dismantle as necessary and subsequently reassemble including freeing, easing and adjusting casements to give correct operation, renew fixing screws, remove, refit or renew ironmongery as necessary, check, lubricate operating mechanism, renew gaskets, make good and test. |  |  | 4.129 |  | 3181BA | NO | 2 | 28.43 | 56.86 | #VALUE! | #VALUE! | 0 | 25.2032 | 50.4064 | NO | 2 | 25.2032 | 50.4064 | 0% | 0 | 0% | 0 | 0
| REPB47684 | SCAFFOLD | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47684 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 117 | 12.92 | 1511.64 | #VALUE! | #VALUE! | 0 | 16.4084 | 1919.7828 | M2 | 117 | 16.4084 | 1919.7828 | 80% | 1535.8262 | 0% | 0 | 1535.8262
| REPB47684 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 80% | 426.72 | 0% | 0 | 426.72
| REPB47684 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 1 | 50 | 50 | #VALUE! | #VALUE! | 0 | 63.5 | 63.5 | unit | 1 | 63.5 | 63.5 | 80% | 50.8 | 0% | 0 | 50.8
| REPB47684 | SCAFFOLD | D | Scaffold taken up&over the roof |  |  | 2.17 |  | SC017 | unit | 1 | 842 | 842 | #VALUE! | #VALUE! | 0 | 1069.34 | 1069.34 | unit | 1 | 1069.34 | 1069.34 | 80% | 855.472 | 0% | 0 | 855.472
| REPB47684 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB47684 | ESTATE WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47684 | ESTATE WORKS | D | Path:Excavate 250mm below required finished level, remove waste and debris, level and compact bottoms of excavations and fill, 150mm hardcore bed, blinded and ne 100mm concrete trowelled smooth including dishing to gullies and the like and all formwork. |  |  | 7.4 |  | 0030AA | SM | 16 | 58.8 | 940.8 | #VALUE! | #VALUE! | 0 | 48.3512 | 773.6198 | SM | 16 | 48.3512 | 773.6198 | 0% | 0 | 0% | 0 | 0
| REPB47684 | ESTATE WORKS | D | Wall: Demolish as necessary, clean off and clear away, rebuild one and a half brick wall in common bricks, bed and point in cement lime mortar (1:1:6) to match existing and remove waste and debris. |  |  | 7.217 |  | 1015AC | SM | 31 | 169.05 | 5240.55 | #VALUE! | #VALUE! | 0 | 122.5613 | 3799.3987 | SM | 31 | 122.5613 | 3799.3987 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 17284.3926 |  |  | TOTAL | 17284.3926 |  | 2868.8182 |  | 0 | 2868.8182

## 13 Oseney Street
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
13 Oseney Street
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB47732 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB47732 | ENERGY EFFICIENY | H
| REPB47732 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! | 0 | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB47732 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0 | 0
| REPB47732 | ASBESTOS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47732 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB47732 | COMMUNAL WORKS | H | [23 empty] | 0
| REPB47732 | COMMUNAL WORKS | D | PROVISIONAL SUM: Hall Stairs: Thoroughly clean down all wall and ceiling surfaces to common areas to remove dirt, grease and surface containments, scrape and remove all loose and defective coatings, prime bare areas with one coat of fire retardant primer and apply two coats of Class ‘O’ fire retardant matt paint, prepare and apply two coats of polyurethane lacquer or one undercoat and one gloss coat to all previously decorated timber surfaces to hall, landing and staircase areas complete (2 storey) (classified as a single area). |  |  | 5.388 |  | PROV SUM | SUM | 1 | 900 | 900 | #VALUE! | 900 |  |  | 900 | SUM | 1 |  | 900 | 0% | 0 | 0% | 0 | 0
| REPB47732 | COMMUNAL WORKS | D | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris. |  |  | 5.389 |  | PROV SUM | SUM | 1 | 500 | 500 | #VALUE! | 500 |  |  | 500 | SUM | 1 |  | 500 | 0% | 0 | 0% | 0 | 0
| REPB47732 | EXTREP | H | [23 empty] | 0
| REPB47732 | EXTREP | D | Wall: Rake out existing joints of brickwork min 12mm and repoint brickwork in mortar to match existing and remove waste and debris. |  |  | 6.91 |  | 1021AA | SM | 2 | 20.13 | 40.26 | #VALUE! | #VALUE! | 0 | 14.5942 | 29.1885 | SM | 2 | 14.5942 | 29.1885 | 0% | 0 | 0% | 0 | 0
| REPB47732 | EXTREP | D | Walls: Wash down, fill in cracks and holes, sand smooth and apply two coats of smooth finish masonry paint to rendered or concrete surfaces of walls. |  |  | 6.194 |  | 4360BA | SM | 60 | 7.02 | 421.2 | #VALUE! | #VALUE! | 0 | 5.967 | 358.02 | SM | 60 | 5.967 | 358.02 | 0% | 0 | 0% | 0 | 0
| REPB47732 | EXTREP | D | Gates: Wire brush, prepare for and apply one undercoat and two coats of gloss paint to both sides of existing painted surface of any size/type single metal gate including all edges and all surfaces of posts. |  |  | 6.214 |  | 4363DA | IT | 1 | 16.98 | 16.98 | #VALUE! | #VALUE! | 0 | 14.433 | 14.433 | IT | 1 | 14.433 | 14.433 | 0% | 0 | 0% | 0 | 0
| REPB47732 | EXTREP | D | Balustrading: Wire brush, prepare for and apply one undercoat and two coats of gloss paint on existing painted surfaces ornamental metal balustrading, railings or gates (measured both sides). |  |  | 6.215 |  | 4363EA | SM | 1 | 16.08 | 16.08 | #VALUE! | #VALUE! | 0 | 13.668 | 13.668 | SM | 1 | 13.668 | 13.668 | 0% | 0 | 0% | 0 | 0
| REPB47732 | EXTREP | D | Pipework: Wire brush, prepare for and apply one undercoat and two coats of gloss paint to existing painted surfaces of external pipework ne 300mm girth including brackets. |  |  | 6.218 |  | 4363HA | LM | 12 | 1.73 | 20.76 | #VALUE! | #VALUE! | 0 | 1.4705 | 17.646 | LM | 12 | 1.4705 | 17.646 | 0% | 0 | 0% | 0 | 0
| REPB47732 | EXTREP | D | Window: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on surfaces of wooden windowsl (one side and edges). |  |  | 6.236 |  | 4380BA | SM | 18 | 25.87 | 465.66 | #VALUE! | #VALUE! | 0 | 21.9895 | 395.811 | SM | 18 | 21.9895 | 395.811 | 0% | 0 | 0% | 0 | 0
| REPB47732 | EXTREP | D | Frame: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on timber frame ne 300mm girth. |  |  | 6.237 |  | 4380CA | LM | 6 | 6.28 | 37.68 | #VALUE! | #VALUE! | 0 | 5.338 | 32.028 | LM | 6 | 5.338 | 32.028 | 0% | 0 | 0% | 0 | 0
| REPB47732 | EXTREP | D | Door: Rub down, prepare for and apply one coat of primer, one undercoat and two coats of gloss paint to all surfaces of any size or type of single glazed timber door. (one sides and edges). |  |  | 6.238 |  | 4380DA | IT | 1 | 20.71 | 20.71 | #VALUE! | #VALUE! | 0 | 17.6035 | 17.6035 | IT | 1 | 17.6035 | 17.6035 | 0% | 0 | 0% | 0 | 0
| REPB47732 | EXTREP | D | Fascias, soffits, Bargeboards and the like: Rub down, prepare for, and apply one undercoat, two coats of gloss paint on existing painted surfaces of facias, soffits, bargeboards and the like ne 300mm girth. |  |  | 6.26 |  | 4381HB | LM | 6 | 3.74 | 22.44 | #VALUE! | #VALUE! | 0 | 3.179 | 19.074 | LM | 6 | 3.179 | 19.074 | 0% | 0 | 0% | 0 | 0
| REPB47732 | EXTREP | D | PROVISIONAL SUM: Decorative Mouldings (Multifaceted) using the Fosroc HB and Fosroc FC repair mortar systems Girth NE150mm Length EX 500mm |  |  | 6.399 |  | PROV SUM | SUM | 1 | 200 | 200 | #VALUE! | 200 |  |  | 200 | SUM | 1 |  | 200 | 0% | 0 | 0% | 0 | 0
| REPB47732 | EXTREP | D | PROVISIONAL SUM: Wall: Rake out existing joints of brickwork min 12mm and repoint brickwork in mortar to match existing and remove waste and debris. |  |  | 6.4 |  | PROV SUM | SUM | 1 | 40 | 40 | #VALUE! | 40 |  |  | 40 | SUM | 1 |  | 40 | 0% | 0 | 0% | 0 | 0
| REPB47732 | EXTREP | D | PROVISIONAL SUM: Walls: Wash down, fill in cracks and holes, sand smooth and apply two coats of smooth finish masonry paint to rendered or concrete surfaces of walls. |  |  | 6.401 |  | PROV SUM | SUM | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | SUM | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47732 | EXTREP | D | PROVISIONAL SUM: Pipework: Wire brush, prepare for and apply one undercoat and two coats of gloss paint to existing painted surfaces of external pipework ne 300mm girth including brackets. |  |  | 6.402 |  | PROV SUM | SUM | 1 | 20 | 20 | #VALUE! | 20 |  |  | 20 | SUM | 1 |  | 20 | 0% | 0 | 0% | 0 | 0
| REPB47732 | EXTREP | D | PROVISIONAL SUM: Window:Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on surfaces of wooden windowsl (one side and edges). |  |  | 6.403 |  | PROV SUM | SUM | 1 | 400 | 400 | #VALUE! | 400 |  |  | 400 | SUM | 1 |  | 400 | 0% | 0 | 0% | 0 | 0
| REPB47732 | EXTREP | D | PROVISIONAL SUM: Frame: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on timber frame ne 300mm girth. |  |  | 6.404 |  | PROV SUM | SUM | 1 | 70 | 70 | #VALUE! | 70 |  |  | 70 | SUM | 1 |  | 70 | 0% | 0 | 0% | 0 | 0
| REPB47732 | EXTREP | D | PROVISIONAL SUM: Door: Rub down, prepare for and apply one coat of primer, one undercoat and two coats of gloss paint to all surfaces of any size or type of single glazed timber door. (one sides and edges). |  |  | 6.405 |  | PROV SUM | SUM | 1 | 40 | 40 | #VALUE! | 40 |  |  | 40 | SUM | 1 |  | 40 | 0% | 0 | 0% | 0 | 0
| REPB47732 | EXTREP | D | PROVISIONAL SUM: Fascias, soffits, Bargeboards and the like: Rub down, prepare for, and apply one undercoat, two coats of gloss paint on existing painted surfaces of facias, soffits, bargeboards and the like ne 300mm girth. |  |  | 6.406 |  | PROV SUM | SUM | 1 | 20 | 20 | #VALUE! | 20 |  |  | 20 | SUM | 1 |  | 20 | 0% | 0 | 0% | 0 | 0
| REPB47732 | ROOF | H | [19 empty] | 0% | 0 | 0% | 0 | 0
| REPB47732 | ROOF | D | PROVISIONAL SUM: Overlay with BAUDER Bauderflex System or equivalent inclusive of 15 year guarantee. Voids 1m2 to be deducted Overlay existing mineral surfaced felt with 2 layer torch-on built up felt roofing (including preparation). Up to 100 m2* |  |  | 3.434 |  | PROV SUM | SUM | 1 | 1100 | 1100 | #VALUE! | 1100 |  |  | 1100 | SUM | 1 |  | 1100 | 0% | 0 | 0% | 0 | 0
| REPB47732 | ROOF | D | PROVISIONAL SUM: Slate: Overhaul natural slate roof, refix loose slates, renew broken or missing slates to match existing, redress, rewedge and repoint all flashings, aprons, chimney gutters etc, cut out and make good cement weather fillets, repoint in cement mortar (1:3) to all hips, ridges and verges, make good, and remove waste and debris. |  |  | 3.435 |  | PROV SUM | SUM | 1 | 1400 | 1400 | #VALUE! | 1400 |  |  | 1400 | SUM | 1 |  | 1400 | 0% | 0 | 0% | 0 | 0
| REPB47732 | ROOF | D | PROVISIONAL SUM: Roof Covering: Extra over any renewal or refixing of natural slates for renew roofing felt and battens. |  |  | 3.436 |  | PROV SUM | SUM | 1 | 200 | 200 | #VALUE! | 200 |  |  | 200 | SUM | 1 |  | 200 | 0% | 0 | 0% | 0 | 0
| REPB47732 | ROOF | D | PROVISIONAL SUM: Gutter: Clean out debris from gutters to any type of property including flush out and test, rod downpipe including clean out gulley and remove debris from site on completion (per elevation). |  |  | 3.437 |  | PROV SUM | SUM | 1 | 250 | 250 | #VALUE! | 250 |  |  | 250 | SUM | 1 |  | 250 | 0% | 0 | 0% | 0 | 0
| REPB47732 | WINDOWS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47732 | WINDOWS | D | Soft wood timber splice with resin; face splice repair method no. 5. Remove old and loose paint as necessary. Cut out decayed timber from windows and frames, piecing in or frame in new wrought softwood with resin to match existing. Leave ready to decorate. Splice not exc 500 to 1000mm |  |  | 4.11 |  | WIND017 | Nr | 2 | 36.75 | 73.5 | #VALUE! | #VALUE! | 0 | 34.9125 | 69.825 | Nr | 2 | 34.9125 | 69.825 | 0% | 0 | 0% | 0 | 0
| REPB47732 | WINDOWS | D | 7. Timber repair system; using window care dry fix/dry flex RP; Conservation Joint; Up to 50mm |  |  | 4.13 |  | WIND022 | Nr | 30 | 4.25 | 127.5 | #VALUE! | #VALUE! | 0 | 4.0375 | 121.125 | Nr | 30 | 4.0375 | 121.125 | 0% | 0 | 0% | 0 | 0
| REPB47732 | WINDOWS | D | 7. Timber repair system; using window care dry fix/dry flex RP; Conservation Joint; up to 100mm |  |  | 4.14 |  | WIND023 | Nr | 5 | 6.75 | 33.75 | #VALUE! | #VALUE! | 0 | 6.4125 | 32.0625 | Nr | 5 | 6.4125 | 32.0625 | 0% | 0 | 0% | 0 | 0
| REPB47732 | WINDOWS | D | Window: Overhaul timber sash window, renew staff and parting beads, take out sashes and later rehang on appropriate sized new undyed plaited nylon sash cords, renew pocket pieces, wedge and cramp loose sash frames, oil pulleys, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.9 |  | 3150CA | NO | 3 | 35.61 | 106.83 | #VALUE! | #VALUE! | 0 | 31.5683 | 94.7048 | NO | 3 | 31.5683 | 94.7048 | 0% | 0 | 0% | 0 | 0
| REPB47732 | WINDOWS | D | PROVISIONAL SUM: Soft wood timber splice with resin; face splice repair method no. 5. Remove old and loose paint as necessary. Cut out decayed timber from windows and frames, piecing in or frame in new wrought softwood with resin to match existing. Leave ready to decorate. Splice not exc 500 to 1000mm |  |  | 4.293 |  | PROV SUM | SUM | 1 | 70 | 70 | #VALUE! | 70 |  |  | 70 | SUM | 1 |  | 70 | 0% | 0 | 0% | 0 | 0
| REPB47732 | WINDOWS | D | PROVISIONAL SUM: 7. Timber repair system; using window care dry fix/dry flex RP; Conservation Joint; Up to 50mm |  |  | 4.294 |  | PROV SUM | SUM | 1 | 130 | 130 | #VALUE! | 130 |  |  | 130 | SUM | 1 |  | 130 | 0% | 0 | 0% | 0 | 0
| REPB47732 | WINDOWS | D | PROVISIONAL SUM: 7. Timber repair system; using window care dry fix/dry flex RP; Conservation Joint; up to 100mm |  |  | 4.295 |  | PROV SUM | SUM | 1 | 30 | 30 | #VALUE! | 30 |  |  | 30 | SUM | 1 |  | 30 | 0% | 0 | 0% | 0 | 0
| REPB47732 | WINDOWS | D | PROVISIONAL SUM: Window: Overhaul timber sash window, renew staff and parting beads, take out sashes and later rehang on appropriate sized new undyed plaited nylon sash cords, renew pocket pieces, wedge and cramp loose sash frames, oil pulleys, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.296 |  | PROV SUM | SUM | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | SUM | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47732 | SCAFFOLD | H | [23 empty] | 0
| REPB47732 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 160 | 12.92 | 2067.2 | #VALUE! | #VALUE! | 0 | 16.4084 | 2625.344 | M2 | 160 | 16.4084 | 2625.344 | 0% | 0 | 0% | 0 | 0
| REPB47732 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 0% | 0 | 0% | 0 | 0
| REPB47732 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 1 | 50 | 50 | #VALUE! | #VALUE! | 0 | 63.5 | 63.5 | unit | 1 | 63.5 | 63.5 | 0% | 0 | 0% | 0 | 0
| REPB47732 | SCAFFOLD | D | Scaffold taken through property (protection to surfaces included) |  |  | 2.16 |  | SC016 | unit | 1 | 379.8 | 379.8 | #VALUE! | #VALUE! | 0 | 482.346 | 482.346 | unit | 1 | 482.346 | 482.346 | 0% | 0 | 0% | 0 | 0
| REPB47732 | SCAFFOLD | D | Scaffold taken up&over the roof |  |  | 2.17 |  | SC017 | unit | 1 | 842 | 842 | #VALUE! | #VALUE! | 0 | 1069.34 | 1069.34 | unit | 1 | 1069.34 | 1069.34 | 0% | 0 | 0% | 0 | 0
| REPB47732 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | 0.0483 | 0 | unit |  | 0.0483 | 0 | 0% | 0 | 0% | 0 | 0
| REPB47732 | ESTATE WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47732 | ESTATE WORKS | D | PROVISIONAL SUM: Fencing: Renew or provide new tanalised timber closeboard fencing including for taking down remnants of existing fence and posts set in concrete, remove from site to approved tip, and set 100x100x1650mm long tanalised softwood posts in concrete at 1.80m centres with two 69x44mm softwood arris rails bolted to posts with 144x20mm vertical boards 1.05m high nailed to rails, provide and fix 25x150mm tanalised softwood gravel board with centre prop. (measured per metre run of fencing). |  |  | 7.316 |  | PROV SUM | SUM | 1 | 250 | 250 | #VALUE! | 250 |  | 250 | 250 | SUM | 1 | 250 | 250 | 0% | 0 | 0% | 0 | 0
| REPB47732 | ESTATE WORKS | D |  |  |  | 7.318 |  | PROV SUM | SUM | 1 | 100 | 100 | #VALUE! | 100 |  | 100 | 100 | SUM | 1 | 100 | 100 | 0% | 0 | 0% | 0 | 0
| REPB47732 | ESTATE WORKS | D | PROVISIONAL SUM: Fracture: Remove any applied finish and cut out bricks as necessary to either side of fracture, one face only, stitch in new bricks, bed and point to match existing in cement lime mortar (1:1:6), and make good any applied finishes, and remove waste and debris (measured over mean general line of fracture). |  |  | 7.319 |  | PROV SUM | SUM | 1 | 400 | 400 | #VALUE! | 400 |  | 400 | 400 | SUM | 1 | 400 | 400 | 0% | 0 | 0% | 0 | 0
| REPB47732 | ESTATE WORKS | D | PROVISIONAL SUM: Wall: Rake out existing joints of brickwork min 12mm and repoint brickwork in mortar to match existing and remove waste and debris. |  |  | 7.32 |  | PROV SUM | SUM | 1 | 400 | 400 | #VALUE! | 400 |  | 400 | 400 | SUM | 1 | 400 | 400 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 13331.4148 |  |  | TOTAL | 13331.4148 |  | 0 |  | 0 | 0

## 29 Grove Terrace
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
29 Grove Terrace
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB47494 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB47494 | ENERGY EFFICIENY | H
| REPB47494 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! | 0 | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB47494 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0 | 0
| REPB47494 | ASBESTOS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47494 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB47494 | COMMUNAL WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47494 | COMMUNAL WORKS | D | Hall: Thoroughly clean down all wall and ceiling surfaces to common areas to remove dirt, grease and surface containments, scrape and remove all loose and defective coatings, prime bare areas with one coat of fire retardant primer and apply two coats of Class ‘O’ fire retardant matt paint, prepare and apply two coats of polyurethane lacquer or one undercoat and one gloss coat to all previously decorated timber surfaces to lobby, hall or corridor over 3.00sm ceiling area complete (classified as a single area). |  |  | 5.1 |  | 4540AC | IT | 1 | 480 | 480 | #VALUE! | #VALUE! | 0 | 408 | 408 | IT | 1 | 408 | 408 | 0% | 0 | 0% | 0 | 0
| REPB47494 | COMMUNAL WORKS | D | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris. |  |  | 5.386 |  | PROV SUM | SUM | 1 | 300 | 300 | #VALUE! | 300 |  |  | 300 | SUM | 1 |  | 300 | 0% | 0 | 0% | 0 | 0
| REPB47494 | COMMUNAL WORKS | D | PROVISIONAL SUM: Take up and renew linoleum floor covering. |  |  | 5.387 |  | PROV SUM | SUM | 1 | 700 | 700 | #VALUE! | 700 |  |  | 700 | SUM | 1 |  | 700 | 0% | 0 | 0% | 0 | 0
| REPB47494 | EXTREP | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47494 | EXTREP | D | Moulding Repairs 0-5no. per property Fosroc repair mortar or equivalent Insitu repairs using straight edge to form moulding repair. (Girth NE300mm Length NE300mm) |  |  | 6.11 |  | FAB071 | no | 5 | 79.14 | 395.7 | #VALUE! | #VALUE! | 0 | 63.312 | 316.56 | no | 5 | 63.312 | 316.56 | 0% | 0 | 0% | 0 | 0
| REPB47494 | EXTREP | D | Fracture: Remove any applied finish and cut out bricks as necessary to either side of fracture, one face only, stitch in new bricks, bed and point to match existing in cement lime mortar (1:1:6), and make good any applied finishes, and remove waste and debris (measured over mean general line of fracture). |  |  | 6.82 |  | 1019AA | LM | 37 | 44.12 | 1632.44 | #VALUE! | #VALUE! | 0 | 31.987 | 1183.519 | LM | 37 | 31.987 | 1183.519 | 0% | 0 | 0% | 0 | 0
| REPB47494 | EXTREP | D | Cills: Prepare, clean off all dust and debris, fill in or resurface cracks or spalled surfaces of concrete with epoxy mortar in surfaces of cills, not exceeding 300mm girth, repair over 5 and ne 10mm deep, and remove waste and debris. |  |  | 6.161 |  | 1460AF | LM | 12 | 38.25 | 459 | #VALUE! | #VALUE! | 0 | 27.7312 | 332.775 | LM | 12 | 27.7312 | 332.775 | 0% | 0 | 0% | 0 | 0
| REPB47494 | EXTREP | D | Walls:Wash down, fill in cracks and holes, sand smooth and apply two coats of smooth finish masonry paint to rendered or concrete surfaces of walls. |  |  | 6.194 |  | 4360BA | SM | 28 | 7.02 | 196.56 | #VALUE! | #VALUE! | 0 | 5.967 | 167.076 | SM | 28 | 5.967 | 167.076 | 0% | 0 | 0% | 0 | 0
| REPB47494 | EXTREP | D | Balustrading: Wire brush, prepare for and apply one coat of primer, one undercoat, two coats of gloss paint on ornamental metal balustrading, railings or gates (measured both sides). |  |  | 6.204 |  | 4362EA | SM | 12 | 20.51 | 246.12 | #VALUE! | #VALUE! | 0 | 17.4335 | 209.202 | SM | 12 | 17.4335 | 209.202 | 0% | 0 | 0% | 0 | 0
| REPB47494 | EXTREP | D | Window: Rub down, prepare and apply one undercoat and one coat of gloss paint on existing painted surfaces of wooden windows (one side and edges). |  |  | 6.262 |  | 4381JB | SM | 34 | 16.86 | 573.24 | #VALUE! | #VALUE! | 0 | 14.331 | 487.254 | SM | 34 | 14.331 | 487.254 | 0% | 0 | 0% | 0 | 0
| REPB47494 | EXTREP | D | Door: Rub down, prepare for and apply one undercoat and one coat of gloss paint to all existing painted surfaces of any size or type of single glazed timber door (both sides and edges). |  |  | 6.265 |  | 4381LB | IT | 1 | 19.34 | 19.34 | #VALUE! | #VALUE! | 0 | 16.439 | 16.439 | IT | 1 | 16.439 | 16.439 | 0% | 0 | 0% | 0 | 0
| REPB47494 | EXTREP | D | PROVISIONAL SUM: Rear wall: Complete pebbledash rendering to lower section of wall SM 8. |  |  | 6.399 |  | PROV SUM | SUM | 1 | 400 | 400 | #VALUE! | 400 |  |  | 400 | SUM | 1 |  | 400 | 0% | 0 | 0% | 0 | 0
| REPB47494 | ROOF | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47494 | ROOF | D | Moss:Carefully remove moss/lichen growth on roof covering of any kind and dispose of debris off site, reistate all disturbed surfaces, replace broken tiles, slates and the like, thoroughly clean out valleys, gutters, downpipes, hoppers etc, prepare and treat the complete roof area with a diluted fungicide solution AKZO or other equal and approved applied strictly in accordance with the manufacturer’s instructions, thoroughly clean out all gutters and the like to remove all chemical residue arising upon completion of the works, and remove waste and debris. |  |  | 3.18 |  | 2115AA | SM | 55 | 10.17 | 559.35 | #VALUE! | #VALUE! | 0 | 8.136 | 447.48 | SM | 55 | 8.136 | 447.48 | 0% | 0 | 0% | 0 | 0
| REPB47494 | ROOF | D | Roofing:Apply sealing compound to cracks to roof or leadwork. |  |  | 3.182 |  | 2150AB | LM | 8 | 5.4 | 43.2 | #VALUE! | #VALUE! | 0 | 4.32 | 34.56 | LM | 8 | 4.32 | 34.56 | 0% | 0 | 0% | 0 | 0
| REPB47494 | ROOF | D | Slate: Overhaul fibre cement slate roof, refix loose slates, renew broken or missing slates to match existing, redress, rewedge and repoint all flashings, aprons, chimney gutters etc, cut out and make good cement weather fillets, repoint in cement mortar (1:3) to all hips, ridges and verges, make good, and remove waste and debris. |  |  | 3.207 |  | 2031CA | SM | 3 | 30.56 | 91.68 | #VALUE! | #VALUE! | 0 | 24.448 | 73.344 | SM | 3 | 24.448 | 73.344 | 0% | 0 | 0% | 0 | 0
| REPB47494 | ROOF | D | Gutter:Clean out debris from gutters to any type of property including flush out and test, rod downpipe including clean out gulley and remove debris from site on completion (per elevation). |  |  | 3.364 |  | 6039BA | IT | 1 | 20.13 | 20.13 | #VALUE! | #VALUE! | 0 | 14.9183 | 14.9183 | IT | 1 | 14.9183 | 14.9183 | 0% | 0 | 0% | 0 | 0
| REPB47494 | WINDOWS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47494 | WINDOWS | D | 7. Timber repair system; using window care dry fix/dry flex RP; Conservation Joint; up to 100mm |  |  | 4.14 |  | WIND023 | Nr | 30 | 6.75 | 202.5 | #VALUE! | #VALUE! | 0 | 6.4125 | 192.375 | Nr | 30 | 6.4125 | 192.375 | 0% | 0 | 0% | 0 | 0
| REPB47494 | WINDOWS | D | Window: Overhaul timber casement window, dismantle as necessary and subsequently reassemble including freeing, easing and adjusting casements to give correct operation, renew sealing gaskets, renew fixing screws, remove, refit or renew ironmongery as necessary, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.89 |  | 3150BA | NO | 4 | 29.05 | 116.2 | #VALUE! | #VALUE! | 0 | 25.7528 | 103.0113 | NO | 4 | 25.7528 | 103.0113 | 0% | 0 | 0% | 0 | 0
| REPB47494 | WINDOWS | D | Window: Overhaul timber sash window, renew staff and parting beads, take out sashes and later rehang on appropriate sized new undyed plaited nylon sash cords, renew pocket pieces, wedge and cramp loose sash frames, oil pulleys, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.9 |  | 3150CA | NO | 26 | 35.61 | 925.86 | #VALUE! | #VALUE! | 0 | 31.5683 | 820.7749 | NO | 26 | 31.5683 | 820.7749 | 0% | 0 | 0% | 0 | 0
| REPB47494 | WINDOWS | D | PROVISIONAL SUM: Allow for unforeseen window repairs. |  |  | 4.293 |  | PROV SUM | SUM | 1 | 300 | 300 | #VALUE! | 300 |  |  | 300 | SUM | 1 |  | 300 | 0% | 0 | 0% | 0 | 0
| REPB47494 | SCAFFOLD | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47494 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 256 | 12.92 | 3307.52 | #VALUE! | #VALUE! | 0 | 16.4084 | 4200.5504 | M2 | 256 | 16.4084 | 4200.5504 | 0% | 0 | 0% | 0 | 0
| REPB47494 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 0% | 0 | 0% | 0 | 0
| REPB47494 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 2 | 50 | 100 | #VALUE! | #VALUE! | 0 | 63.5 | 127 | unit | 2 | 63.5 | 127 | 0% | 0 | 0% | 0 | 0
| REPB47494 | SCAFFOLD | D | Scaffold taken through property (protection to surfaces included) |  |  | 2.16 |  | SC016 | unit | 1 | 379.8 | 379.8 | #VALUE! | #VALUE! | 0 | 482.346 | 482.346 | unit | 1 | 482.346 | 482.346 | 0% | 0 | 0% | 0 | 0
| REPB47732 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB47494 | ESTATE WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47494 | ESTATE WORKS | D | Fencing: Renew or provide new 1.65m tanalised timber vertical board fencing including for taking down remnants of existing fence and posts set in concrete, remove from site to approved tip, and set 125x125mm x 2.65m long softwood posts in concrete at ne 1.80m centres with three 69x44mm softwood rails bolted to posts and 144x20mm vertical boards nailed to rails, softwood gravel board with centre prop (measured per metre run of fencing). |  |  | 7.79 |  | 0171AD | LM | 7 | 93.18 | 652.26 | #VALUE! | #VALUE! | 0 | 76.5008 | 535.5055 | LM | 7 | 76.5008 | 535.5055 | 0% | 0 | 0% | 0 | 0
| REPB47494 | ESTATE WORKS | D | Fracture: Remove any applied finish and cut out bricks as necessary to either side of fracture, one face only, stitch in new bricks, bed and point to match existing in cement lime mortar (1:1:6), and make good any applied finishes, and remove waste and debris (measured over mean general line of fracture). |  |  | 7.244 |  | 1019AA | LM | 17 | 44.12 | 750.04 | #VALUE! | #VALUE! | 0 | 31.987 | 543.779 | LM | 17 | 31.987 | 543.779 | 0% | 0 | 0% | 0 | 0
| REPB47494 | ESTATE WORKS | D | PROVISIONAL SUM: Paving slab: Re-allign to attain even surfcace. SM 3. |  |  | 7.316 |  | PROV SUM | SUM | 1 | 400 | 400 | #VALUE! | 400 |  |  | 400 | SUM | 1 |  | 400 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 13952.1649 |  |  | TOTAL | 13952.1649 |  | 0 |  | 0 | 0

## 28 Leighton Road
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
28 Leighton Road
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB47660 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB47660 | ENERGY EFFICIENY | H
| REPB47660 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! | 0 | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB47660 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0 | 0
| REPB47660 | ASBESTOS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47660 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB47660 | COMMUNAL WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47660 | COMMUNAL WORKS | D | Hall: Thoroughly clean down all wall and ceiling surfaces to common areas to remove dirt, grease and surface containments, scrape and remove all loose and defective coatings, prime bare areas with one coat of fire retardant primer and apply two coats of Class ‘O’ fire retardant matt paint, prepare and apply two coats of polyurethane lacquer or one undercoat and one gloss coat to all previously decorated timber surfaces to lobby, hall or corridor over 3.00sm ceiling area complete (classified as a single area). |  |  | 5.1 |  | 4540AC | IT | 1 | 480 | 480 | #VALUE! | #VALUE! | 0 | 408 | 408 | IT | 1 | 408 | 408 | 0% | 0 | 0% | 0 | 0
| REPB47660 | COMMUNAL WORKS | D | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris. |  |  | 5.154 |  | 4328AC | SM | 6 | 16.28 | 97.68 | #VALUE! | #VALUE! | 0 | 13.7143 | 82.2856 | SM | 6 | 13.7143 | 82.2856 | 0% | 0 | 0% | 0 | 0
| REPB47660 | COMMUNAL WORKS | D | PROVISIONAL SUM: Allow for any unforeseen communal works. |  |  | 5.388 |  | PROV SUM | SUM | 1 | 200 | 200 | #VALUE! | 200 |  |  | 200 | SUM | 1 |  | 200 | 0% | 0 | 0% | 0 | 0
| REPB47660 | EXTREP | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47660 | EXTREP | D | Lintel: Cut out and remove existing lintol from brick wall, prepare to receive new including all necessary propping and temporary supports, and supply and fix 75x150mm precast concrete lintol reinforced with 2 No. 16mm diameter mild steel bars, bed ends in cement lime mortar (1:1:6), renew dpc and make good brickwork, plasterwork and sealant and or cement fillets, and clear away debris on completion. |  |  | 6.103 |  | 1029AA | LM | 1 | 59.11 | 59.11 | #VALUE! | #VALUE! | 0 | 42.8547 | 42.8547 | LM | 1 | 42.8547 | 42.8547 | 0% | 0 | 0% | 0 | 0
| REPB47660 | EXTREP | D | Cills: Prepare, clean off all dust and debris, fill in or resurface cracks or spalled surfaces of concrete with epoxy mortar in surfaces of cills, not exceeding 300mm girth, repair over 5 and ne 10mm deep, and remove waste and debris. |  |  | 6.161 |  | 1460AF | LM | 8 | 38.25 | 306 | #VALUE! | #VALUE! | 0 | 27.7312 | 221.85 | LM | 8 | 27.7312 | 221.85 | 0% | 0 | 0% | 0 | 0
| REPB47660 | EXTREP | D | Walls: Prepare and apply two coats smooth or textured masonry paint to external rendered surfaces of walls. |  |  | 6.179 |  | 4356AA | SM | 106 | 10.36 | 1098.16 | #VALUE! | #VALUE! | 0 | 8.806 | 933.436 | SM | 106 | 8.806 | 933.436 | 0% | 0 | 0% | 0 | 0
| REPB47660 | EXTREP | D | Gates: Wire brush, prepare for and apply one undercoat and two coats of gloss paint to both sides of existing painted surface of any size/type single metal gate including all edges and all surfaces of posts. |  |  | 6.214 |  | 4363DA | IT | 1 | 16.98 | 16.98 | #VALUE! | #VALUE! | 0 | 14.433 | 14.433 | IT | 1 | 14.433 | 14.433 | 0% | 0 | 0% | 0 | 0
| REPB47660 | EXTREP | D | Balustrading: Wire brush, prepare for and apply one undercoat and two coats of gloss paint on existing painted surfaces ornamental metal balustrading, railings or gates (measured both sides). |  |  | 6.215 |  | 4363EA | SM | 12 | 16.08 | 192.96 | #VALUE! | #VALUE! | 0 | 13.668 | 164.016 | SM | 12 | 13.668 | 164.016 | 0% | 0 | 0% | 0 | 0
| REPB47660 | EXTREP | D | Window: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on surfaces of wooden windowsl (one side and edges). |  |  | 6.236 |  | 4380BA | SM | 24 | 25.87 | 620.88 | #VALUE! | #VALUE! | 0 | 21.9895 | 527.748 | SM | 24 | 21.9895 | 527.748 | 0% | 0 | 0% | 0 | 0
| REPB47660 | EXTREP | D | Frame: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on timber frame ne 300mm girth. |  |  | 6.237 |  | 4380CA | LM | 17 | 6.28 | 106.76 | #VALUE! | #VALUE! | 0 | 5.338 | 90.746 | LM | 17 | 5.338 | 90.746 | 0% | 0 | 0% | 0 | 0
| REPB47660 | EXTREP | D | Door: Rub down, prepare for and apply one coat of primer, one undercoat and two coats of gloss paint to all surfaces of any size or type of single glazed timber door. (one sides and edges). |  |  | 6.238 |  | 4380DA | IT | 4 | 20.71 | 82.84 | #VALUE! | #VALUE! | 0 | 17.6035 | 70.414 | IT | 4 | 17.6035 | 70.414 | 0% | 0 | 0% | 0 | 0
| REPB47660 | EXTREP | D | Wall: Hack off any thickness of render from walls, rake out and prepare brickwork or blockwork to receive rendering and remove waste and debris. |  |  | 5.173 |  | 4210AA | SM | 106 | 12.5 | 1325 | #VALUE! | #VALUE! | 0 | 9.0625 | 960.625 | SM | 106 | 9.0625 | 960.625 | 0% | 0 | 0% | 0 | 0
| REPB47660 | EXTREP | D | Wall: Apply 12mm cement and sand render (1:3) with waterproofing agent to external walls including ‘Decorative’ finish, dub out as necessary with cement and sand and all labours and remove waste and debris. |  |  | 5.177 |  | 4210AE | SM | 106 | 31.33 | 3320.98 | #VALUE! | #VALUE! | 0 | 22.7142 | 2407.7105 | SM | 106 | 22.7142 | 2407.7105 | 0% | 0 | 0% | 0 | 0
| REPB47660 | ROOF | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47660 | ROOF | D | Asphalt: Overhaul asphalt roofing to flat roof area, Including sweep and remove moss, algae and other debris, cut out blisters, cracks and make good in asphalt, prepare and apply two coats of solar reflective paint as necessary, rewedge and redress flashings, clear associated gutters and outlets, and remove waste and debris. |  |  | 3.74 |  | 2190GA | SM | 42 | 30.56 | 1283.52 | #VALUE! | #VALUE! | 0 | 24.448 | 1026.816 | SM | 42 | 24.448 | 1026.816 | 0% | 0 | 0% | 0 | 0
| REPB47660 | ROOF | D | Gutter: Renew ne 125mm cast iron gutter of any profile including support brackets fixed to fascia including cutting, making joints, line and level, and connections to existing guttering, and rub down, prepare for redecoration to outside of gutter and apply one coat of bitumastic paint to inside of gutter, and remove waste and debris. |  |  | 3.333 |  | 6033AB | LM | 6 | 53.05 | 318.3 | #VALUE! | #VALUE! | 0 | 39.3154 | 235.8921 | LM | 6 | 39.3154 | 235.8921 | 0% | 0 | 0% | 0 | 0
| REPB47660 | ROOF | D | Hopper: Clear out blocked hopperhead including rod if necessary, flush out and test and remove debris from site on completion, and remove waste and debris. |  |  | 3.361 |  | 6039AB | NO | 1 | 8.05 | 8.05 | #VALUE! | #VALUE! | 0 | 5.9659 | 5.9659 | NO | 1 | 5.9659 | 5.9659 | 0% | 0 | 0% | 0 | 0
| REPB47660 | ROOF | D | Stack: Renew up to 150mm diameter cast iron soil stack length ne 2m long with existing or new clips or ears including all cutting, remake joints, make good and prepare for redecoration, and remove waste and debris.. |  |  | 3.384 |  | 6105AA | NO | 6 | 108.64 | 651.84 | #VALUE! | #VALUE! | 0 | 80.5131 | 483.0786 | NO | 6 | 80.5131 | 483.0786 | 0% | 0 | 0% | 0 | 0
| REPB47660 | ROOF | D | Chimney:Renew any thickness of render to chimney, hack off, rake out, prepare and apply 18mm thick two coats cement and sand render trowelled smooth including all labours, and remove waste and debris. |  |  | 3.424 |  | 1200BA | SM | 4 | 33.68 | 134.72 | #VALUE! | #VALUE! | 0 | 24.418 | 97.672 | SM | 4 | 24.418 | 97.672 | 0% | 0 | 0% | 0 | 0
| REPB47660 | WINDOWS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47660 | WINDOWS | D | Window: Renew window with purpose made softwood double hung cased box frame and sashes complete with 2 sashes, factory applied base stain or primer finish, compressible weatherstripping, glazing beads, ironmongery, remove existing and fix new into prepared opening, bed in mortar, point with sealant, double glazed and make good all finishes, decorate to match existing internally and prepare for redecoration externally, and remove waste and debris. |  |  | 4.28 |  | 3105AC | SM | 3 | 434.56 | 1303.68 | #VALUE! | #VALUE! | 0 | 385.2374 | 1155.7123 | SM | 3 | 385.2374 | 1155.7123 | 0% | 0 | 0% | 0 | 0
| REPB47660 | WINDOWS | D | Window: Overhaul sash window, renew staff and parting beads, take out sashes and later rehang on spiral sash balances, renew pocket pieces, wedge and cramp loose sash frames, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.91 |  | 3150CB | NO | 5 | 98.99 | 494.95 | #VALUE! | #VALUE! | 0 | 87.7546 | 438.7732 | NO | 5 | 87.7546 | 438.7732 | 0% | 0 | 0% | 0 | 0
| REPB47660 | SCAFFOLD | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47660 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 84 | 12.92 | 1085.28 | #VALUE! | #VALUE! | 0 | 16.4084 | 1378.3056 | M2 | 84 | 16.4084 | 1378.3056 | 0% | 0 | 0% | 0 | 0
| REPB47660 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 0% | 0 | 0% | 0 | 0
| REPB47660 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 2 | 50 | 100 | #VALUE! | #VALUE! | 0 | 63.5 | 127 | unit | 2 | 63.5 | 127 | 0% | 0 | 0% | 0 | 0
| REPB47660 | SCAFFOLD | D | Scaffold to chimney stack n.e. 3.00 girth, n.e. 2.00m high to gable, verge or edge |  |  | 2.7 |  | SC008 | unit | 1 | 383.72 | 383.72 | #VALUE! | #VALUE! | 0 | 487.3244 | 487.3244 | unit | 1 | 487.3244 | 487.3244 | 0% | 0 | 0% | 0 | 0
| REPB47660 | SCAFFOLD | D | Scaffold taken through property (protection to surfaces included) |  |  | 2.16 |  | SC016 | unit | 1 | 379.8 | 379.8 | #VALUE! | #VALUE! | 0 | 482.346 | 482.346 | unit | 1 | 482.346 | 482.346 | 0% | 0 | 0% | 0 | 0
| REPB47660 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB47660 | ESTATE WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47660 | ESTATE WORKS | D | Wall: Take down one and a half brick wall and remove waste and debris. |  |  | 7.19 |  | 1011AC | SM | 3 | 39.57 | 118.71 | #VALUE! | #VALUE! | 0 | 28.6883 | 86.0648 | SM | 3 | 28.6883 | 86.0648 | 0% | 0 | 0% | 0 | 0
| REPB47660 | ESTATE WORKS | D | Wall: Supply and lay new common bricks in one and a half brick wall in cement lime mortar (1:1:6). |  |  | 7.199 |  | 1013AC | SM | 5 | 133.42 | 667.1 | #VALUE! | #VALUE! | 0 | 96.7295 | 483.6475 | SM | 5 | 96.7295 | 483.6475 | 0% | 0 | 0% | 0 | 0
| REPB47660 | ESTATE WORKS | D | Coping: Take off precast coping ne 300mm wide, clean mortar from top of wall and coping, bed and point in cement lime mortar (1:1:6) with bonding agent and remove waste and debris. |  |  | 7.298 |  | 1033CA | LM | 3 | 6.04 | 18.12 | #VALUE! | #VALUE! | 0 | 4.379 | 13.137 | LM | 3 | 4.379 | 13.137 | 0% | 0 | 0% | 0 | 0
| REPB47660 | ESTATE WORKS | D | Coping: Supply and lay new precast concrete coping ne 300mm wide in section to match existing, bedded and pointed in cement lime mortar (1:1:6) with bonding agent. |  |  | 7.3 |  | 1033CC | LM | 3 | 14.27 | 42.81 | #VALUE! | #VALUE! | 0 | 10.3457 | 31.0372 | LM | 3 | 10.3457 | 31.0372 | 0% | 0 | 0% | 0 | 0
| REPB47660 | ESTATE WORKS | D | PROVISIONAL SUM: Allow provisional sum for estate works, as no access to rear of property. |  |  | 7.316 |  | PROV SUM | SUM | 1 | 400 | 400 | #VALUE! | 400 |  |  | 400 | SUM | 1 |  | 400 | 0% | 0 | 0% | 0 | 0
| REPB47660 | FRA WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47660 | FRA WORKS | D | Door:Renew internal door with any size single half-hour fire check glazed door having 3.2mm luan, white Meranti or other approved plywood facing both sides and 9mm hardwood lipping on long edges, including remove existing door and hinges, remove and refit door stops as necessary, fit and hang new door on 1.50 pairs of 100mm steel butt hinges, make good or alter recesses on frame, door complete with all ironmongery, intumescent strips and smoke seals, glazed, redecorate to match existing and remove waste and debris. |  |  | 18 |  | 3300FC | Item | 2 | 222.2 | 444.4 | #VALUE! | #VALUE! | 0 | 196.9803 | 393.9606 | Item | 2 | 196.9803 | 393.9606 | 0% | 0 | 0% | 0 | 0
| REPB47660 | FRA WORKS | D | Fire Upgrading Coating:Remove all existing defective paint to plastered or rendered wall surfaces back to a solid edge, feather off and repair any defective areas with a high quality filler as necessary, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, wash down, rinse, clean off and apply one full coat of fire upgrading primer at a coverage rate of 10sm per litre, apply two full coats of fire upgrading finish at a coverage rate of 10sm per litre. |  |  | 27 |  | 4801AB | Item | 1 | 22.53 | 22.53 | #VALUE! | #VALUE! | 0 | 19.1505 | 19.1505 | Item | 1 | 19.1505 | 19.1505 | 0% | 0 | 0% | 0 | 0
| REPB47660 | FRA WORKS | D | Fire Upgrading Coating:Strip off existing multi layer paint coatings to existing plastered or rendered soffits with a proprietary paint stripper, scrape off or remove with a proprietary paint scraper, wash down,rinse, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, clean off and apply one full coat of primer at a coverage rate of 10sm per litre, apply one full coats of colourcoat complete with decorative flakes, and apply one full coat of gloss or satin lacquer finish at a coverage rate of 10sm per litre. |  |  | 41 |  | 4804AD | Item | 1 | 29.34 | 29.34 | #VALUE! | #VALUE! | 0 | 24.939 | 24.939 | Item | 1 | 24.939 | 24.939 | 0% | 0 | 0% | 0 | 0
| REPB47660 | FRA WORKS | D | Fire Upgrading Coating:Remove all existing defective paint to general surfaces of woodwork not exceeding 300mm girth, back to a solid edge, feather off and repair any defective areas with a high quality filler as necessary, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, wash down, rinse, clean off and apply one full coat of fire upgrading primer at a coverage rate of 10sm per litre, apply two full coats of fire upgrading finish at a coverage rate of 10sm per litre. |  |  | 43 |  | 4805AB | Item | 1 | 20.4 | 20.4 | #VALUE! | #VALUE! | 0 | 17.34 | 17.34 | Item | 1 | 17.34 | 17.34 | 0% | 0 | 0% | 0 | 0
| REPB47660 | FRA WORKS | D | Fire Upgrading Coating:Remove all existing defective paint to general surfaces of timber doors back to a solid edge, feather off and repair any defective areas with a high quality filler as necessary, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, wash down, rinse, clean off and apply one full coat of fire upgrading primer at a coverage rate of 10sm per litre, apply two full coats of fire upgrading finish at a coverage rate of 10sm per litre. |  |  | 44 |  | 4805AC | Item | 1 | 35.86 | 35.86 | #VALUE! | #VALUE! | 0 | 30.481 | 30.481 | Item | 1 | 30.481 | 30.481 | 0% | 0 | 0% | 0 | 0
| REPB47660 | FRA WORKS | D | Intumescent Strip:Renew or supply and fix new 22x4mm intumescent strip, half hour application, with integral cold smoke seal and setting into groove in timber frame or door. |  |  | 104 |  | 3431AC | Item | 2 | 3.44 | 6.88 | #VALUE! | #VALUE! | 0 | 3.0496 | 6.0991 | Item | 2 | 3.0496 | 6.0991 | 0% | 0 | 0% | 0 | 0
| REPB47660 | FRA WORKS | D |  |  |  | 115 |  | 8720FA | Item | 2 | 70.11 | 140.22 | #VALUE! | #VALUE! | 0 | 56.088 | 112.176 | Item | 2 | 56.088 | 112.176 | 0% | 0 | 0% | 0 | 0
| REPB47660 | FRA WORKS | D | Closer:Renew or supply and fix Perko type concealed door closer screwed to door and frame, including remove and refix door or door stop as necessary. |  |  | 175 |  | 3905BA | Item | 2 | 9.81 | 19.62 | #VALUE! | #VALUE! | 0 | 8.6966 | 17.3931 | Item | 2 | 8.6966 | 17.3931 | 0% | 0 | 0% | 0 | 0
| REPB47660 | FRA WORKS | D | Partition:Supply and erect or renew stud partition comprising ne 50x100mm sole and head plate, noggins and studs fixed with nails or plugged and screwed to walls, and pack out and scribe, 12.5mm butt jointed plasterboard and 3mm plaster skim coat and all labours to both faces. |  |  | 180 |  | 3013AB | Item | 1 | 62.11 | 62.11 | #VALUE! | #VALUE! | 0 | 55.0605 | 55.0605 | Item | 1 | 55.0605 | 55.0605 | 0% | 0 | 0% | 0 | 0
| REPB47660 | FRA WORKS | D | Test:Carry out test of domestic installation to occupied property complete comprising continuity, insulation resistance, polarity, earth fault loop impedance and operation of residual current operated device, disconnect, repair and renew as necessary after removal of illegal wiring and components, and provide report and NICEIC/ECA test certificate to the Client’s Representative, and remove waste and debris. |  |  | 186 |  | 8950AA | Item | 1 | 86.88 | 86.88 | #VALUE! | #VALUE! | 0 | 69.504 | 69.504 | Item | 1 | 69.504 | 69.504 | 0% | 0 | 0% | 0 | 0
| REPB47660 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to the fire alarm system. |  |  | 190 |  | PROV SUM | Item | 1 | 1500 | 1500 | #VALUE! | 1500 |  |  | 1500 | Item | 1 |  | 1500 | 0% | 0 | 0% | 0 | 0
| REPB47660 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to clear waste and debris from fire escape routes. |  |  | 191 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47660 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional fire stopping works |  |  | 192 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47660 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional signage |  |  | 193 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47660 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional electrical works |  |  | 194 |  | PROV SUM | Item | 1 | 350 | 350 | #VALUE! | 350 |  |  | 350 | Item | 1 |  | 350 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 17108.6909 |  |  | TOTAL | 17108.6909 |  | 0 |  | 0 | 0

## 13 Mortimer Terrace
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
13 Mortimer Terrace
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB47715 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB47715 | ENERGY EFFICIENY | H
| REPB47715 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! | 0 | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB47715 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0 | 0
| REPB47715 | ASBESTOS | H | [18 empty] | 0 |  |  |  |  | 0
| REPB47715 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB47715 | COMMUNAL WORKS | H | [23 empty] | 0
| REPB47715 | COMMUNAL WORKS | D | Hall: Thoroughly clean down all wall and ceiling surfaces to common areas to remove dirt, grease and surface containments, scrape and remove all loose and defective coatings, prime bare areas with one coat of fire retardant primer and apply two coats of Class ‘O’ fire retardant matt paint, prepare and apply two coats of polyurethane lacquer or one undercoat and one gloss coat to all previously decorated timber surfaces to lobby, hall or corridor over 3.00sm ceiling area complete (classified as a single area). |  |  | 5.1 |  | 4540AC | IT | 1 | 480 | 480 | #VALUE! | #VALUE! | 0 | 408 | 408 | IT | 1 | 408 | 408 | 0% | 0 | 0% | 0 | 0
| REPB47715 | COMMUNAL WORKS | D | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris. |  |  | 5.154 |  | 4328AC | SM | 20 | 16.28 | 325.6 | #VALUE! | #VALUE! | 0 | 13.7143 | 274.2854 | SM | 20 | 13.7143 | 274.2854 | 0% | 0 | 0% | 0 | 0
| REPB47715 | COMMUNAL WORKS | D | Nosing: Take off and refix any size or type of nosing to step including drilling and plugging as necessary. |  |  | 5.157 |  | 4329CA | NO | 16 | 9.62 | 153.92 | #VALUE! | #VALUE! | 0 | 8.1039 | 129.6622 | NO | 16 | 8.1039 | 129.6622 | 0% | 0 | 0% | 0 | 0
| REPB47715 | COMMUNAL WORKS | D | Frame: Renew external door frame with softwood door frame, rebated and with fanlight over, to suit any size single door, remove existing door and set aside, remove existing frame and bed new frame in mortar, plugged and screwed to brickwork and point with sealant, rehang door including ease and adjust, refix lock keep including housing out, make good all works disturbed including refix or renew internal beads, architraves etc., glaze to fanlight and decorate to match existing internally and prepare for redecoration externally, and remove waste and debris. |  |  | 5.295 |  | 3411AC | NO | 1 | 197.62 | 197.62 | #VALUE! | #VALUE! | 0 | 175.1901 | 175.1901 | NO | 1 | 175.1901 | 175.1901 | 0% | 0 | 0% | 0 | 0
| REPB47715 | EXTREP | H | [23 empty] | 0
| REPB47715 | EXTREP | D | Wall: Rake out existing joints of brickwork min 12mm and repoint brickwork in mortar to match existing and remove waste and debris. |  |  | 6.91 |  | 1021AA | SM | 3 | 20.13 | 60.39 | #VALUE! | #VALUE! | 0 | 14.5942 | 43.7827 | SM | 3 | 14.5942 | 43.7827 | 0% | 0 | 0% | 0 | 0
| REPB47715 | EXTREP | D | Walls: Wash down, fill in cracks and holes, sand down and apply one coat of stabilising solution and two coats of smooth or textured masonry paint to brickwork surfaces of walls. |  |  | 6.186 |  | 4356BD | SM | 12 | 11.63 | 139.56 | #VALUE! | #VALUE! | 0 | 9.8855 | 118.626 | SM | 12 | 9.8855 | 118.626 | 0% | 0 | 0% | 0 | 0
| REPB47715 | EXTREP | D | Balustrading: Wire brush, prepare for and apply one coat of primer, one undercoat, two coats of gloss paint on ornamental metal balustrading, railings or gates (measured both sides). |  |  | 6.204 |  | 4362EA | SM | 6 | 20.51 | 123.06 | #VALUE! | #VALUE! | 0 | 17.4335 | 104.601 | SM | 6 | 17.4335 | 104.601 | 0% | 0 | 0% | 0 | 0
| REPB47715 | EXTREP | D | Window: Rub down, prepare and apply one undercoat and two coats of gloss paint on existing painted surfaces of wooden windows. (one side and edges). |  |  | 6.249 |  | 4381BB | SM | 22 | 24.54 | 539.88 | #VALUE! | #VALUE! | 0 | 20.859 | 458.898 | SM | 22 | 20.859 | 458.898 | 0% | 0 | 0% | 0 | 0
| REPB47715 | EXTREP | D | Frame: Rub down, prepare and apply one undercoat and two coats of gloss paint on existing painted timber frame ne 300mm girth. |  |  | 6.25 |  | 4381CA | LM | 30 | 5.84 | 175.2 | #VALUE! | #VALUE! | 0 | 4.964 | 148.92 | LM | 30 | 4.964 | 148.92 | 0% | 0 | 0% | 0 | 0
| REPB47715 | EXTREP | D | Door: Rub down, prepare for, and apply three coats decorative wood stain on external surfaces of any size/type of single door(both sides and edges) |  |  | 6.276 |  | 4382DB | IT | 1 | 33.52 | 33.52 | #VALUE! | #VALUE! | 0 | 28.492 | 28.492 | IT | 1 | 28.492 | 28.492 | 0% | 0 | 0% | 0 | 0
| REPB47715 | ROOF | H | [23 empty] | 0
| REPB47715 | [25 empty] | 0
| REPB47715 | WINDOWS | H | [23 empty] | 0
| REPB47715 | WINDOWS | D | Window: Overhaul timber casement window, dismantle as necessary and subsequently reassemble including freeing, easing and adjusting casements to give correct operation, renew sealing gaskets, renew fixing screws, remove, refit or renew ironmongery as necessary, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.89 |  | 3150BA | NO | 5 | 29.05 | 145.25 | #VALUE! | #VALUE! | 0 | 25.7528 | 128.7641 | NO | 5 | 25.7528 | 128.7641 | 0% | 0 | 0% | 0 | 0
| REPB47715 | WINDOWS | D | Window: Overhaul timber sash window, renew staff and parting beads, take out sashes and later rehang on appropriate sized new undyed plaited nylon sash cords, renew pocket pieces, wedge and cramp loose sash frames, oil pulleys, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.9 |  | 3150CA | NO | 6 | 35.61 | 213.66 | #VALUE! | #VALUE! | 0 | 31.5683 | 189.4096 | NO | 6 | 31.5683 | 189.4096 | 0% | 0 | 0% | 0 | 0
| REPB47715 | SCAFFOLD | H | [18 empty] | 0 |  |  |  |  | 0
| REPB47715 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 170 | 12.92 | 2196.4 | #VALUE! | #VALUE! | 0 | 16.4084 | 2789.428 | M2 | 170 | 16.4084 | 2789.428 | 0% | 0 | 0% | 0 | 0
| REPB47715 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 0% | 0 | 0% | 0 | 0
| REPB47715 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 1 | 50 | 50 | #VALUE! | #VALUE! | 0 | 63.5 | 63.5 | unit | 1 | 63.5 | 63.5 | 0% | 0 | 0% | 0 | 0
| REPB47715 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB47715 | ESTATE WORKS | H | [23 empty] | 0
| REPB47715 | FRA WORKS | H | [23 empty] | 0
| REPB47715 | FRA WORKS | D | Door:Renew internal door with any size single half-hour fire check glazed door having 3.2mm luan, white Meranti or other approved plywood facing both sides and 9mm hardwood lipping on long edges, including remove existing door and hinges, remove and refit door stops as necessary, fit and hang new door on 1.50 pairs of 100mm steel butt hinges, make good or alter recesses on frame, door complete with all ironmongery, intumescent strips and smoke seals, glass, make good and prepare door for decoration and make good decorations to frame, and remove waste and debris. |  |  | 13 |  | 3300BD | Item | 2 | 180.78 | 361.56 | #VALUE! | #VALUE! | 0 | 160.2615 | 320.5229 | Item | 2 | 160.2615 | 320.5229 | 0% | 0 | 0% | 0 | 0
| REPB47715 | FRA WORKS | D | Fire Upgrading Coating:Remove all existing defective paint to plastered or rendered wall surfaces back to a solid edge, feather off and repair any defective areas with a high quality filler as necessary, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, wash down, rinse, clean off and apply one full coat of fire upgrading primer at a coverage rate of 10sm per litre, apply two full coats of fire upgrading finish at a coverage rate of 10sm per litre. |  |  | 27 |  | 4801AB | Item | 1 | 22.53 | 22.53 | #VALUE! | #VALUE! | 0 | 19.1505 | 19.1505 | Item | 1 | 19.1505 | 19.1505 | 0% | 0 | 0% | 0 | 0
| REPB47715 | FRA WORKS | D | Fire Upgrading Coating:Strip off existing multi layer paint coatings to existing plastered or rendered soffits with a proprietary paint stripper, scrape off or remove with a proprietary paint scraper, wash down,rinse, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, clean off and apply one full coat of primer at a coverage rate of 10sm per litre, apply one full coats of colourcoat complete with decorative flakes, and apply one full coat of gloss or satin lacquer finish at a coverage rate of 10sm per litre. |  |  | 41 |  | 4804AD | Item | 1 | 29.34 | 29.34 | #VALUE! | #VALUE! | 0 | 24.939 | 24.939 | Item | 1 | 24.939 | 24.939 | 0% | 0 | 0% | 0 | 0
| REPB47715 | FRA WORKS | D | Fire Upgrading Coating:Remove all existing defective paint to general surfaces of woodwork not exceeding 300mm girth, back to a solid edge, feather off and repair any defective areas with a high quality filler as necessary, spot prime filled or bare areas with afire upgrading primer, remove any existing graffiti with a graffiti removal system, wash down, rinse, clean off and apply one full coat of fire upgrading primer at a coverage rate of 10sm per litre, apply two full coats of fire upgrading finish at a coverage rate of 10sm per litre. |  |  | 43 |  | 4805AB | Item | 1 | 20.4 | 20.4 | #VALUE! | #VALUE! | 0 | 17.34 | 17.34 | Item | 1 | 17.34 | 17.34 | 0% | 0 | 0% | 0 | 0
| REPB47715 | FRA WORKS | D | Fire Alarm:Install L2 type fire alarm installation complete to BS5839:Part6 1995, control panel, circuits, call points, automatic detectors and sounders, builders work, make good, test, commission, and remove waste and debris. |  |  | 93 |  | 8711GA | Item | 1 | 550 | 550 | #VALUE! | #VALUE! | 0 | 440 | 440 | Item | 1 | 440 | 440 | 0% | 0 | 0% | 0 | 0
| REPB47715 | FRA WORKS | D | Intumescent Strip:Renew or supply and fix new 22x4mm intumescent strip, half hour application, with integral cold smoke seal and setting into groove in timber frame or door. |  |  | 104 |  | 3431AC | Item | 3 | 3.44 | 10.32 | #VALUE! | #VALUE! | 0 | 3.0496 | 9.1487 | Item | 3 | 3.0496 | 9.1487 | 0% | 0 | 0% | 0 | 0
| REPB47715 | FRA WORKS | D | Smoke Detector:Renew existing with mains operated optical smoke detector with rechargeable DC battery or condensor back up self contained type to BS 5446 kitemark certified with hush button, including back plate and all necessary connections to existing wiring, test and make good on completion, where interlinked detectors are replaced new detectors must be compatible with existing, and remove waste and debris. |  |  | 115 |  | 8720FA | Item | 3 | 70.11 | 210.33 | #VALUE! | #VALUE! | 0 | 56.088 | 168.264 | Item | 3 | 56.088 | 168.264 | 0% | 0 | 0% | 0 | 0
| REPB47715 | FRA WORKS | D | Closer:Renew or supply and fix Perko type concealed door closer screwed to door and frame, including remove and refix door or door stop as necessary. |  |  | 175 |  | 3905BA | Item | 3 | 9.81 | 29.43 | #VALUE! | #VALUE! | 0 | 8.6966 | 26.0897 | Item | 3 | 8.6966 | 26.0897 | 0% | 0 | 0% | 0 | 0
| REPB47715 | FRA WORKS | D | Partition:Supply and erect or renew stud partition comprising ne 50x100mm sole and head plate, noggins and studs fixed with nails or plugged and screwed to walls, and pack out and scribe, 12.5mm butt jointed plasterboard and 3mm plaster skim coat and all labours to both faces. |  |  | 180 |  | 3013AB | Item | 1 | 62.11 | 62.11 | #VALUE! | #VALUE! | 0 | 55.0605 | 55.0605 | Item | 1 | 55.0605 | 55.0605 | 0% | 0 | 0% | 0 | 0
| REPB47715 | FRA WORKS | D | Test:Carry out test of domestic installation to occupied property complete comprising continuity, insulation resistance, polarity, earth fault loop impedance and operation of residual current operated device, disconnect, repair and renew as necessary after removal of illegal wiring and components, and provide report and NICEIC/ECA test certificate to the Client’s Representative, and remove waste and debris. |  |  | 186 |  | 8950AA | Item | 1 | 86.88 | 86.88 | #VALUE! | #VALUE! | 0 | 69.504 | 69.504 | Item | 1 | 69.504 | 69.504 | 0% | 0 | 0% | 0 | 0
| REPB47715 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to the fire alarm system. |  |  | 190 |  | PROV SUM | Item | 1 | 1500 | 1500 | #VALUE! | 1500 |  |  | 1500 | Item | 1 |  | 1500 | 0% | 0 | 0% | 0 | 0
| REPB47715 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to clear waste and debris from fire escape routes. |  |  | 191 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47715 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional fire stopping works |  |  | 192 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47715 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional signage |  |  | 193 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47715 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional electrical works |  |  | 194 |  | PROV SUM | Item | 1 | 350 | 350 | #VALUE! | 350 |  |  | 350 | Item | 1 |  | 350 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 9517.2741 |  |  | TOTAL | 9517.2741 |  | 0 |  | 0 | 0

## 13 Winscombe Terrace
Mulalley & Co Ltd
Camden Better Homes - NW5 Blocks
13 Winscombe Terrace
[10 empty] | ORIGINAL CONTRACT SUM | [8 empty] | PROJECTED FINAL ACCOUNT |  |  |  | MCL TOTAL THIS VALUATION |  | CERTIFIED THIS VALUATION |  | DIFFERENCE
Requirement | REPB47886 | Requirement Type | Rowtype (H=Header, D=Detail) | Description | Works Order Commencement Date | Works Order Completion Date | Specification Ref. Item No.'s | Works Order Delivery Date | SOR Code | SOR Unit | SOR Qty | SOR Cost | Total Cost | Rate (max) | Cost (max) | Modified price | Tendered rate | Tendered total | SOR Unit | SOR Qty | Tendered rate | Tendered total | % COMPLETE | TOTAL | % COMPLETE | TOTAL
| REPB47886 | ENERGY EFFICIENY | H
| REPB47886 | ENERGY EFFICIENY | D | Contractor to access and undertake survey of loft space in accordance with the Project Brief in order to assess level of current loft insulation. Including submittion of a survey report supported by photographic evidance to CM/PM. Where insulation levels are less then 200mm, Contractor to provide cost proposal to upgrade insulation in accordance with NHF SoR Planned Maintenance Version 6.2. |  |  | 9.1 |  | ADD001 | IT | 1 |  |  | #VALUE! | #VALUE! | 0 | 0 | 0 | IT | 1 | 0 | 0 | 0% | 0 | 0% | 0 | 0
| REPB47886 | ENERGY EFFICIENY | D | Insulation:Supply and lay ne 270mm thick insulation quilt to loft area including gain access and moving/replacing contents within loft area in order to undertake work. Item 2270AA |  |  | 9.2 |  | 2270AA | SM | 46.04 | 10.86 | 499.9944 | #VALUE! | #VALUE! | 0 | 8.688 | 399.9955 | SM | 46.04 | 8.688 | 399.9955 | 0% | 0 | 0% | 0 | 0
| REPB47886 | ASBESTOS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47886 | ASBESTOS | D | Refurbishment and Demolition Survey to Full Property (with upto 5 Nr samples) , flat or house any size |  |  | 1.3 |  | A003 | Item | 1 | 234 | 234 | #VALUE! | #VALUE! | 0 | 222.3 | 222.3 | Item | 1 | 222.3 | 222.3 | 0% | 0 | 0% | 0 | 0
| REPB47886 | COMMUNAL WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47886 | COMMUNAL WORKS | D | Hall: Thoroughly clean down all wall and ceiling surfaces to common areas to remove dirt, grease and surface containments, scrape and remove all loose and defective coatings, prime bare areas with one coat of fire retardant primer and apply two coats of Class ‘O’ fire retardant matt paint, prepare and apply two coats of polyurethane lacquer or one undercoat and one gloss coat to all previously decorated timber surfaces to lobby, hall or corridor over 3.00sm ceiling area complete (classified as a single area). |  |  | 5.1 |  | 4540AC | IT | 1 | 480 | 480 | #VALUE! | #VALUE! | 0 | 408 | 408 | IT | 1 | 408 | 408 | 0% | 0 | 0% | 0 | 0
| REPB47886 | EXTREP | H | PROVISIONAL SUM: Sheet Flooring: Supply and lay minimum 2.0mm felt backed vinyl sheet flooring with adhesive to and including supply and lay approved sheet sub base including all necessary cutting, all labours and clean off, and remove waste and debris. | [17 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47886 | EXTREP | D | Wall: Rake out existing joints of brickwork min 12mm and repoint brickwork in mortar to match existing and remove waste and debris. |  |  | 6.91 |  | 1021AA | SM | 2 | 20.13 | 40.26 | #VALUE! | #VALUE! | 0 | 14.5942 | 29.1885 | SM | 2 | 14.5942 | 29.1885 | 0% | 0 | 0% | 0 | 0
| REPB47886 | EXTREP | D | Walls: Wash down, fill in cracks and holes, sand down and apply one undercoat and one coat of gloss paint to rendered or concrete walls. |  |  | 6.197 |  | 4361AB | SM | 6 | 15.71 | 94.26 | #VALUE! | #VALUE! | 0 | 13.3535 | 80.121 | SM | 6 | 13.3535 | 80.121 | 0% | 0 | 0% | 0 | 0
| REPB47886 | EXTREP | D | Balustrading: Wire brush, prepare for and apply one coat of primer, one undercoat, two coats of gloss paint on ornamental metal balustrading, railings or gates (measured both sides). |  |  | 6.204 |  | 4362EA | SM | 5 | 20.51 | 102.55 | #VALUE! | #VALUE! | 0 | 17.4335 | 87.1675 | SM | 5 | 17.4335 | 87.1675 | 0% | 0 | 0% | 0 | 0
| REPB47886 | EXTREP | D | Window: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on surfaces of wooden windowsl (one side and edges). |  |  | 6.236 |  | 4380BA | SM | 10 | 25.87 | 258.7 | #VALUE! | #VALUE! | 0 | 21.9895 | 219.895 | SM | 10 | 21.9895 | 219.895 | 0% | 0 | 0% | 0 | 0
| REPB47886 | EXTREP | D | Frame: Rub down, prepare and apply one coat of primer, one undercoat and two coats of gloss paint on timber frame ne 300mm girth. |  |  | 6.237 |  | 4380CA | LM | 14 | 6.28 | 87.92 | #VALUE! | #VALUE! | 0 | 5.338 | 74.732 | LM | 14 | 5.338 | 74.732 | 0% | 0 | 0% | 0 | 0
| REPB47886 | EXTREP | D | Door: Rub down, prepare for and apply one coat of primer, one undercoat and two coats of gloss paint to all surfaces of any size or type of single glazed timber door. (one sides and edges). |  |  | 6.238 |  | 4380DA | IT | 3 | 20.71 | 62.13 | #VALUE! | #VALUE! | 0 | 17.6035 | 52.8105 | IT | 3 | 17.6035 | 52.8105 | 0% | 0 | 0% | 0 | 0
| REPB47886 | ROOF | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47886 | [20 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47886 | WINDOWS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47886 | WINDOWS | D | Window: Overhaul timber casement window, dismantle as necessary and subsequently reassemble including freeing, easing and adjusting casements to give correct operation, renew sealing gaskets, renew fixing screws, remove, refit or renew ironmongery as necessary, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.89 |  | 3150BA | NO | 2 | 29.05 | 58.1 | #VALUE! | #VALUE! | 0 | 25.7528 | 51.5056 | NO | 2 | 25.7528 | 51.5056 | 0% | 0 | 0% | 0 | 0
| REPB47886 | WINDOWS | D | Window: Overhaul timber sash window, renew staff and parting beads, take out sashes and later rehang on appropriate sized new undyed plaited nylon sash cords, renew pocket pieces, wedge and cramp loose sash frames, oil pulleys, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations internally to match existing and prepare for redecoration externally, and remove waste and debris. |  |  | 4.9 |  | 3150CA | NO | 5 | 35.61 | 178.05 | #VALUE! | #VALUE! | 0 | 31.5683 | 157.8413 | NO | 5 | 31.5683 | 157.8413 | 0% | 0 | 0% | 0 | 0
| REPB47886 | SCAFFOLD | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47886 | SCAFFOLD | D | Standard Scaffold item: erect; dismantle; basic independent tied working scaffolding; 5 boards wide, including hire period; completely accessible; debris netting to all elevations; double boarded and polythene included as necessary, any fan(s) included as required; rope plus wheel for lifting operations; 3rd handrail included whenever necessary; as per applicable regulations (applies to up to 5 storeys). Measured up to second handrail and by the middle of the scaffold (equidistant from the inside/outside face) including design when required. Rate to include for 12 week hire |  |  | 2.1 |  | SC001 | M2 | 140 | 12.92 | 1808.8 | #VALUE! | #VALUE! | 0 | 16.4084 | 2297.176 | M2 | 140 | 16.4084 | 2297.176 | 0% | 0 | 0% | 0 | 0
| REPB47886 | SCAFFOLD | D | Scaffold alarm - 1 x sounder, 2 x PIR 1 X key pad (Divided by Number of properties if continuous scaffolds) |  |  | 2.5 |  | SC005 | unit | 1 | 420 | 420 | #VALUE! | #VALUE! | 0 | 533.4 | 533.4 | unit | 1 | 533.4 | 533.4 | 0% | 0 | 0% | 0 | 0
| REPB47886 | SCAFFOLD | D | E/O for additional PIRS |  |  | 2.6 |  | SC007 | unit | 1 | 50 | 50 | #VALUE! | #VALUE! | 0 | 63.5 | 63.5 | unit | 1 | 63.5 | 63.5 | 0% | 0 | 0% | 0 | 0
| REPB47886 | SCAFFOLD | D | Scaffold taken through property (protection to surfaces included) |  |  | 2.16 |  | SC016 | unit | 1 | 379.8 | 379.8 | #VALUE! | #VALUE! | 0 | 482.346 | 482.346 | unit | 1 | 482.346 | 482.346 | 0% | 0 | 0% | 0 | 0
| REPB47886 | SCAFFOLD | D | Additional Hire if required - % per week of total scaffolding costs. This is to be applied in the event an agreed programme exceeding the duration set out above. An example would be large low level blocks of 4 storeys requiring a large programme duration |  |  |  |  | SC024 | unit |  | 0.0483 | 0 | #VALUE! | #VALUE! | #N/A | #N/A | 0 | unit |  | #N/A |  | 0% | 0 | 0% | 0 | 0
| REPB47886 | ESTATE WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47886 | FRA WORKS | H | [18 empty] | 0 | 0% | 0 | 0% | 0 | 0
| REPB47886 | FRA WORKS | D | Fire Alarm:Install L2 type fire alarm installation complete to BS5839:Part6 1995, control panel, circuits, call points, automatic detectors and sounders, builders work, make good, test, commission, and remove waste and debris. |  |  | 93 |  | 8711GA | Item | 1 | 550 | 550 | #VALUE! | #VALUE! | 0 | 440 | 440 | Item | 1 | 440 | 440 | 0% | 0 | 0% | 0 | 0
| REPB47886 | FRA WORKS | D | Intumescent Strip:Renew or supply and fix new 22x4mm intumescent strip, half hour application, with integral cold smoke seal and setting into groove in timber frame or door. |  |  | 104 |  | 3431AC | Item | 2 | 3.44 | 6.88 | #VALUE! | #VALUE! | 0 | 3.0496 | 6.0991 | Item | 2 | 3.0496 | 6.0991 | 0% | 0 | 0% | 0 | 0
| REPB47886 | FRA WORKS | D | Smoke Detector:Renew existing with mains operated optical smoke detector with rechargeable DC battery or condensor back up self contained type to BS 5446 kitemark certified with hush button, including back plate and all necessary connections to existing wiring, test and make good on completion, where interlinked detectors are replaced new detectors must be compatible with existing, and remove waste and debris. |  |  | 115 |  | 8720FA | Item | 2 | 70.11 | 140.22 | #VALUE! | #VALUE! | 0 | 56.088 | 112.176 | Item | 2 | 56.088 | 112.176 | 0% | 0 | 0% | 0 | 0
| REPB47886 | FRA WORKS | D | Closer:Renew or supply and fix Perko type concealed door closer screwed to door and frame, including remove and refix door or door stop as necessary. |  |  | 175 |  | 3905BA | Item | 2 | 9.81 | 19.62 | #VALUE! | #VALUE! | 0 | 8.6966 | 17.3931 | Item | 2 | 8.6966 | 17.3931 | 0% | 0 | 0% | 0 | 0
| REPB47886 | FRA WORKS | D | Test:Carry out test of domestic installation to occupied property complete comprising continuity, insulation resistance, polarity, earth fault loop impedance and operation of residual current operated device, disconnect, repair and renew as necessary after removal of illegal wiring and components, and provide report and NICEIC/ECA test certificate to the Client’s Representative, and remove waste and debris. |  |  | 186 |  | 8950AA | Item | 1 | 86.88 | 86.88 | #VALUE! | #VALUE! | 0 | 69.504 | 69.504 | Item | 1 | 69.504 | 69.504 | 0% | 0 | 0% | 0 | 0
| REPB47886 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to the fire alarm system. |  |  | 190 |  | PROV SUM | Item | 1 | 1500 | 1500 | #VALUE! | 1500 |  |  | 1500 | Item | 1 |  | 1500 | 0% | 0 | 0% | 0 | 0
| REPB47886 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional works to clear waste and debris from fire escape routes. |  |  | 191 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47886 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional fire stopping works |  |  | 192 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47886 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional signage |  |  | 193 |  | PROV SUM | Item | 1 | 100 | 100 | #VALUE! | 100 |  |  | 100 | Item | 1 |  | 100 | 0% | 0 | 0% | 0 | 0
| REPB47886 | FRA WORKS | D | Provisional Sum: Allow provisional sum for additional electrical works |  |  | 194 |  | PROV SUM | Item | 1 | 350 | 350 | #VALUE! | 350 |  |  | 350 | Item | 1 |  | 350 | 0% | 0 | 0% | 0 | 0
[17 empty] | TOTAL | 7955.1512 |  |  | TOTAL | 7955.1512 |  | 0 |  | 0 | 0