## Sheet1
Program of Construction Works - 28 Kylemore Road NW6 2PT | January |  |  |  | 2020 | February |  |  | 2020 | March |  |  | 2020 | April | Program of Construction Works - 28 Kylemore Road NW6 2PT | April |  | 2020 | May |  |  |  | 2020 | June |  |  | 2020 | July
Work Stage | Wk 1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | W13 | Wk14 | Work Stage | Wk15 | Wk16 | Wk17 | Wk18 | Wk19 | Wk20 | Wk21 | Wk22 | Wk23 | Wk24 | Wk25 | Wk26 | Wk27
Party Wall Notices (To be agreed before commencement) | Wk 1: XXXXX; Wk2: XXXXX
Site set up and clearance | Wk2: XXXXX
Demolitions and Structural Work (Not Party Wall Associated) | Wk3: XXXXX; Wk4: XXXXX
Re-Route Gas & Water Suppies into building (1 day each) | bar: Wk3
Underpinning (Party Wall Notices Required) | Wk6: XXXXX; Wk7: XXXXX; Wk8: XXXXX; Wk9: XXXXX; Wk10: XXXXX
Front Lightwell (Party Wall Notices Required) | Wk10: XXXXX; Wk11: XXXXX; Wk12: XXXXX; W13: XXXXX; Wk14: XXXXX
Rear Extension Excavations (Party Wall Notices Required) | Wk6: XXXXX
Rear Extension Brickwork/Blockwork | Wk7: XXXXX; Wk8: XXXXX
Rear Extension Roof | Wk9: XXXXX
Rear Extension Knock Through | Wk10: XXXXX
Structutal Work (Party Wall Notices Required) | Wk6: XXXXX; Wk10: XXXXX; Wk11: XXXXX
New Drainage | Wk11: XXXXX
New Floor Constructions | Wk11: XXXXX; Wk12: XXXXX; W13: XXXXX
Lower Ground Floor Tanking Membrane (Walls & Floors) | Wk14: XXXXX
External Windows and Doors | Wk14: XXXXX | External Windows and Doors | XXXXX
Internal Non Load Bearing Partitions | Wk5: XXXXX | Internal Non Load Bearing Partitions | XXXXX
First Fix Electrical | [14 empty] | First Fix Electrical | XXXXX | XXXXX | XXXXX
First Fix Plumbing | Wk14: XXXXX | First Fix Plumbing | XXXXX | XXXXX
Acoustic Insulation | [14 empty] | Acoustic Insulation |  | XXXXX | XXXXX
Internal Door Frames, Plasterboard & Plaster | [14 empty] | Internal Door Frames, Plasterboard & Plaster |  |  | XXXXX | XXXXX | XXXXX
Kitchen Installation | [14 empty] | Kitchen Installation |  |  |  |  | XXXXX | XXXXX
Bathroom Installations | [14 empty] | Bathroom Installations |  |  |  |  | XXXXX | XXXXX
Second Fix Plumbing | [14 empty] | Second Fix Plumbing | [5 empty] | XXXXX | XXXXX
Second Fix Electrical | [14 empty] | Second Fix Electrical | [6 empty] | XXXXX | XXXXX
Internal Doors, Architraves, Skirtings and the like | [14 empty] | Internal Doors, Architraves, Skirtings and the like | [6 empty] | XXXXX | XXXXX | XXXXX
Decoration Internal | [14 empty] | Decoration Internal | [7 empty] | XXXXX | XXXXX
External Works - Front & Rear Gardens | [14 empty] | External Works - Front & Rear Gardens | [7 empty] | XXXXX | XXXXX
Decoration External | [14 empty] | Decoration External | [8 empty] | XXXXX | XXXXX
Final Snagging and Clean Down | [14 empty] | Final Snagging and Clean Down | [10 empty] | XXXXX