## Year 1
Kiln Place
Item | Feature | Task Description | Freq | Work Programme
 | time axis 2020-08-24 to 2021-08-16
 | time axis 2020-08-24 to 2021-08-16
1 | Inspection / Quality Assurance
1.1 | Site wide Inspection | Visit to record condition of site features, identify and record issues and defects. Record and report plant condition and failures, and soil moisture levels. | 26 | bar: 2020-08-24 to 2021-08-16
1.2 | Plant Failures Inspection | Inspection for plant failures | 1 | bar: 2020-08-24 to 2021-08-16
1.3 | Maintenance Plan | 1 year maintenance plan to be submitted. | 1 | bar: 2020-08-24 to 2021-08-16
2 | Trees
2.1 | Trees | Weed Control | 26 | bar: 2020-08-31; 2020-09-14; 2020-09-28; 2020-10-12; 2020-10-26; 2020-11-09; 2020-11-23; 2020-12-07; 2020-12-21; 2021-01-04; 2021-01-18; 2021-02-01; 2021-02-15; 2021-03-01; 2021-03-15; 2021-03-29; 2021-04-12; 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19; 2021-08-02; 2021-08-16
2.2 | Trees | Fertiliser | 1 | bar: 2021-05-10
2.3 | Trees | Mulching | 2 | bar: 2020-10-12; 2021-04-12
2.4 | Trees | Remove stakes | 1 | bar: 2021-08-09
2.5 | Trees | Pruning | 1 | bar: 2020-11-02
2.6 | Trees | Watering (As required) | 13 | bar: 2020-08-24; 2020-09-07; 2020-09-21; 2021-04-12; 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19; 2021-08-02; 2021-08-16
3 | Hedges and Native Planting
3.1 | Hedges and Native Planting | Hoeing and weed control | 26 | bar: 2020-08-24 to 2021-08-16
3.2 | Hedges and Native Planting | Apply fertiliser | 2 | bar: 2020-08-24 to 2021-08-16
3.3 | Hedges and Native Planting | Hard Pruning to aid establishment | 3 | bar: 2020-08-24 to 2021-08-16
3.4 | Hedges and Native Planting | Plant Replacement | 1 | bar: 2020-08-24 to 2021-08-16
3.5 | Hedges and Native Planting | Mulching | 1 | bar: 2020-08-24 to 2021-08-16
3.6 | Hedges and Native Planting | Watering (As required) | 13 | bar: 2020-08-24 to 2021-08-16
4 | Ornamental shrub and herbaceous planting
4.1 | Ornamental Planting | Forking and light cultivation | 3 | bar: 2020-11-09; 2021-03-01; 2021-06-21
4.2 | Ornamental Planting | Hoeing and weed control | 13 | bar: 2020-08-31; 2020-09-28; 2020-10-26; 2020-11-23; 2020-12-21; 2021-01-18; 2021-02-15; 2021-03-15; 2021-04-12; 2021-05-10; 2021-06-07; 2021-07-05; 2021-08-02
4.3 | Ornamental Planting | Apply fertiliser | 2 | bar: 2020-09-14; 2021-04-12
4.4 | Ornamental Planting | Pruning, deadheading and staking/tying | 4 | bar: 2020-11-09; 2021-03-01; 2021-04-26; 2021-06-21
4.5 | Ornamental Planting | Herbaceous cut down to removal dead growth and stems | 1 | bar: 2021-03-01
4.6 | Ornamental Planting | Mulching | 1 | bar: 2021-04-12
4.7 | Ornamental Planting | Plant Replacement | 1 | bar: 2020-11-23
4.8 | Ornamental Planting | Watering (As required) | 13 | bar: 2020-08-24; 2020-09-07; 2020-09-21; 2021-04-12; 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19; 2021-08-02; 2021-08-16

## Year 2
Kiln Place
Item | Feature | Task Description | Freq | Work Programme
 | time axis 2020-08-24 to 2021-08-16
 | time axis 2020-08-24 to 2021-08-16
1 | Inspection / Quality Assurance
1.1 | Site wide Inspection | Visit to record condition of site features, identify and record issues and defects. Record and report plant condition and failures, and soil moisture levels. | 26 | bar: 2020-08-24 to 2021-08-16
1.2 | Plant Failures Inspection | Inspection for plant failures | 1 | bar: 2020-08-24 to 2021-08-16
1.3 | Maintenance Plan | 1 year maintenance plan to be submitted. | 1 | bar: 2020-08-24 to 2021-08-16
2 | Trees
2.1 | Trees | Weed Control | 26 | bar: 2020-08-31; 2020-09-14; 2020-09-28; 2020-10-12; 2020-10-26; 2020-11-09; 2020-11-23; 2020-12-07; 2020-12-21; 2021-01-04; 2021-01-18; 2021-02-01; 2021-02-15; 2021-03-01; 2021-03-15; 2021-03-29; 2021-04-12; 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19; 2021-08-02; 2021-08-16
2.2 | Trees | Fertiliser | 1 | bar: 2021-05-10
2.3 | Trees | Mulching | 2 | bar: 2020-10-12; 2021-04-12
2.4 | Trees | Remove stakes | 1 | bar: 2021-08-09
2.5 | Trees | Pruning | 1 | bar: 2020-11-02
2.6 | Trees | Watering (As required) | 13 | bar: 2020-08-24; 2020-09-07; 2020-09-21; 2021-04-12; 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19; 2021-08-02; 2021-08-16
3 | Hedges and Native Planting
3.1 | Hedges and Native Planting | Hoeing and weed control | 26 | bar: 2020-08-24 to 2021-08-16
3.2 | Hedges and Native Planting | Apply fertiliser | 2 | bar: 2020-08-24 to 2021-08-16
3.3 | Hedges and Native Planting | Plant Replacement | 1 | bar: 2020-08-24 to 2021-08-16
3.4 | Hedges and Native Planting | Mulching | 1 | bar: 2020-08-24 to 2021-08-16
3.5 | Hedges and Native Planting | Watering (As required) | 13 | bar: 2020-08-24 to 2021-08-16
4 | Ornamental shrub and herbaceous planting
4.1 | Ornamental Planting | Forking and light cultivation | 3 | bar: 2020-11-09; 2021-03-01; 2021-06-21
4.2 | Ornamental Planting | Hoeing and weed control | 13 | bar: 2020-08-31; 2020-09-28; 2020-10-26; 2020-11-23; 2020-12-21; 2021-01-18; 2021-02-15; 2021-03-15; 2021-04-12; 2021-05-10; 2021-06-07; 2021-07-05; 2021-08-02
4.3 | Ornamental Planting | Apply fertiliser | 2 | bar: 2020-09-14; 2021-04-12
4.4 | Ornamental Planting | Pruning, deadheading and staking/tying | 4 | bar: 2020-11-09; 2021-03-01; 2021-04-26; 2021-06-21
4.5 | Ornamental Planting | Herbaceous cut down to removal dead growth and stems | 1 | bar: 2021-03-01
4.6 | Ornamental Planting | Mulching | 1 | bar: 2021-04-12
4.7 | Ornamental Planting | Plant Replacement | 1 | bar: 2020-11-23
4.8 | Ornamental Planting | Watering (As required) | 13 | bar: 2020-08-24; 2020-09-07; 2020-09-21; 2021-04-12; 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19; 2021-08-02; 2021-08-16