## 2019-2022
| MAITLAND PARK | [19 empty] | Contract 22nd Feb 2021- 18th August 2022 ( 74 weeks) value £38 Million
SOCIAL VALUE STAKEHOLDER ENGAGEMENT PLAN
[6 empty] | Activities we were able to do |  |  | Activities we are not able to do |  |  | Activities still to do |  |  | Community Notifications
|  |  |  | 2019 |  |  |  | 2020 | [11 empty] | 2021 | [11 empty] | 2022
|  |  |  | -4 | -3 | -2 | -1 | 1 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
|  |  |  | PCSA September 2019 - September 2020 ( demolition - now till December 2020) | [16 empty] | Phase 1 - Year 1
Works / Activities |  |  |  | September | October | November | December | January | February | March | April | May | July | July | August | September | October | November | December | January | February | March | April | May | June | July | August | Sept | Oct | November | December | January | February | March | April | May | June | July | August
COMMUNITY
Newsletters (monthly once on site) | [13 empty] | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | March | April | May | June | July | August | Sept
Stakeholder Site Visits
CWG Meetings | [10 empty] | CWG Meetings |  |  | 2020-07-01: CWG Meetings; 2020-10-01: CWG Meetings; 2021-01-01: CWG Meetings; 2021-04-01: CWG Meetings; 2021-08-01: CWG Meetings; 2021-11-01: CWG Meetings; 2022-02-01: CWG Meetings |  | CWG Meetings |  | CWG Meetings |  | CWG Meetings
Events (Topping out, etc.)
Capital Clean up day (volunteering)
Clothes Collection point for Salvation Army
Mayors Charity appeal
Community Open Day and events | [15 empty] | 27/9/2020 Coffee Macmillan event | 1-28th October - Stop Smoking month 10th October Mental Health Awareness Day 1-31st October Breast Cancer Awareness Month | 1-30th November November Men's Health Month & 16-22nd Road Safety week | 1st December - Worlds Aid Day & 11th December Red/Christmas Jumper Day Save the Children | Get fit for January and Dry January | LGBTQ month | International Women's Day | Street Awareness month and Walk to work day 4/4/2021 | Dementia Awareness Week | Men's Health Week | TBD | TBd | TBD | TBd | TBd | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Community Notifications | [13 empty] | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin | Monthly newsletter or bulletin
Community Days x 4 per month
Donation of Rose Bushes by Bouygues
EDUCATION
Educational Engagement working with Kingscross construction Centre | [13 empty] | 2020-11-01: Virtual Working with Kingscross Construction Centre; 2020-12-01: Virtual Working with Kingscross Construction Centre; 2021-02-01: Virtual Working with Kingscross Construction Centre; 2021-04-01: Virtual Working with Kingscross Construction Centre; 2021-06-01: Virtual Working with Kingscross Construction Centre; 2021-08-01: Virtual Working with Kingscross Construction Centre; 2021-10-01: Virtual Working with Kingscross Construction Centre; 2021-12-01: Virtual Working with Kingscross Construction Centre; 2022-02-01: Virtual Working with Kingscross Construction Centre |  | Virtual Working with Kingscross Construction Centre |  | Virtual Working with Kingscross Construction Centre |  | Virtual Working with Kingscross Construction Centre
Primary
Secondary
Further Education
University | [13 empty] | 2021-01-01: Graduate Taken on Via Southbank University
Careers Events and Women in construction | [13 empty] | 2020-11-01: Careers Events and Women in construction; 2020-12-01: Careers Events and Women in construction; 2021-02-01: Careers Events and Women in construction; 2021-04-01: Careers Events and Women in construction; 2021-07-01: Careers Events and Women in construction; 2021-10-01: Careers Events and Women in construction; 2022-01-01: Careers Events and Women in construction |  | Careers Events and Women in construction |  |  | Careers Events and Women in construction
Curriculum Enrichment (schools)
Skills and Employment Section 106 |  | Target | Actual
Meet the Buyer Event |  | 2 | [11 empty] | 2021-01-01: Meet the Biyer Event; 2021-09-01: Meet the Biyer Event
Work Experience Placements (16) |  | 16
Locally procured goods and service 10%ly procured |  | 10%
Local Employment 20% |  | 20%
Jobs Created - Apprentices (9) |  | 9
Job Created - Graduates (1) |  | 1
Career 1-2-1 sessions |  | 9 events | 1 | [10 empty] | 2020-07-01: Virtual Mentoring via Women in Construction Camden resident for 4 week sin July 2020
Workshops |  | 4