## RAM - Plot 3
Task Information Delivery Plan (TIDP) - Plot 3 |  |  | Template Rev: | P01 (20/03/2020) |  |  |  | STAGE 2 PREPARATION & BRIEF | [8 empty] | STAGE 3 DEVELOPED DESIGN | [8 empty] | STAGE 4a TECHNICAL DESIGN | [8 empty] | STAGE 4b TECHNICAL DESIGN | [8 empty] | STAGE 5 CONSTRUCTION | [8 empty] | STAGE 6 HANDOVER
|  |  | File Name: | BEMP-RAM-P3-XX-SH-S-XX-0001
Example File Name: |  |  | Issue Date: | 2020-11-20 | Fields with this hatch should be left empty |  |  | DIM (Design Information Model), 2D Drawings and Documents | [8 empty] | DIM (Design Information Model), 2D Drawings and Documents | [8 empty] | DIM (Design Information Model), 2D Drawings and Documents | [8 empty] | DIM (Design Information Model), 2D Drawings and Documents | [8 empty] | PIM (Project Information Model), 2D Drawings and Documents | [8 empty] | AIM (Asset Information Model), 2D Drawings and Documents
|  |  | Rev: | P02-P05
Package / Series | File Name | Exchange Formats | Type | Description | Company | Document Register | Stage Gateway | Stage 2 S3 Required Date | Stage 2 S4 Required Date | Stage 2 A1 Required Date | Stage 2 S3 Issued Date | Stage 2 S4 Issued Date | Stage 2 A1 Issued Date | Stage 2 Status | Stage 2 Revision | Stage 2 Review Status | Stage 3 S3 Required Date | Stage 3 S4 Required Date | Stage 3 A1 Required Date | Stage 3 S3 Issued Date | Stage 3 S4 Issued Date | Stage 3 A1 Issued Date | Stage 3 Status | Stage 3 Revision | Stage 3 Review Status | Stage 4a S3 Required Date | Stage 4a S4 Required Date | Stage 4a A1 Required Date | Stage 4a S3 Issued Date | Stage 4a S4 Issued Date | Stage 4a A1 Issued Date | Stage 4a Status | Stage 4a Revision | Stage 4a Review Status | Stage 4b S3 Required Date | Stage 4b S4 Required Date | Stage 4b A1 Required Date | Stage 4b S3 Issued Date | Stage 4b S4 Issued Date | Stage 4b A1 Issued Date | Stage 4b Status | Stage 4b Revision | Stage 4b Review Status | Stage 5 S3 Required Date | Stage 5 S4 Required Date | Stage 5 A1 Required Date | Stage 5 S3 Issued Date | Stage 5 S4 Issued Date | Stage 5 A1 Issued Date | Stage 5 Status | Stage 5 Revision | Stage 5 Review Status | Stage 6 S3 Required Date | Stage 6 S4 Required Date | Stage 6 A1 Required Date | Stage 6 S3 Issued Date | Stage 6 S4 Issued Date | Stage 6 A1 Issued Date | Stage 6 Status | Stage 6 Revision | Stage 6 Review Status | Comments
3D model | BEMP-RAM-P3-ZZ-M3-S-00-0001 | RVT | Model | Structural Model Plot 3 Model | Ramboll | Plot 3 |  | 2020-04-17 | [8 empty] | 2020-11-20
3D model | BEMP-RAM-P3-ZZ-MR-S-00-0001 | IFC | Model | Structural Model Plot 3 Model | Ramboll | Plot 3 |  | 2020-04-17 | [8 empty] | 2020-11-20
Substructure | BEMP-RAM-P3-FN-DR-S-20-0050 | PDF | Drawing | 3D views | Ramboll | Plot 3 |  | 2020-04-09 | 2020-04-17 | [7 empty] | 2020-11-20
Substructure | BEMP-RAM-P3-FN-DR-S-20-0600 | PDF | Drawing | Foundation GA | Ramboll | Plot 3 |  | 2020-04-09 | 2020-04-17 | [7 empty] | 2020-11-20
Substructure | BEMP-RAM-P3-B2-DR-S-20-0700 | PDF | Drawing | Basement Level 2 GA | Ramboll | Plot 3 |  | 2020-04-09 | 2020-04-17 | [7 empty] | 2020-11-20
Substructure | BEMP-RAM-P3-B1-DR-S-20-0900 | PDF | Drawing | Basement Level 1 GA | Ramboll | Plot 3 |  | 2020-04-09 | 2020-04-17 | [7 empty] | 2020-11-20
Substructure | BEMP-RAM-P3-BM-DR-S-20-0950 | PDF | Drawing | Basement Level B1 Mezzanine GA | Ramboll | Plot 3 |  | 2020-04-09 | 2020-04-17 | [7 empty] | 2020-11-20
Substructure | BEMP-RAM-P3-00-DR-S-20-1000 | PDF | Drawing | Ground Floor GA | Ramboll | Plot 3 |  | 2020-04-09 | 2020-04-17 | [7 empty] | 2020-11-20
Substructure | BEMP-RAM-P3-ZZ-DR-S-20-2101 | PDF | Drawing | Substructure Sections and Details Sheet 01 | Ramboll | Plot 3 |  | 2020-04-09 | 2020-04-17 | [7 empty] | 2020-11-20
Substructure | BEMP-RAM-P3-ZZ-DR-S-20-2102 | PDF | Drawing | Substructure Sections and Details Sheet 02 | Ramboll | Plot 3 |  | 2020-04-09 | 2020-04-17 | [7 empty] | 2020-11-20
Superstructure | BEMP-RAM-P3-00-DR-S-20-1100 | PDF | Drawing | First Floor GA | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Superstructure | BEMP-RAM-P3-00-DR-S-20-1200 | PDF | Drawing | Second Floor GA | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Superstructure | BEMP-RAM-P3-00-DR-S-20-1300 | PDF | Drawing | Third Floor GA | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Superstructure | BEMP-RAM-P3-00-DR-S-20-1400 | PDF | Drawing | Fourth Floor GA | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Superstructure | BEMP-RAM-P3-00-DR-S-20-1500 | PDF | Drawing | Fifth Floor GA | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Superstructure | BEMP-RAM-P3-00-DR-S-20-1600 | PDF | Drawing | Sixth Floor GA | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Superstructure | BEMP-RAM-P3-00-DR-S-20-1700 | PDF | Drawing | Roof GA | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Substructure | BEMP-RAM-P3-ZZ-DR-S-20-2103 | PDF | Drawing | Substructure Sections and Details Sheet 03 | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Report | BEMP-RAM-P3-XX-RP-CG-00-0001 | PDF | Report | Basement Impact Assessment (Plot 1&3) | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Report | BEMP-RAM-SW-XX-RP-CG-00-0014 | PDF | Report | Geotechnical and Geoenvironmental Desk Study | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Report | BEMP-RAM-SW-XX-RP-EC-91-0013 | PDF | Report | Flood Risk Assessment | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Report | BEMP-RAM-P2-XX-RP-S-00-2002 | PDF | Report | Structural Strategy Statement | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Report | BEMP-RAM-P1-XX-RP-C-00-0022 | PDF | Report | Drainage Strategy | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Drainage | BEMP-RAM-SW-00-DR-C-51-0110 | PDF | Drawing | Surface and Foul Water Drainage Layout Level 00 - Site Wide | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Drainage | BEMP-RAM-SW-B1-DR-C-51-0111 | PDF | Drawing | Surface and Foul Water Drainage Layout Basement 1 - Site Wide | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Drainage | BEMP-RAM-SW-B2-DR-C-51-0112 | PDF | Drawing | Surface and Foul Water Drainage Layout Basement 2 - Site Wide | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Drainage | BEMP-RAM-SW-XX-DR-C-50-0100 | PDF | Drawing | Surface and Foul Water Drainage Details - Sheet 1 | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Drainage | BEMP-RAM-SW-XX-DR-C-50-0101 | PDF | Drawing | Surface and Foul Water Drainage Details - Sheet 2 | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Drainage | BEMP-RAM-SW-XX-DR-C-50-0102 | PDF | Drawing | Surface and Foul Water Drainage Details - Sheet 3 | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Drainage | BEMP-RAM-SW-XX-DR-C-50-0103 | PDF | Drawing | Surface and Foul Water Drainage Details - Sheet 4 | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Drainage | BEMP-RAM-SW-XX-DR-C-97-0100 | PDF | Drawing | Pavement Layout | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Drainage | BEMP-RAM-SW-XX-DR-C-97-0101 | PDF | Drawing | Pavement Build-up Details | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Drainage | BEMP-RAM-SW-XX-DR-C-97-0102 | PDF | Drawing | Pavement Kerb Details | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Drainage | BEMP-RAM-SW-XX-DR-C-97-0103 | PDF | Drawing | Kerb Layout Plan | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Drainage | BEMP-RAM-SW-XX-SH-C-50-0001 | PDF | Drawing | Surface, Lab and Foul Water Manhole Schedule | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Drainage | BEMP-RAM-SW-ZZ-DR-C-51-0103 | PDF | Drawing | Surface and Foul Water Drainage Layout Roof Level | Ramboll | Plot 3 | [10 empty] | 2020-11-20
Note on I10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Drawings will be issued for costing on 09/04, with formal Stage 2 issued on 17/04. Applies to all drawings.

## Pick List
Document Register | Stage
Plot 1 | Stage 3
Plot 2 | Stage 4
Plot 3 | Stage 4a
Site Wide | Stage 4b
Not Required | Stage 5
Stage 6