**Construction/ Demolition Management Plan**

pro forma

**Contents**

**Revisions 3**

**Introduction 4**

**Timeframe 6**

[**Contact**](#_Contact) **7**

[**Site**](#_Site) **9**

[**Community liaison**](#_Community_Liaison) **12**

[**Transport**](#_Transport) **14**

[**Environment**](#_Environment) **26**

**Agreement 31**

# Revisions & additional material

Please list all iterations here:

|  |  |  |
| --- | --- | --- |
| **Date** | **Version** | **Produced by** |
| **02/08/2021** | **V1** | **Esmail Ali, PMA Traffic (Consultant)** |
| **15/06/2022** | **V2** | **Mark Skehill, Sygnet Style Ltd (Main Contractor)** |
| **22/07/2022** | **V3** | **Mark Skehill, Sygnet Style Ltd (Main Contractor)** |
| **27/07/2022** | **V4** | **Mark Skehill, Sygnet Style Ltd (Main Contractor)** |
| **22/08/2022** | **V5** | **Mark Skehill, Sygnet Style Ltd (Main Contractor)** |
| **2/09/2022** | **V6** | **Mark Skehill, Sygnet Style Ltd (Main Contractor)** |
| **5/09/2022** | **V7** | **Mark Skehill, Sygnet Style Ltd (Main Contractor)** |
|  |  |  |

**Additional sheets**

Please note – the review process will be quicker if these are submitted as Word documents or searchable PDFs.

|  |  |  |
| --- | --- | --- |
| **Date** | **Version** | **Produced by** |
| 02/08/2021 | Figure 1. Site Location Plans | PMA |
| 02/08/2021 | Figure 2. Local Highway Network & Preliminary Construction Site Plan | PMA |
| 02/08/2021 | Figure 3. Construction Vehicle Routing Plan | PMA |
| 02/08/2021 | Figure 6. Swept Path Analysis; 7.5t Box Van | PMA |
| 05/09/2021 | Figure 7. Swept Path Analysis; 6m3 Concrete truck | PMA |

# Introduction

The purpose of the **Construction Management Plan (CMP)** is to help developers to minimise construction impacts, and relates to all construction activity both on and off site that impacts on the wider environment.

It is intended to be a live document whereby different stages will be completed and submitted for application as the development progresses.

The completed and signed CMP must address the way in which any impacts associated with the proposed works, and any cumulative impacts of other nearby construction sites, will be mitigated and managed. The level of detail required in a CMP will depend on the scale and nature of development. Further policy guidance is set out in Camden Planning Guidance **(CPG)** 6: Amenity and **(CPG)** 8: Planning Obligations.

This CMP follows the best practice guidelines as described in the [Construction Logistics and Community Safety](https://www.clocs.org.uk/) (**CLOCS**) Standard and the [Guide for Contractors Working in Camden.](https://www.camden.gov.uk/documents/20142/1269042/Guide+for+Contractors+in+Camden.pdf/18b7bb06-119e-9957-7037-fdb633f17ae6)

Camden charges a [fee](https://www.camden.gov.uk/documents/20142/1269042/3.+Construction+and+Demolition+Management+Plans+-+updated+Implementation+Support+Contribution+levels.pdf/6375c32e-9c58-91f0-219f-268269143a6c) for the review and ongoing monitoring of CMPs. This is calculated on an individual basis according to the predicted officer time required to manage this process for a given site.

The approved contents of this CMP must be complied with unless otherwise agreed with the Council in writing. The project manager shall work with the Council to review this CMP if problems arise during construction. Any future revised plan must also be approved by the Council and complied with thereafter.



It should be noted that any agreed CMPdoes not prejudice or override the need to obtain any separate consents or approvals such as road closures or hoarding licences.

If your scheme involves any demolition, you need to make an application to the Council’s Building Control Service. Please complete the “[**Demolition Notice**](https://www.camden.gov.uk/apply-for-building-control-camden)**.**”

Please complete the questions below with additional sheets, drawings and plans as required. The boxes will expand to accommodate the information provided, so please provide as much information as is necessary. It is preferable if this document, and all additional documents, are completed electronically and submitted as Word files to allow comments to be easily documented. These should be clearly referenced/linked to from the CMP. Please only provide the information requested that is relevant to a particular section.

(Note the term 'vehicles' used in this document refers to all vehicles associated with the implementation of the development, e.g. demolition, site clearance, delivery of plant & materials, construction etc.)

Revisions to this document may take place periodically.

Timeframe

**DEVELOPER ACTIONS**

**COUNCIL ACTIONS**

**Planning Permission granted**

**0ommunity liaison**

**Appoint principal contractor**

**Begin community liaison**

**Work can commence if CMP is approved**

**Council response to second draft**

**Submit draft CMP**

**Work can commence if draft CMP is approved**

**Resubmission of CMP if first draft required further development**

**2ommunity liaison**

**3ommunity liaison**

**1ommunity liaison**

INDICATIVE TIMEFRAME (MONTHS)

**4ommunity liaison**

**Council response to draft**

# Contact

**IMPORTANT NOTICE:** If your site falls within a Cumulative Impact Area *(as of 03/02/2020 to 03/08/2020 there is only one established CIA for the Central London area)* you are required to complete the CIA Checklist and circulate as an appendix to the CMP and included as part of any public consultation – a CMP submission will not be accepted until evidence of this has been supplied.

The CIA Checklist can be found at <https://www.camden.gov.uk/about-construction-management-plans>

1. Please provide the full postal address of the site and the planning reference relating to the construction works.

Address: 43A Redington Road, London, NW3 7RA

Planning reference number to which the CMP applies: 2021/4234/P

2. Please provide contact details for the person responsible for submitting the CMP.

Name: Alessandra Maiolino (Project Architect)

Address: Amos Goldreich Architects, Studio 25, Bickerton House, 25 Bickerton Road, London N19 5JT

Email: alessandra@agarchitecture.net

Phone: 07904 406 966

3. Please provide full contact details of the site project manager responsible for day-to-day management of the works and dealing with any complaints from local residents and businesses.

Name: Mark Skehill (Main Contractor)

Address: Sygnet Style Ltd, 1 Mansel Grove, London E17 5BN

Email: mark@sygnetstyle.co.uk

Phone: 07964 945 412

4. Please provide full contact details of the person responsible for community liaison and dealing with any complaints from local residents and businesses if different from question 3. In the case of Community Investment Programme (CIP), please provide contact details of the Camden officer responsible.

Name: See response to question 3

Address: TBC

Email: TBC

Phone: TBC

5. Please provide full contact details including the address where the main contractor accepts receipt of legal documents for the person responsible for the implementation of the CMP.

Name: See response to question 3

Address:

Email:

Phone:

# Site

6. Please provide a site location plan and a brief description of the site, surrounding area and development proposals for which the CMP applies.

A site location plan is presented in **Figure 1** of this report. The proposal comprises of lowering the depth of the existing basement.

The site is in the Redington Frognal conservation area.

The site has frontage to Redington Road. The main pedestrian entrance to the existing building is via Redington Road.

Redington Road is in permit zone CA-S which restricts parking between Monday-Friday 12:30-2:30pm.

A preliminary site set-up plan with local highway context is presented at **Figure 2** of this report and is referenced again later in this report.

The existing property is a three bedroom. two storey lower ground floor and ground floor converted flat. It currently uses the main entrance on the upper ground floor as its primary entrance. The existing conversion has been poorly carried out and the property is in need of full renovation to bring it up to modern living standards.

7. Please provide a very brief description of the construction works including the size and nature of the development and details of the main issues and challenges (e.g. narrow streets, close proximity to residential dwellings etc).

The project involves extension and remodelling including rear single storey extension at Lower Ground Floor level onto the garden (33.5 sqm), ans an Upper Ground Floor single storey side extension atop the existing garage. The garage (21sqm) will also be converted to provide a new main entrance to the flat at lower ground floor. The existing gross area will be increased from 237sqm to 316sqm

The existing lower ground floor area is split level and suffers from poor light levels and ceiling height. 30% of the lower ground floor area will be lowered to match the existing levels of the rest of the existing floor level. The level reduction is 65cm (3 steps) to the utility and hallway and 50cm to the existing garage.

An external stairwell (20 sqm) will also be provided, replacing the current car ramp, to provide access to the lower ground floor. This involves a re-grading of the levels to the front garden.

8. Please provide the proposed start and end dates for each phase of construction as well as an overall programme timescale. (A Gantt chart with key tasks, durations and milestones would be ideal).

It is anticipated that construction will start on 30 August 2022, and complete by end September 2023. Key milestones are as follows:

Week 1-4. Site set up and demolition

Weeks 5-12 Underpinning and ground works

Weeks 13-24 Side and rear extension walls, roof and glazing

Weeks 25-36 Waterproofing, first fix and linings

Weeks 37-48 Fit out, decorating and front garden work

Week 49-52 Snagging, cleaning, commissioning and completion

9. Please confirm the standard working hours for the site, noting that the standard working hours for construction sites in Camden are as follows:

* 8.00am to 6pm on Monday to Friday
* 8.00am to 1.00pm on Saturdays
* No working on Sundays or Public Holidays

The working hours above will be adhered to.

# Community Liaison

**A neighbourhood consultation process must have been undertaken prior to submission of the CMP first draft.**

**This consultation must relate to construction impacts, and should take place following the granting of planning permission in the lead up to the submission of the CMP. A consultation process specifically relating to construction impacts must take place regardless of any prior consultations relating to planning matters. This consultation must include all of those individuals that stand to be affected by the proposed construction works. These individuals should be provided with a copy of the draft CMP, or a link to an online document. They should be given adequate time with which to respond to the draft CMP, and any subsequent amended drafts. Contact details which include a phone number and email address of the site manager should also be provided.**

Significant time savings can be made by running an effective neighbourhood consultation process. This must be undertaken in the spirit of cooperation rather than one that is dictatorial and unsympathetic to the wellbeing of local residents and businesses.

These are most effective when initiated as early as possible and conducted in a manner that involves the local community. Involving locals in the discussion and decision making process helps with their understanding of what is being proposed in terms of the development process. **The consultation and discussion process should have already started, with the results incorporated into the CMP first draft submitted to the Council for discussion and sign off.**This communication should then be ongoing during the works, with neighbours and any community liaison groups being regularly updated with programmed works and any changes that may occur due to unforeseen circumstances through newsletters, emails and meetings.

Please note that for larger sites, details of a construction working group may be required as a separate S106 obligation. If this is necessary, it will be set out in the S106 Agreement as a separate requirement on the developer.

**Cumulative impact**

Sites located within high concentrations of construction activity that will attract large numbers of vehicle movements and/or generate significant sustained noise levels should consider establishing contact with other sites in the vicinity in order to manage these impacts.

**The Council can advise on this if necessary.**

**10. Sensitive/affected receptors**

Please identify the nearest potential receptors (dwellings, business, etc.) likely to be affected by the activities on site (i.e. noise, vibration, dust, fumes, lighting etc.).

The nearest potential receptors likely to be affected by the activities on-site are listed as follows:

39 Reddington Road NW3 7RA

41 Reddington Road NW3 7RA

Flats 1-4, 43 Reddington Road NW3 7RA

45 Reddington Road NW3 7RA

Flats 1-4, 47 Reddington Road NW3 7RA

Flats 1-5, 30 Reddington Road NW3 7RB

28 Redington Road NW3 7RB

26 Redington Road NW3 7RB

24 Redington Road NW3 7RB

**11. Consultation**

The Council expects meaningful consultation. For large sites, this may mean two or more meetings with local residents **prior to submission of the first draft CMP**.

Evidence of who was consulted, how the consultation was conducted and a summary of the comments received in response to the consultation should be included. Details of meetings including minutes, lists of attendees etc. should be appended.

In response to the comments received, the CMP should then be amended where appropriate and, where not appropriate, a reason given. The revised CMP should also include a list of all the comments received. Developers are advised to check proposed approaches to consultation with the Council before carrying them out. If your site is on the boundary between boroughs then we would recommend contacting the relevant neighbouring planning authority.

Please provide details of consultation of draft CMP with local residents, businesses, local groups (e.g. residents/tenants and business associations) and Ward Councillors.

**12. Construction Working Group**

For particularly sensitive/contentious sites, or sites located in areas where there are high levels of construction activity, it may be necessary to set up a construction working group.

If so, please provide details of the group that will be set up, the contact details of the person responsible for community liaison and how this will be advertised to the local community, and how the community will be updated on the upcoming works i.e. in the form of a newsletter/letter drop, or weekly drop in sessions for residents.

The neighbouring residents have firstly been consulted via the planning application process consultation period. A draft (V1) of this CMP was submitted with the planning application, together with all of the submitted plans and documents.

Following the appointment of the main contractor, an updated draft of the CMP (v2) was issued. Following this a second consultation was carried out in July 2022. On the 11th July 2022, letters were sent to all nearby residents listed on page 12. The letter provides a link to the updated draft (V2) of this CMP. A copy is included in Appendix A. This letter facilitated residents the opportunity to get in direct contact with feedback or queries. Furthermore, it extended an invitation to an open meeting which was held in the front garden of 43A on 21st July 2022 to provide a second forum for residents to obtain information and provide feedback. The meeting was attended by the client, architect and main contractor. No comments or queries were received during this process.

On 26th July 22, a zoom meeting was held with the main contractor, client, and residents of Flat 3, 43 Redington Road. This flat is directly above the works site. A detailed explanation of our schedule and some proposed mitigations were circulated to the residents by email prior. The initial comments received during the zoom call included:

-The residents were on leave when the letter and public meeting were held. It was explained that all parties were keen to engage in further direct communication ahead of works commencing.

- Some corrections to the CMP were noted and updated in the latest version of this document.

- The status of asbestos removal was queried. It was noted that asbestos survey and removal have already been carried out and completed professionally.

-It was requested that no portaloos would be placed on the public highway. It was confirmed they would not be as there is a site toilet installed within the building.

-Contractors access was queried. It was explained that contractors would access separately via 43A, and not the main entrance to other flats at no 43 which would not be impacted. Occasional use of the side access to the rear garden would be needed but this would not interfere with residents use of their bins.

-Extent of dust was queried. It was explained that while a dust free environment could not be guaranteed the contractor would implement methods to reduce dust as much as practical, including the installation of an internal temporary ceiling, and liaison with residents ahead of any works expected to be dusty such as concrete breaking.

-The residents noted they needed further time to review the info and would provide further feedback or queries in due course. The meeting was concluded after 45 minutes, and it was agreed that any further queries would be sent, and a follow up meeting could take place following this. A full set of queries and replies are appended to this docuemnt

On commencement, Sygnet style Ltd will contact all local residents again, via letter drop. This will provide site manager contact details, plus a download link to this CMP. It is expected that a number of residents will get in touch with queries after works have commenced. Any issues raised will be set out in future iterations of the CMP.

The scale of the heavy building work is limited and typical of this type of domestic renovation project. The are some limited alterations to floor levels and the work does not involve a new basement.

Although some construction activities are necessarily noisy and disruptive, the project is not anticipated to be particularly contentious, and disruption is expected to be limited to residents directly adjacent. Communication and updates to adjacent residents will be regular focused

Following our initial letter, there will be additional letters to communicate an important piece of information that residents need to be aware of such as the delivery of large items of plant and equipment.

An email distribution list will be set up of all local resident to whom have been issued a letter or a copy of the CMP, plus subsequent updates.

We will also use this email distribution list to inform all stakeholders of forthcoming works and activities in relation to the project.

An information board will be posted on the site hoarding, clearly visible from the public highway, to advise of key personnel contact details and site information.

In addition to the above, Sygnet Style, as main contractor, operate an open door policy whereby members of the local community can speak to the site management if they have specific concerns or complaints.

A complaints and compliments register would be maintained throughout the life of the project. The aim would be to close out all complaints to the satisfaction of the individual making the observation/ complaint. Simple devices such as vision panels in the site hoarding help to remove the mystery of the site. It helps to remove the element of suspicion regarding what exactly is happening behind closed site hoardings.

Site contact details and out of hours emergency contact details will be provided to all local residents.

**13. Schemes**

Please provide details of your Considerate Constructors Scheme (CCS) registration. Please note that Camden requires [enhanced CCS registration](https://www.ccscheme.org.uk/construction-logistics-and-cyclist-safety-clocs/) that includes CLOCS monitoring. Please provide a CCS registration number that is specific to the above site.

Contractors will also be required to follow the [Guide for Contractors Working in Camden](https://www.camden.gov.uk/documents/20142/1269042/Guide+for+Contractors+in+Camden.pdf/18b7bb06-119e-9957-7037-fdb633f17ae6). Please confirm that you have read and understood this, and that you agree to abide by it.

It is also noted that we will follow the Council’s “Guide for Contractors Working in Camden”

Site specific inductions will focus on not only the onsite construction works but also the surrounding community. Operatives will be advised on how to behave on site and whilst interacting with the local area and its people. It will be made clear to all that they will be representing the site and therefore the appointed contractor. If staff or operatives were to be found or reported as having misbehaved whilst off of the site, then it is a reflection on the appointed contractor, and they will be asked to leave the site and not to return.

Operatives will also be encouraged to engage with the local community by using local public transport and amenities such as local cafes, shops, community gymnasiums etc.

**14. Neighbouring sites**

Please provide a plan of existing or anticipated construction sites in the local area and please state how your CMP takes into consideration and mitigates the cumulative impacts of construction in the vicinity of the site. The council can advise on this if necessary.

Two construction sites are currently in operation near the site of works.

A minor refurbishment of the Ground floor flat is currently under way at 43 Redington Road. We have established communication channels with the contractor to facilitate cooperation particularly with regard to any large planning deliveries or utilities works.

A larger building project is currently on site across the road at no 28 Reddington Road. This property is located on a larger site with space for vehicle turning within the front garden as such culumative impacts are not expected. Management will liaise with the adjacent contractor with regard to the dates for any planned utilities works.

Site management will monitor and continue liaise with adjacent contractors as necessary.Further reviews will be carried out periodically and any sizeable projects locally that would benefit from liaison and cooperation with this project would be referenced in any future iterations of this report.

# Transport

**This section must be completed in conjunction with your principal contractor. If one is not yet assigned, please leave the relevant sections blank until such time when one has been appointed.**

Camden is a CLOCS Champion, and is committed to maximising road safety for Vulnerable Road Users (VRUs) as well as minimising negative environmental impacts created by motorised road traffic. As such, all vehicles and their drivers servicing construction sites within the borough are bound by the conditions laid out in the CLOCS Standard.

This section requires details of the way in which you intend to manage traffic servicing your site, including your road safety obligations with regard to VRU safety. It is your responsibility to ensure that your principal contractor is fully compliant with the terms laid out in the CLOCS Standard. It is your principal contractor’s responsibility to ensure that all contractors and sub-contractors attending site are compliant with the terms laid out in the CLOCS Standard.

Checks of the proposed measures will be carried out by CCS monitors as part of your enhanced CCS site registration, and possibly council officers, to ensure compliance. Please refer to the CLOCS Standard when completing this section.

Please contact [CLOCS@camden.gov.uk](mailto:CLOCS@camden.gov.uk) for further advice or guidance on any aspect of this section.

**CLOCS Contractual Considerations**

15. Name of Principal contractor:

Sygnet Style Ltd

16. Please submit the proposed method for checking operational, vehicle and driver compliance with the CLOCS Standard throughout the duration of the contract.

Sygnet Style Ltd are committed to the FORS scheme and full compliance with CLOCS will be observed. The site manager and our purchasing and logistics team will put in place site specific risk assessments, arrangements as regards routing, access, unloading areas and delivery management.

Gate checks to vehicles and drivers will be carried out by site manager. A FORS manager will carry out regular checks on compliance, and independent audits carried out every 6 months

17. Please confirm that you as the client/developer and your principal contractor have read and understood the CLOCS Standard and included it in your contracts.

I confirm that I have included the requirement to abide by the CLOCS Standard in my contracts to my contractors and suppliers:

The requirement to abide by the CLOCS Standard will be incorporated into contracts to all contractors and suppliers.

Please contact [CLOCS@camden.gov.uk](mailto:CLOCS@camden.gov.uk) for further advice or guidance on any aspect of this section.

**Site Traffic**

**Sections below shown in blue directly reference the CLOCS Standard requirements. The CLOCS Standard should be read in conjunction with this section.**

**18. Traffic routing**: *“Clients shall ensure that a suitable, risk assessed vehicle route to the site is specified and that the route is communicated to all contractors and drivers. Clients shall make contractors and any other service suppliers aware that they are to use these routes at all times unless unavoidable diversions occur.”* (P19, 3.4.5)

Routes should be carefully considered and risk assessed, taking into account the need to avoid where possible any major cycle routes and trip generators such as schools, offices, stations, public buildings,museums etc.

Consideration should also be given to weight restrictions, low bridges and cumulative impacts of construction (including neighbouring construction sites) on the public highway network. The route(s) to and from the site should be suitable for the size of vehicles that are to be used.

Please show vehicle approach and departure routes between the site and the Transport for London Road Network (TLRN). Please note that routes may differ for articulated and rigid HGVs.

Routes should be shown clearly on a map, with approach and departure routes clearly marked. If this is attached, use the following space to reference its location in the appendices.

A construction vehicle routing plan is set out in **Figure 3** of this report. As is shown the development site is located on Redington Road which forms part of Camden’s road network. All large construction vehicles will be routed to and from the site via Redington Road.

Following feedback from Transport Officer Maxim Lyne on 17th August, it is confirmed:

* No tipper trucks will be used. Cement trucks expected to be limited to 5/6 visits and bin days will be avoided for concrete pours to avoid causing any potential traffic congestion
* We agreed to trial the cement truck reversing into the property and will temporarily remove the front wall pillar to facilitate this. We have attached an updated Swept Path Analysis to demonstrate this. A separate concrete pump will also be located in the front garden for any concrete pours and will not be located on the highway
* The footway will be protected prior to the truck reversing onto the drive way and it was confirmed Sygnet agree to pay for any damage to footway.
* Bays will be suspended for HGV deliveries to avoid obstruction of driveway of adjacent property.
* Sygnet have contacted the building contractor adjacent at the Transport Officers request to agree a method for avoiding large delivery clashes. Both site management teams have exchanged emails and a phone call regarding this and a Watsapp group has been set up by both Contractors for delivery coordination.

b. Please confirm how contractors and delivery companies will be made aware of the route (to and from the site) and of any on-site restrictions, prior to undertaking journeys.

All contractors, sub-contractors, delivery companies and visitors will be advised of and required to adhere to the specified route and all the other terms of this plan.

**19. Control of site traffic, particularly at peak hours**: “*Clients shall consider other options to plan and control vehicles and reduce peak hour deliveries”* (P20, 3.4.6)

Construction vehicle movements should be restricted to the hours of 9.30am to 4.30pm on weekdays and between 8.00am and 1.00pm on Saturdays. If there is a school in the vicinity of the site or on the proposed access and/or egress routes, then deliveries must be restricted to the hours of 9.30am and 3pm on weekdays during term time.

Vehicles may be permitted to arrive at site at 8.00am if they can be accommodated on site. Where this is the case they must then wait with their engines switched off.

A delivery plan should ensure that deliveries arrive at the correct part of site at the correct time. Instructions explaining such a plan should be sent to all suppliers and contractors**.**

Please provide details of the types of vehicles required to service the site and the approximate number of deliveries per day for each vehicle type during the various phases of the project.

For Example:

32t Tipper: 10 deliveries/day during first 4 weeks

Skip loader: 2 deliveries/week during first 10 weeks

Artic: plant and tower crane delivery at start of project, 1 delivery/day during main construction phase project

18t flatbed: 2 deliveries/week for duration of project

3.5t van: 2 deliveries/day for duration of project

The typical size of vehicles that would access the site during the construction programme are anticipated to be as follows:

**CONCRETE**

Medium sized 6m3 three-axle concrete mixer – 8.4m x 2.4m

See **Figure 7** for swept path analysis of a 6m3 concrete truck reversing onto the front driveway and exiting the site in forward gear. The front garden will also accommodate a separate concrete pump during this time.

Frequency: this will be limited to siz half days when concrete pours are scheduled to take place

**SKIP TRUCK**

The skip truck size is – 5.1m x 3m

See **Figure 7** for swept path analysis of a concrete truck reversing onto and leaving the site in forward gear. As the cement trick is larger than a skip truck this demonstrates that a skip truck can be reversed onto site

Frequency: twice weekly for the first 8 weeks, following this there will be one skip collection per week

**GENERAL SUPPLIES/DELIVERIES**

7.5 tonne box van and flatbed van – 8m x 2.1m

See **Figure 6** for swept path analysis of a 7.5t box van entering and exiting the suspended parking bay outside of the site in forward gear.

Large deliveries are typically weekly and scheduled for after 10am and smaller deliveries 2-3 times weekly by a small van driver. Owing to the relatively modest scale of the construction project, vehicle attendance at the kerb side loading area and dwell time is anticipated to be relatively low, and it can be confirmed at this stage that there would never be more than one construction related vehicle related to muck-away, concrete delivery, or general deliveries at the site at any one time.

b. Cumulative affects of construction traffic servicing multiple sites should be minimised where possible. Please provide details of other developments in the local area or on the route that might require deliveries coordination between two or more sites. This is particularly relevant for sites in very constrained locations.

Two construction sites are currently in operation near the site of works.

A minor refurbishment of the Ground floor flat is currently under way at 43 Redington Road. We have established communication channels with the contractor to facilitate cooperation particularly with regard to any large planning deliveries or utilities works.

A larger building project is currently on site across the road at no 28 Reddington Road. This property is located on a larger site with space for parking and vehicle turning within the front garden as such cumulative impacts are not expected. Management will liaise with the adjacent contractor with regard to the dates for any planned utilities works.

c. Please provide swept path analyses for constrained manoeuvres along the proposed route.

It is currently envisaged that all large construction vehicle traffic including skip lorrys will reverse onto site and unload within the site. A traffic marshal will be available at the entrance to the site to safely receive vehicles and assist vehicles leaving.

Vehicles would be able to stop on the public highway on Redington Road outside the site. Smaller delivery vehicles will occasionally deliver kerb side ensuring there is no encroachment onto the adjacent driveway. If any larger vehicles need to park roadside, the contractor would ensure that the necessary parking bay suspensions are obtained from the Council in advance of each requirement. Such instances are expected to be infrequent throughout the project.

There are no constrained manoeuvres along the proposed route for construction vehicles which require further swept path assessment.

d. Consideration should be given to the location of any necessary holding areas/waiting points for sites that can only accommodate one vehicle at a time/sites that are expected to receive large numbers of deliveries. Vehicles must not queue or circulate on the public highway. Whilst deliveries should be given set times to arrive, dwell and depart, no undue time pressures should be placed upon the driver at any time.

Please identify the locations of any off-site holding areas or waiting points. This can be a section of single yellow line that will allow the vehicle to wait to phone the site to check that the delivery can be accommodated.

Please refer to question 24 if any parking bay suspensions will be required to provide a holding area.

As discussed, it is currently envisaged that the majority of construction vehicle loading and unloading will take place in the front garden. We have demonstrated that a concrete truck will be able to access and egress the site via Redington Road, we have also demonstrated that there is plenty of space for vehicles to pass stationary construction vehicles. See figures 2, 6-7.

It is not expected that there will be any waiting of construction vehicles beyond 40 minutes on Redington Road, the frequency of vehicle visits is not predicted to be high, and the vehicle activity will be managed by the contractor such that there will never be more than one vehicle at the site at any one time. Suitable provisions will be made for construction vehicles to be able to stop on the public highway on Redington Road outside the site.

Parking bay suspensions will be obtained from the Council in advance of this requirement. Such instances are reasonably expected to be infrequent throughout the project.

A trained traffic marshal will be on hand to ensure the safe passage of pedestrians, cyclists and motor traffic in the street when vehicles are being loaded or unloaded.

e. Delivery numbers should be minimised where possible. Please investigate the use of construction material consolidation centres, and/or delivery by water/rail if appropriate.

Water/rail deliveries are not feasible due to the site location. We have material consolidation policies in place whereby the majority of our materials are ordered from a single builders merchant at key project stages. For smaller specialist materials, we have a full time van driver on the road who routes pick ups and deliveries efficiently on a weekly basis to minimise fuel costs. We have an off site storage facility in Walthamstow.

f. Emissions from engine idling should be minimised where possible. Please provide details of measures that will be taken to reduce delivery vehicle engine idling, both on and off site (this does not apply to concrete mixers).

The engines of contractors’ vehicles shall not be kept idling, except for concrete mixers which require to be running to dispense concrete.

A trained traffic marshal will be positioned at the entrance on Redington Road and would advise drivers to switch off their engines once vehicles are in place.

**20. Site access and egress:** “*Clients shall ensure that access to and egress from the site is appropriately managed, clearly marked, understood and clear of obstacles.”* (P18, 3.4.3)

This section is only relevant where vehicles will be entering the site. Where vehicles are to load from the highway, please skip this section and refer to Q23.

Vehicles entering and leaving the site should be carefully managed, using gates that are clearly marked and free from obstacles. Traffic marshals must ensure the safe passage of all traffic on the public highway, in particular pedestrians and cyclists, when vehicles are entering and leaving site, particularly if reversing.

Traffic marshals, or site staff acting as traffic marshals, should hold the relevant qualifications required for directing large vehicles when reversing. Marshals should be equipped with ‘STOP – WORKS’ signs (not STOP/GO signs) if control of traffic on the public highway is required. Marshals should have radio contact with one another where necessary.

a. Please detail the proposed site access and egress points on a map or diagram. If this is attached, use the following space to reference its location in the appendices.

See figure 7

b. Please describe how the access and egress arrangements for construction vehicles in and out of the site will be managed, including the number and location of traffic marshals where applicable. If this is shown in an attached drawing, use the following space to reference its location in the appendices.

A trained traffic marshal will be positioned at the entrance on Redington Road and would advise drivers to switch off their engines once vehicles are in place.

c. Please provide swept path drawings for vehicles accessing/egressing the site if necessary. If these are attached, use the following space to reference their location in the appendices.

See figure 7

d. Provision of wheel washing facilities should be considered if necessary. If so, please provide details of how this will be managed and any run-off controlled. Please note that wheel washing should only be used where strictly necessary, and that a clean, stable surface for loading should be used where possible.

N/A – the existing concrete driveway will be retained for the duration of structural works

**21. Vehicle loading and unloading:** *“Clients shall ensure that vehicles are loaded and unloaded on-site as far as is practicable.”* (P19, 3.4.4)

This section is only relevant if loading/unloading is due to take place off-site on the public highway. If loading is taking place on site, please skip this section.

a. please provide details of the parking and loading arrangements for construction vehicles with regard to servicing and deliveries associated with the site (e.g. delivery of materials and plant, removal of excavated material). This is required as a scaled site plan, showing all points of access and where materials, skips and plant will be stored, and how vehicles will access and egress the site. If this is attached, use the following space to reference its location in the appendices. Please outline in question 24 if any parking bay suspensions will be required.

Suitable provisions will be made for construction vehicles to be able to stop on the public highway on the Redington Road outside the site.

We would ensure that the necessary parking bay suspensions are obtained from the Council in advance of this requirement. Such instances are reasonably expected to be limited throughout the project.

A trained traffic marshal will be on hand to ensure the safe passage of pedestrians, cyclists and motor traffic in the street when vehicles are being loaded or unloaded. See Figure 2 for the Construction Site Plan.

b. Where necessary, Traffic Marshalls must ensure the safe passage of pedestrians, cyclists and motor traffic in the street when vehicles are being loaded or unloaded. Please provide detail of the way in which marshals will assist with this process, if this differs from detail provided in Q20 b.

Suitable provisions will be made for construction vehicles to be able to stop on the public highway on Redington Road outside the site.

Parking bay suspensions will be requested where necessary so as to minimise disruption to adjoining neighbours/occupiers. Such instances are reasonably expected to be infrequent throughout the project.

The traffic marshal shall assist the construction vehicles entering the parking space outside of the site and will assist vehicles leaving the loading area outside of the site and back onto the public highway. The traffic marshal will make sure that pedestrians and cyclist are kept clear from construction vehicles while manoeuvring into the parking space.

**Street Works**

**Full justification must be provided for proposed use of the public highway to facilitate works. Camden expects all options to minimise the impact on the public highway to have been fully considered prior to the submission of any proposal to occupy the highway for vehicle pit lanes, materials unloading/crane pick points, site welfare etc.**

**Please note that Temporary Traffic Orders (TTOs) and hoarding/scaffolding licenses may be applied for prior to CMP submission but won’t be granted until the CMP is signed-off.**

**Please note that there is a two week period required for the statutory consultation process to take place as part of a TTO.**

**If the site is on or adjacent to the TLRN, please provide details of preliminary discussions with Transport for London in the relevant sections below.**

**If the site conflicts with a bus lane or bus stop, please provide details of preliminary discussions with Transport for London in the relevant sections below.**

**22. Site set-up**

Please provide a scaled plan detailing the local highway network layout in the vicinity of the site. This should include details of on-street parking bay locations, cycle lanes, footway extents, relevant street furniture, and proposed site access locations. If these are attached, use the following space to reference their location in the appendices.

A scaled plan detailing the local highway network layout in the vicinity of the site, site access locations and site set-up details is presented in **Figure 2** of this report.

**23. Parking bay suspensions and temporary traffic orders**

Parking bay suspensions should only be requested where absolutely necessary and these are permitted for a maximum of 6 months only. For exclusive access longer than 6 months, you will be required to obtain a [Temporary Traffic Order (TTO)](https://www.camden.gov.uk/temporary-traffic-restrictions) for which there is a separate cost.

Please provide details of any proposed parking bay suspensions and/or TTO’s which would be required to facilitate the construction - include details of the expected duration in months/weeks. Building materials and equipment must not cause obstructions on the highway as per your CCS obligations unless the requisite permissions are secured.

Information regarding parking suspensions can be found [here.](http://www.camden.gov.uk/ccm/navigation/transport-and-streets/parking/parking-bay-suspensions/)

See Figure 2 for the site setup plan.

Parking bay suspensions will be requested where necessary so as to minimise disruption to adjoining neighbours/occupiers. Such instances are reasonably expected to be infrequent throughout the project.

**24. Occupation of the public highway**

Please note that use of the public highway for storage, site accommodation or welfare facilities is at the discretion of the Council and is generally not permitted. If you propose such use you must supply full justification, setting out why it is impossible to allocate space on-site. We prefer not to close footways but if this is unavoidable, you should submit a scaled plan of the proposed diversion route showing key dimensions.

a. Please provide justification of proposed occupation of the public highway.

N/A

b. Please provide accurate scaled drawings of any highway works necessary to enable construction to take place (e.g. construction of temporary vehicular accesses, removal of street furniture etc). If these are attached, use the following space to reference their location in the appendices.

Other than ad-hoc parking bay suspensions, it is not currently envisaged that any highways work will necessary to enable this construction project to take place.

**25. Motor vehicle and/or cyclist diversions**

Where applicable, please supply details of any diversion, disruption or other anticipated use of the public highway during the construction period. Please show locations of diversion signs on drawings or diagrams. If these are attached, use the following space to reference their location in the appendices.

There will not be any highway diversions required to the public highway.

**26. Scaffolding, hoarding, and associated pedestrian diversions**

Pedestrians safety must be maintained if diversions are put in place. Vulnerable footway users should also be considered. These include wheelchair users, the elderly, those with walking difficulties, young children, those with prams, the blind and partially sighted. Appropriate ramps must be used if cables, hoses, etc. are run across the footway.

Any work above ground floor level may require a covered walkway adjacent to the site. A licence must be obtained for scaffolding and gantries. The adjoining public highway must be kept clean and free from obstructions, and hoarding should not restrict access to adjoining properties, including fire escape routes. Lighting and signage should be used on temporary structures/skips/hoardings etc.

A secure hoarding will generally be required at the site boundary with a lockable access.

a. Where applicable, please provide details of any hoarding and/or scaffolding that intrudes onto the public highway, describing how pedestrian safety will be maintained through the diversion, including any proposed alternative routes. Please provide detailed, scale drawings that show hoarding lines, gantries, crane locations, scaffolding, pedestrian routes, parking bay suspensions, remaining road width for vehicle movements, temporary vehicular accesses, ramps, barriers, signage, lighting etc. If these are attached, use the following space to reference their location in the appendices.

Secure hoarding will be installed at the site’s boundary with lockable accesses at pedestrian access points.

No pedestrian or cyclist diversions will be required to be put in place.

There is a footpath that is wide enough for pedestrians to use, and appropriate statutory signage will be displayed on the hoardings to warn of hazards. The site contact details and out of hours emergency contact details will also be prominently displayed on the site hoardings.

Daily inspections will be undertaken of the site perimeter and footpaths to check for potential hazards (such as blocked footpaths, build-up of rubbish, leaves etc.).

The following requirements will be stipulated in sub-contractors and suppliers orders when operating large vehicles over 3.5 tonnes:

• Operators must be a member of TfL’s Fleet Operator Recognition Scheme (www.tfl.gov.uk/fors) or similar at the silver level.

• All drivers must have undertaken cycle awareness training such as the Safe Urban Driver module through FORS or similar.

• All vehicles associated with the construction of the Development must:

• Have Side Guards fitted, unless it can be demonstrated to the reasonable satisfaction of the Employer, that the Lorry will not perform the function, for which it was built, if Side Guards are fitted.

• Have a close proximity warning system fitted comprising of a front mounted, rear facing CCTV camera (or Fresnel Lens where this provides reliable alternative), a Close Proximity Sensor, an in-cab warning device (visual or audible) and an external warning device to make the road user in close proximity aware of the driver’s planned manoeuvre.

• Have a Class VI Mirror.

• Bear prominent signage on the rear of the vehicle to warn cyclists of the dangers of passing the vehicle on the inside

b. Please provide details of any other temporary structures which would overhang/oversail the public highway (e.g. scaffolding, gantries, cranes etc.) If these are attached, use the following space to reference their location in the appendices.

None are required.

**27. Services**

Please indicate if any changes to services are proposed to be carried out that would be linked to the site during the works (i.e. connections to public utilities and/or statutory undertakers’ plant). Larger developments may require new utility services. If so, a strategy and programme for coordinating the connection of services will be required. If new utility services are required, please confirm which utility companies have been contacted (e.g. Thames Water, National Grid, EDF Energy, BT etc.) You must explore options for the utility companies to share the same excavations and traffic management proposals. Please supply details of your discussions.

There is an existing mains gas, electricity, water supply and drainage service to the property. It is anticipated than an upgrade to the mains water supply will be needed. This runs under the public footpath. Trench excavation for this will be within the site. The water meter is located 30cm from the site boundary and connection to this will be carried out by Thames Water operatives.

# Environment

To answer these sections please refer to the relevant sections of **Camden’s Minimum Requirements for Building Construction (**[**CMRBC**](https://www.camden.gov.uk/about-construction-management-plans)**).**

28. Please list all [noisy operations](http://www.camden.gov.uk/ccm/content/environment/environmental-health--consumer-protection/noise/reducing-noise/noise-from-construction-sites.en?page=2)  and the construction method used, and provide details of the times that each of these are due to be carried out.

Noisy operations will be limited to 8am-5pm Monday to Friday and avoided on weekends or public holidays. Very noisy operations will include:

-demolition of existing structural walls (1 week)

-removal of existing concrete slab (1 week)

-formation of front stair well (2 weeks)

All other activities will be carried out using electric hand tools and are not expected to be very noisy

29. Please confirm when the most recent noise survey was carried out (before any works were carried out) and provide a copy. If a noise survey has not taken place please indicate the date (before any works are being carried out) that the noise survey will be taking place, and agree to provide a copy.

A noise survey will be carried out before any works are being carried out.

30. Please provide predictions for [noise](http://www.camden.gov.uk/ccm/content/environment/environmental-health--consumer-protection/noise/reducing-noise/noise-from-construction-sites.en?page=2) and vibration levels throughout the proposed works.

Noise levels from the site will aim to be within a daily level of 70 decibels (LAeq, 10hr) for airborne noise at the nearest occupied premises/site Boundary

31. Please provide details describing mitigation measures to be incorporated during the construction/[demolition](http://www.camden.gov.uk/ccm/navigation/environment/building-control/demolition/) works to prevent noise and vibration disturbances from the activities on the site, including the actions to be taken in cases where these exceed the predicted levels.

The following mitigation measures to control noise and vibration will be adopted during the demolition and construction period.

• The quietest / lowest impact processes that are reasonably practicable will be employed on site to carry out the demolition and construction works.

• The quietest vehicles and plant shall be used as far as is reasonably practicable.

• No machinery starting up on site before the designated site start times (8.00am).

• No engines left running on vehicles waiting to enter the site.

• Noise suppression / screening will be a prime consideration in order to reduce the noise impact for the surrounding community (e.g. around generators).

• Keeping voices and conversations to a low in volume. No shouting or swearing.

• No banging of doors, gates, scaffolding.

• Noise levels from all sites must aim to be within a daily level of 70 decibels (LAeq, 10hr) for airborne noise at the nearest occupied premises/site Boundary as covered in the code of construction for other areas of London.

• Include within material and subcontractor requisitions details of permitted vehicle arrivals i.e. not before 9.30am or after 4.30pm

• Hiring equipment from reputable companies who can supply new, well-maintained plant

• Locating noise-generating fixed plant as far away from sensitive premises as possible

• Arranging for materials, such as flagstones and steelwork, to be cut off-site where practicable

• Ensuring that an appropriate electricity supply exists before any work involving demolition or excavation starts, so that generators are not necessary

If the noise level exceeds the daily level, work will be stopped with the works and methodology reviewed.

As far as reasonably practicable, demolition and piling methods will be selected to minimise noise and vibration.

In addition, local residents will be advised when the above works are programmed to commence via regular information updates.

32. Please provide evidence that staff have been trained on BS 5228:2009

Staff have been trained on BS5228:2009 and we will also ensure that all sub-contractors and operatives are trained on BS5228:2009. This is included in our site induction.

33. Please provide specific details on how air pollution and dust nuisance arising from dusty activities on site will be prevented. This should be relevant and proportionate to activities due to take place, with focus on both preventative and reactive mitigation measures.

Control of dust, particularly during periods of dry and windy weather is a prime concern for all construction projects. We have a hierarchical policy of prevention – suppression – containment with regards to dust control to prevent dust migrating beyond the site boundary. This applies to an operative drilling a hole to dust being blown about the site in dry weather.

The following measures and practices will be implemented throughout the period of the works programme:

* Make frequent site inspections during dust generating operations and at least once daily during general works to ensure that there is no dust release caused by site operations. The frequency of any site inspections must be increased when site activities have a high potential to generate dust and during prolonged dry and windy weather.
* Limit cutting, grinding and sawing on-site by use of pre-fabricated material and modules where practicable.
* Fit equipment such as disc cutters, table saws, sanders, etc., with dust suppression (water spray) or a dust collection facility.
* Ensure that there is sufficient water suppression such as water sprays, and/or pressure washers during demolition work and other activities that generate high levels of dust.
* Cover stockpiles/arisings of sand, earth or similar dust-generating materials when not in use to prevent wind whipping.
* Skips, chutes and conveyors must be completely covered and, if necessary, completely enclosed to ensure that dust does not escape. Similarly, drop heights must be minimised to control the fall of materials and the impact that results.
* Adopt and implement good housekeeping measures (i.e. regular wet sweeping, cleaning, vacuuming etc.).
* Regularly clean hoardings, fencing, barriers and scaffolding using wet methods, where practicable, to prevent re-suspension of particulates.
* Seal cement, sand, fine aggregates and other fine powders after use and if necessary, store in enclosed or containers or silos. Where appropriate, keep materials damp to reduce the risk of drying out.
* Where necessary due to dust contamination, contractors should offer to have neighbours’ property and cars cleaned at regular intervals when dust is known to have escaped the site.
* Ensure that all on-road vehicles comply with the Low Emission Zone (LEZ) and Ultra Low Emission Zone (ULEZ).
* All commercial road vehicles attending the site must meet European Emission Standards
* Reuse and recycle waste materials to reduce dust and pollution.
* Do not allow any on-site bonfires/incineration/burning of waste materials.
* All site must make efforts to have sufficient mains electrical power to avoid the use of diesel/petrol generators.
* Ensure that all non-road mobile machinery (NRMM), such as generators, excavators, piling machines, comply with Stage IIIB of EU Directive 97/87/EC or the requirements of the NRMM LEZ (whichever is most stringent).

34. Please provide details describing how any significant amounts of dirt or dust that may be spread onto the public highway will be prevented and/or cleaned.

No construction vehicles will enter the site. The main pedestrian exit point will provide a paved area between site and public highway which can be monitored and cleaned as required to prevent mud tracking onto the road/public footpath.

Question 33 above outlines a tranche of preventative measures to reduce dirt and dust spreading onto the public highway.

35. Please provide details describing arrangements for monitoring of [noise](http://www.camden.gov.uk/ccm/content/environment/environmental-health--consumer-protection/noise/reducing-noise/noise-from-construction-sites.en?page=2), vibration and dust levels, including instrumentation, locations of monitors and trigger levels where appropriate.

Noise and vibration monitoring will be carried out at designated locations around the site boundary. Noise monitoring will be carried out using a hand held Type 2 Sound level meter.

As a minimum, the following measures and practices must be implemented for monitoring noise, vibration and dust:

* A site target max noise level or 5dB above pre-construction ambient noise level will be set.
* Record and respond to all dust and air quality pollutant emission incidents and complaints. Records must be made available to the local authority when requested.
* All sites must visually monitor dust emissions and keep a log book of any incidents of dust release which are made available to the Council immediately upon request.
* Any noise monitoring that is required will be carried out by the developer and/or their appointed contractor. In some circumstances, the Council may carry out short-duration attended monitoring to confirm noise levels when this is deemed necessary.
* Where noise limits and monitoring are to be carried out, a noise (and, where necessary, vibration) monitoring protocol and specification must be agreed with the Council’s Construction Management Team prior to works starting on site and the relevant details included in the Site Construction Management Plan and s61 Prior Consent application. It may only be necessary for monitoring to be carried out during the high impact phases of works. Monitoring data must be made available to the Construction Management Team on request.

36. Please confirm that an Air Quality Assessment and/or Dust Risk Assessment has been undertaken at planning application stage in line with the GLA policy [The Control of Dust and Emissions During Demolition and Construction 2014 (SPG)](https://www.london.gov.uk/what-we-do/planning/implementing-london-plan/london-plan-guidance-and-spgs/control-dust-and) (document access at bottom of webpage), and that the summary dust impact risk level (without mitigation) has been identified. The risk assessment must take account of proximity to all human receptors and sensitive receptors (e.g. schools, care homes etc.), as detailed in the [SPG](https://www.google.com/url?sa=t&rct=j&q=&esrc=s&source=web&cd=&cad=rja&uact=8&ved=2ahUKEwjk8qS10KXvAhWQQRUIHWToAWcQFjABegQIAxAD&url=https%3A%2F%2Fwww.london.gov.uk%2Fsites%2Fdefault%2Ffiles%2Fgla_migrate_files_destination%2FDust%2520and%2520Emissions%2520SPG%25208%2520July%25202014.pdf&usg=AOvVaw06DJ0urJ7JWa8G5jmd_p8N). **Please attach the risk assessment and mitigation checklist as an appendix**.

See attached.

37. Please confirm that all of the GLA’s ‘highly recommended’ measures from the SPG document relative to the level of dust impact risk identified in question 36 have been addressed by completing the GLA mitigation measures checklist. (See Appendix 7 of the SPG document.)

It is confirmed that all of the GLA’s ‘highly recommended’ measures from the SPG document relative to the level of risk identified in question 36 will be addressed.

38. Please confirm the number of real-time dust monitors to be used on-site.

Note: **real-time dust (PM10) monitoring with MCERTS ‘Indicative’ monitoring equipment will be required for** **all sites with a high OR medium dust impact risk level**. If the site is a ‘high impact’ site, 4 real time dust monitors will be required. If the site is a ‘medium impact’ site’, 2 real time dust monitors will be required.

The dust monitoring must be in accordance with the SPG and IAQM guidance, and **the proposed dust monitoring regime (including number of monitors, locations, equipment specification, and trigger levels) must be submitted to the Council for approval**. Dust monitoring is required for the entire duration of the development and must be in place and operational **at least three months prior to the commencement of works on-site**. Monthly dust monitoring reports must be provided to the Council detailing activities during each monthly period, dust mitigation measures in place, monitoring data coverage, graphs of measured dust (PM10) concentrations, any exceedances of the trigger levels, and explanation on the causes of any and all exceedances in addition to additional mitigation measures implemented to rectify these.

In accordance with Camden’s Clean Air Action Plan, the monthly dust monitoring reports must also be made readily available and accessible online to members of the public soon after publication. Information on how to access the monthly dust monitoring reports should be advertised to the local community (e.g. presented on the site boundaries in full public view).

**Inadequate dust monitoring or reporting, or failure to limit trigger level exceedances, will be indicative of poor air quality and dust management and will lead to enforcement action.**

Owing to the relatively modest scale of the construction project the emission of significant amounts of dust is not expected to arise and accordingly it is not expected that this is a ‘High Risk Site’.

39. Please provide details about how rodents, including rats, will be prevented from spreading out from the site. You are required to provide information about site inspections carried out and present copies of receipts (if work undertaken).

The existing building will be assessed for the presence of rodents prior to demolition. Should any rodent or vermin issues arise an external contractor will be appointed to deal with these.

40. Please confirm when an asbestos survey was carried out at the site and include the key findings.

An asbestos survey has been carried out and all asbestos already safely removed by a completent asbestos removal company

41. Complaints often arise from the conduct of builders in an area. Please confirm steps being taken to minimise this e.g. provision of a suitable smoking area, tackling bad language and unnecessary shouting.

As noted previously, the appointed contractor would be registered with the Considerate

Constructor Scheme, enhanced to include CLOCS monitoring as required by Camden Council.

Site specific inductions will focus on not only the on-site construction works but also the surrounding community. Operatives will be advised on how to behave on site and whilst interacting with the local area and its people. It will be made clear to all that they will be representing the site and therefore the appointed contractor. If staff or operatives were to be found or reported as having misbehaved whilst off of the site then it is a reflection on the contractor and they will be asked to leave the site and not to return.

Operatives will also be encouraged to engage the local community by using local public transport and amenities such as local cafes, shops, community gymnasiums etc.

42. If you will be using non-road mobile machinery (NRMM) on site with net power between 37kW and 560kW it will be required to meet the standards set out below. The standards are applicable to both variable and constant speed engines and apply for both PM and NOx emissions. See the Mayor of London webpage ‘Non-Road Mobile Machinery (NRMM)’ for more information, a map of the Central Activity Zone, and for links to the NRMM Register and the NRMM Practical guide: <https://www.london.gov.uk/what-we-do/environment/pollution-and-air-quality/nrmm>

**From 1st September 2015**

**(i) Major Development Sites** – NRMM used on the site of any major development will be required to meet Stage IIIA of EU Directive 97/68/EC

**(ii) Any development site within the Central Activity Zone -** NRMM used on any site within the Central Activity Zone will be required to meet Stage IIIB of EU Directive 97/68/EC

**From 1st September 2020**

**(iii) Any development site -** NRMM used on any site within Greater London will be required to meet Stage IIIB of EU Directive 97/68/EC

**(iv) Any development site within the Central Activity Zone -** NRMM used on any site within the Central Activity Zone will be required to meet Stage IV of EU Directive 97/68/EC

Please provide evidence demonstrating the above requirements will be met by answering the following questions:

1. Construction time period (mm/yy - mm/yy): (TBC):
2. Is the development within the CAZ? : (N)
3. Will the NRMM with net power between 37kW and 560kW meet the standards outlined above? (Y/N): (N):
4. Please provide evidence to demonstrate that all relevant machinery will be registered on the NRMM Register, including the site name under which it has been registered: N/A):
5. Please confirm that an inventory of all NRMM will be kept on site and that all machinery will be regularly serviced and service logs kept on site for inspection: N/A)
6. Please confirm that records will be kept on site which details proof of emission limits, including legible photographs of individual engine plates for all equipment, and that this documentation will be made available to local authority officers as required: Not known at this early stage): N/A

43. Vehicle engine idling (leaving engines running whilst parked or not in traffic) produces avoidable air pollution and can damage the health of drivers and local communities. Camden Council and City of London Corporation lead the London **Idling** **Action Project** to educate drivers about the health impacts of air pollution and the importance of switching off engines as a simple action to help protect the health of all Londoners.

Idling Action calls for businesses and fleet operators to take the **Engines Off pledge** to reduce emissions and improve air quality by asking fleet drivers, employees and subcontractors to avoid idling their engines wherever possible. Free driver training materials are available from the website: <https://idlingaction.london/business/>

Please provide details about how you will reduce avoidable air pollution from engine idling, including whether your organisation has committed to the Engines Off pledge and the number of staff or subcontractors who have been provided with free training materials.

The engines of operative vehicles shall not be kept idling, except for concrete mixers which require to be running to dispense concrete.

A trained traffic marshal will be positioned at the gated entrance to the on Redington Road and would also advise drivers to switch off their engines once vehicles are in place within the suspended parking bay.

The site management will make sure that drivers and construction workers are trained adequately to ensure that vehicle will not be left idling.

SYMBOL IS FOR INTERNAL USE

# Agreement

The agreed contents of this Construction Management Plan must be complied with unless otherwise agreed in writing by the Council. This may require the CMP to be revised by the Developer and reapproved by the Council. The project manager shall work with the Council to review this Construction Management Plan if problems arise in relation to the construction of the development. Any future revised plan must be approved by the Council in writing and complied with thereafter.

It should be noted that any agreed Construction Management Plan does not prejudice further agreements that may be required such as road closures or hoarding licences.

**Signed:** …………………Text, letter

Description automatically generated

**Date:** ……………..……22/7/22

**Print Name:** ………………Mark Skehill…

**Position:** …………Director, Sygnet Style Ltd, Main Contractor

Please submit to: [planningobligations@camden.gov.uk](mailto:planningobligations@camden.gov.uk)

**End of form.**

V2.7