## Project Planner
163 Sumatra Road
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Week Highlight: |  |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Week
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Site Amendments, Methos Statement Health & Saftey | 1 | 8 | 0 | 0 | 0%
Site Clearance to make Safe | 2 | 4 | 0 | 0 | 0%
Excavations and Basement | 10 | 17 | 0 | 0 | 0%
Brickwork & Flooring to Roof Height | 27 | 9 | 0 | 0 | 0%
Roof Construction & Tiling | 37 | 3 | 0 | 0 | 0%
Utilities and Glazing | 40 | 2 | 0 | 0 | 0%
1st Fix Electrics and Plumbing | 41 | 4 | 0 | 0 | 0%
Plaster Boarding, flooring & Soundproofing | 46 | 3 | 0 | 0 | 0%
Plastering | 50 | 2 | 0 | 0 | 0%
Joinery - Skirtings, Architravesl, Doors | 51 | 2 | 0 | 0 | 0%
2nd Fix Electrics & Plumbing | 53 | 4 | 0 | 0 | 0%
Kitchens & Bathrooms | 56 | 4 | 0 | 0 | 0%
Tiling and Decorating | 59 | 45 | 0 | 0 | 0%
Flooring | 64 | 2 | 0 | 0 | 0%
Cleaning, Landscaping, Sound Testing, EPC, Gas Certs Etc | 65 | 4 | 0 | 0 | 0%
Activity 16 | 0 | 0 | 0 | 0 | 0%
Activity 17 | 0 | 0 | 0 | 0 | 0%
Activity 18 | 0 | 0 | 0 | 0 | 0%
Activity 19 | 0 | 0 | 0 | 0 | 0%
Activity 20 | 0 | 0 | 0 | 0 | 0%
Activity 21 | 0 | 0 | 0 | 0 | 0%
Activity 22 | 0 | 0 | 0 | 0 | 0%
Activity 23 | 0 | 0 | 0 | 0 | 0%
Activity 24 | 0 | 0 | 0 | 0 | 0%
Activity 25 | 0 | 0 | 0 | 0 | 0%
Activity 26 | 0 | 0 | 0 | 0 | 0%

## Sheet1
163 Sumatra Road
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Week Highlight: |  |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Week
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Site Amendments, Method Statement Health & Saftey | 1 | 8 | 0 | 0 | 0%
Site Clearance to make Safe | 2 | 4 | 0 | 0 | 0%
Excavations and Basement | 10 | 17 | 0 | 0 | 0%
Brickwork & Flooring to Roof Height | 27 | 9 | 0 | 0 | 0%
Roof Construction & Tiling | 37 | 3 | 0 | 0 | 0%
Utilities and Glazing | 40 | 2 | 0 | 0 | 0%
1st Fix Electrics and Plumbing | 41 | 4 | 0 | 0 | 0%
Plaster Boarding, flooring & Soundproofing | 46 | 3 | 0 | 0 | 0%
Plastering | 50 | 2 | 0 | 0 | 0%
Joinery - Skirtings, Architravesl, Doors | 51 | 2 | 0 | 0 | 0%
2nd Fix Electrics & Plumbing | 53 | 4 | 0 | 0 | 0%
Kitchens & Bathrooms | 56 | 4 | 0 | 0 | 0%
Tiling and Decorating | 59 | 45 | 0 | 0 | 0%
Flooring | 64 | 2 | 0 | 0 | 0%
Cleaning, Landscaping, Sound Testing, EPC, Gas Certs Etc | 65 | 4 | 0 | 0 | 0%